## Work List
Exported on: 2026-09-07 08:57:41
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: DEVPUR PRATAHAM
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1708006023/IC/22012034889023 — कूप निमार्ण कार्य सिंचाई हेतु समुदाय के लिये मुकेश अहिरवार के खेत के पास ग्राम देवपुरप्रथम | New | 0 | 0 | 2025-01-26
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708006023/IF/22012035307076 — हितेषी खेत तालाब हरपालसिंह पिता रघुनाथ सिंह ग्राम मनकपुरा , देवपुरप्रथम | Approved | 0 | 0 | 2025-01-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006023/IF/22012035591940 — एक बगिया माँ के नाम नीमाबाई अहिरवार/जगना अहिरवार भू स्वामी (सम्बन्ध पति) ग्राम पंचायत देवपुर प्रथम | Ongoing | 282605.93 | 1800 | 2025-08-29
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006023/IF/22012035607816 — एक बगिया माँ के नाम प्रमिला अहिरवार पति गुड्डन अहिरवार भू स्वामी (सम्बन्ध पति) ग्राम पंचायत देवपुर प | New | 0 | 0 | 2025-08-14
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/5988391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106876039 | Ongoing | 27000 | 7200 | 2026-05-15
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/5989056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106269225 | Ongoing | 27000 | 7200 | 2026-04-19
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/6001073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117949890 | Ongoing | 27000 | 0 | 2026-04-19
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/6002497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123410006 | Ongoing | 27000 | 0 | 2026-08-30
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/6003361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122034140 | Ongoing | 27000 | 0 | 2026-08-30
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006023/IF/IAY/6243008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106514467 | Ongoing | 27000 | 3600 | 2026-07-04
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1708006023/RC/22012034842427 — सुदूर सड़क ग्रेवल रोड निर्माण कार्य टौरे मोहल्ला से हजरत मोहल्ला तक ग्राम पंचायत देवपुर प्रथम | Ongoing | 1924000 | 0 | 2025-04-28
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006023/RC/22012034850242 — सीमेंट कंक्रीट निर्माण कार्य मेन रोड से नन्हे भाई आदिवासी के घर तक ग्राम पंचायत देवपुर प्रथम | Ongoing | 42000 | 0 | 2025-12-07
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708006023/RS/22012035135435 — नाली निर्माण कार्य ग्राम मनकपुरा में स्कूल की पुलिया से परसोदन यादव के घर की ओर ग्राम पंचायत देवपुर | Approved | 45000 | 0 | 2024-10-02
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708006023/WC/22012035228747 — सार्वजनिक खेततालाब रखैला मोटाखेरा देवपुर प्रथम | Approved | 0 | 0 | 2024-04-25
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708006023/WC/22012035228753 — सार्वजनिक खेततालाब गोलननाला मनकपुरा देवपुर प्रथम | Approved | 0 | 0 | 2024-04-26
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708006023/WC/22012035266405 — सोक पिट निमार्ण सार्वजनिक कूॅप हरिजन बस्ती दलीपुर | Approved | 0 | 0 | 2025-04-02
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708006023/WC/22012035266410 — सोक पिट निमार्ण सार्वजनिक कूॅप आदिवासी बस्ती दलीपुर | Approved | 0 | 0 | 2025-04-02