## Work List
Exported on: 2026-10-26 22:51:15
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: BAMNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708006050/AV/22012034392533 — शांतिधाम निर्माण कार्य बमनी | Ongoing | 257000 | 0 | 2020-04-28
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035313053 — हितेषी खेत तालाब निर्माण कार्य मच्चू / दारूवा अहिरवार ग्राम पंचायत बमनी | New | 0 | 0 | 2025-01-24
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035489850 — हितेषी खेत तालाब निर्माण कार्य रामदास/नरवदिया अहिरवार पात्रता एस0सी0 | Approved | 0 | 0 | 2025-04-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035489872 — हितेषी खेत तालाब निर्माण कार्य कल्ला/गोला अहिरवार पात्रता एस0सी0 | Approved | 399226.48 | 0 | 2025-04-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035519954 — हितेषी खेत तालाब निर्माण कार्य कल्ला/गोला अहिरवार पात्रता एस0सी0 | Approved | 0 | 0 | 2025-04-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035520208 — HITAISHI KHET TALAB NIRMAN KARYA MACHCHU / DARUWA AHIRWAR | New | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006050/IF/22012035520214 — HITAISHI KHET TALAB NIRMAN KARYA MACHCHU / DARUWA AHIRWAR | Approved | 399226.48 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708006050/IF/22012035650474 — PMAYG MP118820600 | Ongoing | 23490 | 0 | 2026-01-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708006050/IF/22012035650480 — PMAYG MP150007220 | Ongoing | 23490 | 0 | 2026-01-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708006050/IF/22012035650481 — PMAYG MP148251787 | Ongoing | 23490 | 0 | 2026-01-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4622404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126808127 | Ongoing | 27000 | 15900 | 2025-09-21
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4652808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145858080 | Ongoing | 27000 | 0 | 2025-08-19
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4664839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150088784 | Physically Completed | 27000 | 3300 | 2024-11-21 | 2026-09-27
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4767968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123569373 | Approved | 27000 | 0 | 2024-09-30
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4801750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150091407 | Ongoing | 27000 | 0 | 2025-03-06
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4960802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125336947 | Ongoing | 27000 | 0 | 2025-05-06
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4982042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145860887 | Ongoing | 27000 | 0 | 2025-05-06
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/4983042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148240239 | Ongoing | 27000 | 0 | 2025-05-06
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/5102211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148437161 | Ongoing | 27000 | 0 | 2025-04-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/5105899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150038437 | Physically Completed | 27000 | 6600 | 2025-08-19 | 2026-09-06
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006050/IF/IAY/5729125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126552187 | Ongoing | 27000 | 0 | 2025-09-21
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1708006050/LD/22012034959898 — खकरी निर्माण कार्य मुक्ति धाम के के चारो ओर बमनी | Approved | 0 | 0 | 2025-08-15
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006050/RS/22012035129687 — नाली निर्माण कार्य बिंदा के घर से बड़ी नाली तक ग्राम पंचायत बमनी | Approved | 14000 | 0 | 2024-06-08
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006050/RS/22012035138821 — नाली निर्माण कार्य बिहारी यादव के घर से आशाराम के मकान तक ग्राम पंचायत बमनी | Ongoing | 24000 | 0 | 2025-12-30
BADA MALEHARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006050/WC/22012035169054 — खेत तालाब निर्माण कार्य शांतिधाम के पास ग्राम पंचायत बमनी | New | 0 | 0 | 2024-01-24
BADA MALEHARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708006050/WC/22012035169060 — परकोलेसन निर्माण कार्य महेश दुबे के खेत के पास ग्राम पंचायत बमनी | New | 0 | 0 | 2024-01-24
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006050/WC/22012035252003 — परकोलेसन टेंक निर्माण कार्य पटरुआ पहाड़ी के पास ग्राम बमनी | Approved | 0 | 0 | 2025-01-26