## Work List
Exported on: 2026-10-28 17:19:45
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: KARKI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1708006074/AV/22012034507146 — बाऊंड्रीवाल निर्माण कार्य शा0प्रा0 शाला गुंजारी | Ongoing | 670000 | 0 | 2020-02-09
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1708006074/AV/22012034665724 — आंगनवाड़ी भवन निर्माण कार्य केंद्र ग्राम गुंजारी ग्राम पंचायत करकी | Approved | 99000 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural Produce Storage Building for Community | Constr of Food Grain storage | 1708006074/AV/22012034665961 — सामुदायिक परकुलेसन टेंक निर्माण कार्य वीर बहादुर के खेत के पास ग्राम पंचायत करकी | New | 0 | 0 | 2025-04-02
BADA MALEHARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006074/DP/22012034433720 — सार्वजनिक कूप निर्माण बमनोराखुर्द | Ongoing | 511000 | 0 | 2020-09-29
BADA MALEHARA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708006074/DP/22012034566802 — बृक्षाराेपण कार्य उका की पहाडी पर ग्राम गोचीपुरा | Ongoing | 713299.02 | 0 | 2022-09-18
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1708006074/DP/22012034583944 — बृक्षारोपण निर्माण कार्य माध्यमिक शाला परिसर गुंजारी करकी | Ongoing | 665612.42 | 0 | 2024-08-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006074/IC/22012034889743 — सिंचाई कूप निर्माण का धर्मदास यादव के खेत के पास ग्राम पंचायत करकी | Ongoing | 736900.62 | 0 | 2026-01-27
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006074/IC/22012034889765 — सिंचाई कूप निर्माण का रामराजा के खेत के पास ग्राम गोचिपुरा ग्राम पंचायत करकी | New | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006074/IC/22012034889767 — सिंचाई कूप निर्माण का परमलाल यादव के खेत के पास ग्राम पंचायत करकी | New | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006074/IC/22012034889829 — सिंचाई कूप निर्माण का गौरी बाई विश्वकर्मा के खेत के पास ग्राम पंचायत करकी | New | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708006074/IF/22012035349287 — हितेषी खेत तालाब लोकपाल सिंह / प्यारे जू ग्राम गोचीपुरा ग्राम पंचायत करकी | New | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708006074/IF/22012035349318 — हितेषी खेत तालाब जानकी बाई / परम लाल यादव ग्राम गोचीपुरा ग्राम पंचायत करकी | Approved | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708006074/IF/22012035349341 — Hiteshi khet talab muluva sour / Pirva sour gram Gochipura gram panchayat karki | Approved | 0 | 0 | 2025-04-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006074/IF/22012035619783 — एक बगिया माँ के नाम रुकमनी राजे/माधव सिंह भू स्वामी (सम्बन्ध पति) ग्राम पंचायत करकी | New | 0 | 0 | 2025-08-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006074/IF/22012035632251 — एक बगिया माँ के नाम बबली राजा/शेलेन्द्र सिंह भू स्वामी (सम्बन्ध पति) ग्राम गोरा ग्राम पंचायत करकी | Ongoing | 275925.18 | 800 | 2025-11-21
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006074/IF/22012035633243 — एक बगिया माँ के नाम नन्हीबाई यादव/रामचरण यादव भू स्वामी (सम्बन्ध पति) ग्राम पंचायत करकी | New | 0 | 0 | 2025-10-02
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006074/IF/22012035637392 — एक बगिया माँ के नाम अवदेश राजा/ विपेंद्र सिंह भू स्वामी (सम्बन्ध पति) ग्राम गोरा पंचायत करकी | Ongoing | 275925.18 | 1450 | 2025-12-08
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006074/IF/22012035637399 — एक बगिया माँ के नाम संतोष राजा/रामराजा भू स्वामी (सम्बन्ध पति) ग्राम गोरा पंचायत करकी | Approved | 0 | 0 | 2025-10-02
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006074/IF/22012035658921 — हितेषी खेत तालाब निर्माण कार्य भुमनीदीन यादव/ परमलाल यादव ग्राम गोंचीपुरा ग्राम पंचायत करकी | Approved | 0 | 0 | 2025-10-02
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006074/IF/22012035658932 — हितेषी खेत तालाब निर्माण कार्य मुलुवा सौर/पिरवा सौर ग्राम गोंचीपुरा ग्राम पंचायत करकी | Approved | 0 | 0 | 2025-10-02
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6028445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122500301 | Ongoing | 27000 | 0 | 2026-06-16
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6265563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126534350 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6406893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124864241 | Approved | 27000 | 0 | 2025-04-09
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6408785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124484776 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6409367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115870459 | Approved | 27000 | 0 | 2025-07-09
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6418482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124163934 | Approved | 27000 | 0 | 2026-02-13
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6421931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124810892 | Approved | 27000 | 0 | 2026-02-16
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6422387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126546015 | Approved | 27000 | 0 | 2025-06-23
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006074/IF/IAY/6423039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116045484 | Approved | 27000 | 0 | 2026-03-12
BADA MALEHARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1708006074/WC/22012034618389 — सार्वजनिक खेत तालाब निर्मांण कार्य- गोंचीपुरा ग्रामपंचायत करकी | Ongoing | 332962.02 | 0 | 2021-02-27