## Work List
Exported on: 2026-09-11 11:22:59
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: PANPA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/5767459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105184336 | Ongoing | 27000 | 0 | 2025-09-01
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/5769058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151156456 | Ongoing | 27000 | 0 | 2025-09-01
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/5983781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145363585 | Ongoing | 27000 | 0 | 2026-06-04
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/5998511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100685880 | Physically Completed | 27000 | 0 | 2026-06-04 | 2026-09-06
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/6000454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126273266 | Ongoing | 27000 | 0 | 2026-06-04
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/6000712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881405 | Ongoing | 27000 | 0 | 2026-09-08
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/6000713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881496 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/6027664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151156031 | Ongoing | 27000 | 0 | 2026-07-12
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006079/IF/IAY/6228843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126017423 | Ongoing | 27000 | 0 | 2026-07-26
BADA MALEHARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006079/RC/22012034851762 — सी सी रोड निर्माण कार्य मोहन आदिवासी के घर से मन्जुवा आदिवासी के घर की ओर ग्राम पंचायत पनया | Physically Completed | 50000 | 0 | 2026-04-21 | 2026-09-09
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708006079/RS/22012035135941 — नाली निर्माण कार्य मोनापाल के घर से नंन्हे भैया पाल के घर की ओर ग्राम पंचायत पनया | Approved | 21000 | 0 | 2025-02-04
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708006079/WC/22012035266680 — सोक पिट निमार्ण कार्य हैण्ड पम्प ताज मोहम्मद के मकान के पास पनया | Approved | 0 | 0 | 2025-04-02
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708006079/WC/22012035266684 — सोक पिट निमार्ण कार्य सार्वजनिक कूप मजार के पास पनया | Approved | 0 | 0 | 2025-04-02