## Work List
Exported on: 2026-10-23 11:03:14
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: NARAYANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708008031/DP/22012034617931 — Braksharopan nirman karya mender pariser per agra gp narayenpura | Approved | 0 | 0 | 2024-06-10
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708008031/DP/22012034617934 — Braksharopan nirman karya mandir pariser narayenpura Gp narayenpura | Approved | 0 | 0 | 2024-06-10
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1708008031/DP/22012034618573 — सार्वजनिक वृक्षारोपण कार्य हनुमान मंदिर परिसर नारायणपुरा | Ongoing | 173308.58 | 0 | 2024-08-01
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1708008031/DP/22012034618574 — वृक्षारोपण कार्य देवी जी मंदिर परिसर अगरा | Ongoing | 173308.58 | 0 | 2024-07-11
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708008031/DP/22012034627846 — सार्वजनिक वृक्षारोपण कार्य धवा बब्‍बा के खेत के पास | Approved | 0 | 0 | 2024-06-08
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1708008031/DP/22012034628041 — sarvjanik briksharopan karya dhaba babba ke khet ke pass gp narayanpura | Approved | 0 | 0 | 2024-08-16
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708008031/DP/22012034628043 — sarvjanik briksharopan karya dhaba babba ke khet ke pass gp narayanpura | Approved | 0 | 0 | 2024-08-16
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034887253 — सार्वजनिक सिंचाई कूप निर्माण कार्य मुकेश रैकवार के खेत के पास | New | 0 | 0 | 2024-10-02
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034887423 — सार्वजनिक कूप निर्माण कार्य गौशाला के पास | New | 0 | 0 | 2024-10-02
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034887638 — सार्वजनिक कूप निर्माण कार्य गौशाला के पास | Ongoing | 597086.08 | 0 | 2025-05-12
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034889341 — सार्वजनिक सिंचाई कूप निर्माण कार्य रजुआ अहिरवार के खेत के पास | New | 0 | 0 | 2025-01-25
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034890290 — सार्वजनिक कूप निर्माण कार्य शांतिधाम के पास | New | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708008031/IC/22012034890291 — सार्वजनिक कूप निर्माण कार्य मुकेश रैकवार के खेत के पास | New | 0 | 0 | 2025-04-14
BIJAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008031/IF/22012034849591 — Nandan Fallodhan Brachharopan Karya Ram Dulari / Chuttan Sahu | Ongoing | 117912.51 | 0 | 2021-10-18
BIJAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008031/IF/22012034849596 — Nandan Fallodhan Brachharopan Karya Laxmi devi / Swami Sahu | Ongoing | 117912.51 | 0 | 2021-10-18
BIJAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008031/IF/22012034849597 — Nandan Fallodhan Brachharopan Karya Kiran / Bhagirath Sahu | Ongoing | 117912.51 | 0 | 2021-10-20
BIJAWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708008031/IF/22012035142568 — पशु शेट निर्माण कार्य उर्मिला देवी / प्रमोद साहू ग्राम अगर ग्राम पंचायत नारायणपुरा | Ongoing | 116453.91 | 0 | 2024-01-24
BIJAWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708008031/IF/22012035142574 — पशु शेट निर्माण कार्य सुषमा साहू / प्रबेश साहू ग्राम अगर ग्राम पंचायत नारायणपुरा | Ongoing | 116120.22 | 0 | 2024-01-24
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708008031/IF/22012035237887 — खेत तालाब निर्माण कार्य राकेश रैकवार के खेत के पास | Approved | 0 | 0 | 2024-06-08
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Agro Forestry Block Plantation for Individual | Plantation | 1708008031/IF/22012035254726 — BRAKSHAPORA NIRMAN KARYA DESHRAJ / PARMANAND SHUKLA NARANPURA | Ongoing | 145050.83 | 0 | 2024-12-28
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708008031/IF/22012035283606 — कपिलधारा कूप निर्माण कार्य श्रीमति सुनिया/मुन्‍नी लाल कोंदर | Approved | 0 | 0 | 2024-10-02
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708008031/IF/22012035310273 — खेत तालाब निर्माण कार्य राजू अहिरवार के खेत के पास | New | 0 | 0 | 2025-01-25
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708008031/IF/22012035523957 — recharge structure kapildhara koop ramsevak jatav narayanpura | New | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708008031/IF/22012035523984 — recharge structure kapildhara koop gorishankar/ baldu sen | Approved | 3000 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708008031/IF/22012035524002 — recharge structure kapildhara koop dharmdas /nannu prajapati narayanpura | Ongoing | 3000 | 0 | 2025-05-24
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708008031/IF/22012035524015 — recharge structure kapildhara koop gokul / salla jatav | Ongoing | 3000 | 0 | 2025-05-24
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4535994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102919628 | Ongoing | 27000 | 0 | 2025-05-27
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4602610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123971970 | Ongoing | 27000 | 0 | 2026-02-01
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4742264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113674216 | Ongoing | 27000 | 0 | 2026-02-01
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4927249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123975323 | Ongoing | 27000 | 0 | 2025-05-27
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4927910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123971292 | Ongoing | 27000 | 0 | 2025-05-27
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4928941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126697062 | Ongoing | 27000 | 0 | 2025-05-27
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/4932520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151233989 | Ongoing | 27000 | 0 | 2025-06-10
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/5779868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123977971 | Ongoing | 27000 | 0 | 2025-09-16
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/5780611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122945399 | Ongoing | 27000 | 0 | 2025-10-28
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/5780929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123974916 | Physically Completed | 23490 | 0 | 2026-02-03 | 2026-08-02
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008031/IF/IAY/5780930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123980225 | Ongoing | 27000 | 0 | 2026-02-03
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1708008031/LD/22012034947708 — चारागाह विकास कार्य गौशाला के पास नारायणपुरा | Approved | 964293.82 | 0 | 2024-10-02
BIJAWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708008031/WC/22012034874490 — Percolation Tank Sarju Jatav ke khet ke Pass Narayanpura (RFR) | Ongoing | 362806.8 | 0 | 2021-11-25
BIJAWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708008031/WC/22012034874503 — Mini Percolation Tank Nanna Prajapati ke khet ke Pass Narayanpura (RFR) | Ongoing | 356438.39 | 0 | 2021-11-25
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008031/WC/22012035205937 — gravin nirman karya ganesh pal ke khet ke pass gp narayenpura | Approved | 0 | 0 | 2024-06-10
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708008031/WC/22012035205940 — gravin nirman karya hajari kushwaha ke khet ke pass gp narayenpura | Approved | 0 | 0 | 2024-06-10
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708008031/WC/22012035205966 — gravin nirman karya lakshmi raikwar ke khet ke pass gp narayenpura | Approved | 0 | 0 | 2024-06-10
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008031/WC/22012035238293 — लूज बोल्‍डर चैक डेम निर्माण कार्य जंगरिया के आगे नाला पर 10 नंग | Approved | 0 | 0 | 2024-10-02
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008031/WC/22012035255116 — सार्वजनिक खेत तालाब निर्माण कार्य राजू अहिरवार के खेत के पास | Approved | 0 | 0 | 2025-01-25
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008031/WC/22012035255117 — सार्वजनिक खेत तालाब निर्माण कार्य बदनिया के पास | Approved | 0 | 0 | 2025-01-25
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008031/WC/22012035275710 — samudayak khet talab goshala ke pass narayanpura | Ongoing | 450885.64 | 0 | 2025-05-07
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008031/WC/22012035276314 — सार्वजनिक खेत तालाब निर्माण कार्यों गोशाला के समीप नारायणपुरा | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008031/WC/22012035300969 — रिचार्ज पिट निर्माण कार्य सार्वजनिक कूप धोवी मोहल्ला के समीप | Approved | 16000 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008031/WC/22012035300975 — रिचार्ज पिट निर्माण कार्य सार्वजनिक कुआं गोरिशंकर/ बब्बलू सेन के पास | Ongoing | 16000 | 0 | 2025-05-25
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008031/WC/22012035300984 — रिचार्ज पिट निर्माण कार्य सार्वजनिक कुआं राज्जू कंकोटी jatav के पास | Approved | 16000 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008031/WC/22012035300996 — रिचार्ज पिट निर्माण कार्य सार्वजनिक कूप धर्मदास के कूप के पास | Approved | 16000 | 0 | 2025-04-14