## Work List
Exported on: 2026-10-13 18:44:49
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: MAJHGUWAKALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BIJAWAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1708008044/AV/22012034641870 — Nali nirman karya Rajkumari kushwaha ke ghar se manghata ki puliya tak g.p. majhguwakala | Ongoing | 105000 | 0 | 2025-03-05
BIJAWAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Village/Rural Haat for community / Construction of Rural Haat Building for Community | Construction of Village Haats | 1708008044/AV/22012034664856 — चबूतरा निर्माण कार्य प्रेमलाल के घर के पास पुनगुंवा | Approved | 11000 | 0 | 2025-01-25
BIJAWAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Village/Rural Haat for community / Construction of Rural Haat Building for Community | Construction of Village Haats | 1708008044/AV/22012034664857 — चबूतरा निर्माण कार्य मिजाजी यादव के घर के पास ग्राम पुनगुंवा | Approved | 11000 | 0 | 2025-01-24
BIJAWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708008044/AV/22012034666215 — पुलिया निर्माण कार्य हरिजन बस्‍ती खिलैंया अहिरवार के घर के पास | Ongoing | 59000 | 0 | 2025-06-14
BIJAWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708008044/IF/22012034588519 — pashu shed nirman karya Aarti / Ramprasad | Ongoing | 101273.16 | 0 | 2020-09-05
BIJAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008044/IF/22012034848458 — Nandan Fallodhan Brachharopan Karya Ramprakash / Siyaram Boudhaliya | Ongoing | 117912.51 | 0 | 2021-10-04
BIJAWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008044/IF/22012034851638 — Nandan Fallodhan Brachharopan Karya Jagmohan Yadav | Ongoing | 117912.51 | 0 | 2021-10-04
BIJAWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1708008044/IF/22012035085195 — पशुशेड निर्माण कार्य श्री हीरालाल/बिहारीलाल कुशवाहा | Ongoing | 125546.98 | 0 | 2023-06-19
BIJAWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708008044/IF/22012035136068 — पशुशेड निर्माण कार्य श्री सावित्री/रतीराम कुशवाहा | Ongoing | 125546.98 | 0 | 2023-09-12
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708008044/IF/22012035551858 — dugwell recharge pit range ke samne | New | 0 | 0 | 2025-04-10
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008044/IF/22012035594466 — एक बगिया माँ के नाम श्रीमति बतीबाई/जगदीश कुशवाहा (भूस्वामी श्री जगदीश कुशवाहा, पति) | Ongoing | 270536.27 | 23200 | 2025-09-03
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708008044/IF/22012035597348 — एक बगिया माँ के नाम श्रीमति गुमनी बाई/कन्‍दू कुशवाहा (भूस्वामी श्री कन्‍दू कुशवाहा, पति) | Approved | 0 | 0 | 2025-08-15
BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5778863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127214193 | Approved | 27000 | 0 | 2025-02-24
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5900420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123995561 | Ongoing | 27000 | 12600 | 2026-07-15
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5900421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123997189 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5900736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120821353 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5900777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148752855 | Ongoing | 27000 | 12600 | 2026-07-15
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5901537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118647997 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/5902490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123429036 | Ongoing | 27000 | 12600 | 2026-07-15
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6078480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118646415 | Ongoing | 27000 | 14700 | 2026-07-15
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6081686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121972767 | Ongoing | 27000 | 15000 | 2026-07-15
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6083297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123222641 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6083667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123519779 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6084766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124294683 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6084767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124296812 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6098232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147411880 | Ongoing | 27000 | 15000 | 2026-07-15
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6099290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148750632 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6283572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148750245 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6323086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148749829 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6323656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119091771 | Approved | 27000 | 0 | 2026-02-03
BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708008044/IF/IAY/6384318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148752773 | Approved | 27000 | 0 | 2026-03-13
BIJAWAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708008044/RC/22012034839138 — सीसी रोड एवं नाली निर्माण कार्य हरप्रसाद खंगार के घर से रतिराम यादव के घर की ओर | Ongoing | 93000 | 0 | 2025-03-18
BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708008044/WC/22012035244902 — मिनी परकोलेशन टैंक निर्माण हरदुकोर हार में | Approved | 0 | 0 | 2024-10-02
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035261580 — बोल्टर चेक डेम निर्माण कार्य मुढ़ी नाला पर 10 नग ग्राम पुनगुआ ग्राम पंचयात मजगुआ कला | Approved | 0 | 0 | 2025-04-11
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035261592 — बोल्टर चेक डेम निर्माण कार्य कलू नाला पर 10 नग ग्राम पुनगुआ ग्राम पंचयात मजगुआ कला | Approved | 0 | 0 | 2025-04-04
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035261598 — बोल्टर चेक डेम निर्माण कार्य चमर्याऊ नाला नाला पर 10 नग ग्राम पुनगुआ ग्राम पंचयात मजगुआ कला | Approved | 0 | 0 | 2025-04-04
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035276469 — सार्वजनिक खेत तालाब निर्माण कार्य हरदुकोर हार में | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035288350 — सार्वजनिक खेत तालाब निर्माण कार्य कालू बगैचा के पास | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035288361 — सार्वजनिक खेत तालाब निर्माण कार्य सैरा नाला के पास | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035288375 — सार्वजनिक खेत तालाब निर्माण कार्य मनघटा के पास | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035288386 — सार्वजनिक खेत तालाब निर्माण कार्य दशरथ यादव के खेत के पास | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008044/WC/22012035311451 — dugwell recharge pit range ke samne | New | 0 | 0 | 2025-04-10
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708008044/WC/22012035311472 — dugwell recharge pit highschool k koop k pass | Approved | 3000 | 0 | 2025-04-10
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035316109 — Percolation tank Nirman Karya lamati Nala per gram Punguaa Gram Panchayat majhgawan Kala 10 nag | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035316133 — Percolation tank Nirman Karya Mahua jawab Nala per gram Punguaa Gram Panchayat majhgawan Kala 10 | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035316510 — बोल्टर चेक डेम निर्माण कार्य लमती नाला पर 10 नग ग्राम पुनगुआ ग्राम पंचयात मजगुआ कला | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008044/WC/22012035316511 — बोल्टर चेक डेम निर्माण कार्य महुआ जुआब नाला पर 10 नग ग्राम पुनगुआ ग्राम पंचयात मजगुआ कला | Approved | 0 | 0 | 2025-04-14
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708008044/WC/22012035329109 — सार्वजनिक खेत तालाब निर्माण कार्य मउआजुआब के पास | Approved | 0 | 0 | 2026-01-25
BIJAWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1708008044/WH/22012034945656 — सार्वजनिक खेत तालाब निर्माण कार्य महुआ जवाब के पास ग्राम पुनगुआ ग्राम पंचायत मजगांव कला | Approved | 0 | 0 | 2026-01-25