## Work List
Exported on: 2026-09-11 14:43:09
Filters applied:
Data source: VBGRAMG
District: PANNA
Block: All
Panchayat: TARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1709002011/IF/22012034588465 — ब़क्षारोपण निर्माण कार्य रामसजीवन/रामकिशुन कुशवाहा ग्राम पंचायत तारा | Ongoing | 113100 | 0 | 2020-07-26
PANNA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1709002011/IF/22012034588780 — ब़क्षारोपण निर्माण कार्य श्‍याम बाई/किशोरीलाल ग्राम पंचायत तारा | Ongoing | 113100 | 0 | 2021-02-10
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709002011/IF/22012035348872 — खेत तालाब निर्माण कार्य जमुना प्रसाद / रामप्रसाद ग्राम पंचायत तारा | Approved | 189623.12 | 0 | 2025-04-14
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709002011/IF/22012035349041 — खेत तालाब निर्माण कार्य सखाराम/काशीराम कुशवाहा ग्राम पंचायत तारा | Approved | 189623.12 | 0 | 2025-04-14
PANNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/4771284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124776209 | Ongoing | 27000 | 0 | 2024-11-12
PANNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/4878444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127064250 | Ongoing | 27000 | 0 | 2025-02-19
PANNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/4885344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127066392 | Ongoing | 27000 | 0 | 2025-02-19
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/4967419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127056502 | Ongoing | 27000 | 0 | 2025-04-03
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5507784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127054108 | Ongoing | 27000 | 0 | 2025-05-07
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5747548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123595409 | Ongoing | 27000 | 0 | 2025-08-24
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5935614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123429246 | Ongoing | 27000 | 10800 | 2026-07-06
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5935708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126130839 | Ongoing | 27000 | 16200 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5936290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116952056 | Ongoing | 27000 | 0 | 2026-07-06
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5937865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126151758 | Ongoing | 27000 | 12600 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5937993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127052647 | Ongoing | 27000 | 8400 | 2026-07-06
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5937994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127053647 | Ongoing | 27000 | 4200 | 2026-07-20
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5937996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127075821 | Approved | 27000 | 0 | 2026-01-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5938164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127059782 | Ongoing | 27000 | 0 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5938193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125763089 | Ongoing | 27000 | 0 | 2026-08-04
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5939146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145904843 | Ongoing | 27000 | 0 | 2026-04-23
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5939165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127045339 | Approved | 27000 | 0 | 2026-01-27
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5939195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126196920 | Ongoing | 27000 | 8400 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5939196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127055554 | Ongoing | 27000 | 0 | 2026-04-24
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5940286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126197885 | Ongoing | 27000 | 7800 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5940812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125766848 | Ongoing | 27000 | 8100 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125751728 | Ongoing | 27000 | 3900 | 2026-04-24
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127062777 | Approved | 27000 | 0 | 2026-01-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126135401 | Ongoing | 27000 | 8400 | 2026-04-23
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125922854 | Ongoing | 27000 | 16200 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127047318 | Ongoing | 27000 | 0 | 2026-04-24
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127058160 | Ongoing | 27000 | 8400 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127058785 | Ongoing | 27000 | 0 | 2026-07-06
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5941976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127060247 | Approved | 27000 | 0 | 2026-01-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5942522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127073437 | Ongoing | 27000 | 4200 | 2026-07-06
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/5943291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127065399 | Approved | 27000 | 0 | 2026-01-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/6011878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127396830 | Ongoing | 27000 | 8400 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/6019628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127049791 | Ongoing | 27000 | 8400 | 2026-07-20
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/6022352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127061783 | Ongoing | 27000 | 0 | 2026-07-06
PANNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/6025454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133208725 | Ongoing | 27000 | 8400 | 2026-07-20
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/6060760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127075165 | Approved | 27000 | 0 | 2026-02-26
PANNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709002011/IF/IAY/706618 — Construction of IAY House -IAY REG. NO. MP1521555 | Ongoing | 27000 | 0 | 2025-09-24
PANNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709002011/WC/22012035283410 — DUG WELL RECHARGE SCHOOL PARISAR TARA | Ongoing | 25899.46 | 0 | 2025-04-26
PANNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709002011/WC/22012035283415 — DUG WELL RECHARGE SHANTIDHAM KE PAS TARA | Ongoing | 25899.46 | 0 | 2025-04-26
PANNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709002011/WC/22012035283423 — DUG WELL RECHARGE KABIR AASHRAM KE PAS TARA | Ongoing | 25899.46 | 0 | 2025-04-26
PANNA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1709/RC/22012034566782 — सुदूर संपर्क सड़क मार्ग तारा से शंकरपुरा से सकतपुरा तक | Ongoing | 10312000 | 0 | 2021-10-18