## Work List
Exported on: 2026-09-02 23:53:11
Filters applied:
Data source: VBGRAMG
District: PANNA
Block: All
Panchayat: BIHARASAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GUNOR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1709003028/AV/22012034547169 — पुलिया निर्माण कार्य सुरनहा नाला पर सिंघासर | Ongoing | 1494968.29 | 0 | 2021-02-26
GUNOR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1709003028/IF/22012034581545 — Vraksha Ropan Nirman Karya Lakhan Singh Singhasar | Ongoing | 115360 | 0 | 2020-07-30
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709003028/IF/22012035409091 — Jalganga Khet Talab Nirman Kary 2025 - Chandrabhan Pandey Sighasar | Ongoing | 185441.45 | 0 | 2025-05-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709003028/IF/22012035535447 — Jalganga Khet Talab Nirman Kary 2025 - Jamuna Prasad Lodhi | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709003028/IF/22012035553440 — Jalganga Khet Talab Nirman Kary 2025 - Deepak Kumar Mishra Sighasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/4781169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128856923 | Ongoing | 27000 | 0 | 2024-11-13
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5135832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128858422 | Ongoing | 27000 | 0 | 2025-04-02
GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5139174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128382660 | Ongoing | 27000 | 0 | 2025-03-25
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5457516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128385140 | Ongoing | 27000 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5696612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128384195 | Ongoing | 27000 | 0 | 2025-07-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5697889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128386448 | Ongoing | 27000 | 0 | 2025-07-21
GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5743145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128387435 | Approved | 27000 | 0 | 2024-10-09
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5745860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128004298 | Ongoing | 27000 | 0 | 2025-10-16
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5950068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131343761 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5950069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131343780 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5953676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132228668 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5954560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127431807 | Approved | 27000 | 0 | 2026-02-05
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5960583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126828462 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5961705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106007098 | Approved | 27000 | 0 | 2026-02-05
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5964347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131739087 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5966125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102261722 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709003028/IF/IAY/5966126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102261731 | Ongoing | 27000 | 0 | 2026-04-23
GUNOR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1709003028/WC/22012034858441 — parkuletion tank nirman karya hanuman ji mandir ke pass singhsar | Ongoing | 652875.32 | 0 | 2022-03-10
GUNOR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1709003028/WC/22012034858444 — parkuletion tank nirman karya bitaiya ke khet k pass | Ongoing | 620448.29 | 0 | 2022-03-10
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258885 — Boulder Check Dam Nirman Kary -Dhurhai Nala Ramroop Badgaiya ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258890 — Boulder Check Dam Nirman Kary - Dhurhai Nala Hakke Lodhi Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258893 — Boulder Check Dam Nirman Kary - Dhurhai Nala Rajkumar Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258895 — Boulder Check Dam Nirman Kary - Dhurhai Nala Sudama Soni Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258897 — Boulder Check Dam Nirman Kary - Dhurhai Nala Rajkishor Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258899 — Boulder Check Dam Nirman Kary - Jhinna Nala Badri Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258900 — Boulder Check Dam Nirman Kary - Jhinna Nala Panchhi Lal Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258902 — Boulder Check Dam Nirman Kary - Jhinna Nala Kandhi Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258904 — Boulder Check Dam Nirman Kary - Jhinna Nala Nandlal Soni Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003028/WC/22012035258905 — Boulder Check Dam Nirman Kary - Jhinna Nala Manoj Soni Ke Khet Pass Bihrasar | Approved | 0 | 0 | 2025-04-01