## Work List
Exported on: 2026-10-23 18:58:08
Filters applied:
Data source: VBGRAMG
District: PANNA
Block: All
Panchayat: PALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GUNOR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1709003033/AV/22012034549319 — Ghat Nirman Karya Pali ke Bhatwa ke talab pass Pali GP Pali | Ongoing | 1450405.27 | 0 | 2021-02-16
GUNOR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1709003033/AV/22012034552225 — Ghat Nirman Karya Bade Ghat par Pul Pass Pali | Ongoing | 1488584.57 | 0 | 2021-03-06
GUNOR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1709003033/DP/22012034599923 — Vashudha Vatika Khabees ke pas PALI | Ongoing | 102745.01 | 35400 | 2023-09-07
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035007667 — Niji Khet me Faloddyan Bhagwandas Sahu S/O Punni Sahu Gram Pali GP Pali | Ongoing | 125831.88 | 10800 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035007669 — Niji Khet me Faloddyan Gilahri Sahu S/O Baldua Sahu Gram Pali, GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035007808 — Niji Khet me Faloddyan Dropti Bai Garg W/O Ramnivas Garg Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035007842 — Niji Khet me Faloddyan Ahilya Bai Upadhyay W/o Birendra Upadhyay Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035007846 — Niji Khet me Faloddyan Omprakash Sahu D/O Mangi Sahu Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035008075 — Niji Khet me Faloddyan Ramdatt Gautam S/O Sabhapati Gautam Gram Pali GP Pali | Ongoing | 124031.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035008080 — Niji Khet me Faloddyan Narendra Upadhyay S/o Shivnarayan Upadhyay Gram Pali GP Pali | Ongoing | 125831.88 | 1800 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035008084 — Niji Khet me Faloddyan chhiddi Sahu S/O Chainu Sahu Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035008089 — Niji Khet me Faloddyan Kanchhedi Kori S/o Pancha Kori Gram Pali, GP Pali | Ongoing | 125831.88 | 7200 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035008098 — Niji Khet me Faloddyan Vinod Garg S/O Rambhuvan Garg Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1709003033/IF/22012035009018 — Niji Khet me Braksharopad Amit Kumar S/O Ramautar Upadhyay Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035009936 — Niji Khet me Faloddyan Ramsharan Upadhyay S/o Awdhesh Upadhyay Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-08
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035009938 — Niji Khet me Faloddyan Matadeen Chaudhari S/O Kaliyan Chaudhari Gram Pali GP Pali | Ongoing | 125831.88 | 5400 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035009970 — Niji Khet me Faloddyan Rajju Chaudhari S/O Chhidiya Chaudhari Gram Pali GP Pali | Ongoing | 125831.88 | 10800 | 2022-09-09
GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003033/IF/22012035009972 — Niji Khet me Faloddyan Ramanuj Gautam S/O Rajkishor Gautam Gram Pali GP Pali | Ongoing | 125831.88 | 0 | 2022-09-09
GUNOR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035142017 — Niji Khet me Faloddyan Baijnath Sahu / Panchma Sahu Gram Pali GP Pali | Ongoing | 133269.6 | 0 | 2023-10-03
GUNOR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035142038 — Niji Khet me Faloddyan Bewa Mulayam Bai Chaudhari W/O Late. Sudama Chaudhari Gram Pali GP Pali | Ongoing | 133269.6 | 0 | 2023-10-05
GUNOR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035142099 — Niji Khet me Faloddyan Mijjee Sekh S/O Muhbat Gram Pali GP Pali | Ongoing | 133269.6 | 0 | 2023-10-05
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035325425 — Khet Talab Jaysingh S/O Phoolsingh Gram Gundaura GP Pali | Ongoing | 146914.69 | 0 | 2025-04-22
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035546171 — JAL GANGA KHET TALAB BHAGWATPRASAD S/O RAJARAM GRAM GUNDAURA GP PALI | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035546180 — JAL GANGA KHET TALAB SANTOSH SINGH S/O GULAB SINGH GRAM GUNDAURA GP PALI | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035546191 — JAL GANGA KHET TALAB SURESH SINGH S/O BHAGWAT PRASAD GRAM GUNDAURA GP PALI | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035546196 — JAL GANGA KHET TALAB RAMDEV UPADHYAY S/O RAMSIYA GRAM PALI GP PALI | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003033/IF/22012035546207 — JAL GANGA KHET TALAB RAMJI UPADHYAY S/O RAM MILAN GRAM PALI GP PALI | Approved | 0 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035590229 — plantation work suman bai pali | Approved | 0 | 0 | 2025-08-10
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035603046 — Ek Bagiya Maa Ke Nam Roshani Garg W/O Vishnu Garg MP09003033001162 | Ongoing | 284423.98 | 0 | 2025-09-12
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035630910 — Ek Bagiya Maa Ke Nam Himanti Upadhyay W/O Ramdev Upadhyay Gram Pali GP Pali | Ongoing | 199623.67 | 0 | 2025-11-02
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035630931 — Ek Bagiya Maa Ke Nam Rajkumari Garg W/O Ramsujan Garg Gram Pali GP Pali | Approved | 199623.67 | 0 | 2025-08-15
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035648598 — Ek Bagiya Maa Ke Nam MP0900303300243 Guddi Singh W/O Santosh Singh Gram Gundaura GP Pali | New | 0 | 0 | 2025-08-16
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035648609 — Ek Bagiya Maa Ke Nam MP0900303300243 Guddi Singh W/O Santosh Singh Gram Gundaura GP Pali | Ongoing | 198700.47 | 0 | 2025-12-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035649088 — Ek Bagiya Maa Ke Nam MP0900303300205 Guddi Chandkuvar W/O Ravendra Singh Gram Gundaura GP Pali | Approved | 198700.47 | 0 | 2025-08-16
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035650542 — Ek Bagiya Maa Ke Nam MP090030330026D Durgawati W/O Moorat Singh Gram Gundaura GP Pali | Ongoing | 198700.47 | 5400 | 2025-12-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035650586 — Ek Bagiya Maa Ke Nam MP090030330026A Mamta Bai Rajput W/O Sahab Singh Gram Gundaura GP Pali | Ongoing | 198700.47 | 0 | 2025-12-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709003033/IF/22012035652793 — Ek Bagiya Maa Ke Nam Aneeta Upadhyay W/O Ramji Upadhyay Gram Pali GP Pali | Ongoing | 198700.47 | 12600 | 2026-01-24
GUNOR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/129801 — Construction of IAY House -IAY REG. NO. MP-09-003-033-001/22763 | Approved | 27000 | 0 | 2016-02-03
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5136181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126781761 | Ongoing | 27000 | 0 | 2025-04-04
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5136383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123609095 | Ongoing | 27000 | 0 | 2025-04-04
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5136772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125034974 | Ongoing | 27000 | 0 | 2025-05-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5141246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126224200 | Ongoing | 27000 | 0 | 2025-08-06
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5141693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126805129 | Ongoing | 27000 | 0 | 2025-05-20
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5166355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126001890 | Ongoing | 27000 | 0 | 2025-05-22
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5166699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125509133 | Ongoing | 27000 | 0 | 2025-04-04
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003033/IF/IAY/5697051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126816375 | Ongoing | 27000 | 0 | 2025-08-06
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1709003033/IF/VB/YD/22012035665493 — GOAT1 | Approved | 0 | 0 | 2026-10-01
GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1709003033/IF/VB/YD/22012035665495 — GOAT2 | Approved | 0 | 0 | 2026-10-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253749 — Boulder check dam nirman karya Umashankar Upadhyay ke khet paas nala me gram Pali gp Pali | Approved | 0 | 0 | 2025-03-08
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253756 — Boulder check dam nirman karya Harvansh Upadhyay ke khet paas nala me gram Pali gp Pali | Approved | 0 | 0 | 2025-03-08
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253825 — Boulder check dam nirman karya Keshkumar Mishra ke khet paas nala me gram Pali gp Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253835 — Boulder check dam nirman karya Khabeesh paas naraiya me gram Pali gp Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253838 — Boulder Check dam nirman karya Ramnaresh Upadhyay ke khet paas pali nala me GP Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253841 — Boulder Check Dam Nirman karya Ramji Upadhyay ke khet paas nala me gram pali GP Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253844 — Boulder Check dam nirman karya Dinesh Chounrha ke khet ke paas nala pali me Gram Pali GP Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035253847 — Boulder Check dam nirman karya Umesh Garg ke khet ke paas nala pali me Gram Pali GP Pali | Approved | 0 | 0 | 2025-03-10
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035255752 — Boulder Check dam nirman karya Dinesh Chounrha ke khet ke paas nala pali me Gram Pali GP Pali | Approved | 244162.1 | 0 | 2025-03-23
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035255754 — Boulder check dam nirman karya Harvansh Upadhyay ke khet paas nala me gram Pali gp Pali | Approved | 244162.1 | 0 | 2025-03-23
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035255755 — Boulder check dam nirman karya Khabeesh paas naraiya me gram Pali gp Pali | Approved | 243662.1 | 0 | 2025-03-23
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035255758 — Boulder Check dam nirman karya Umesh Garg ke khet ke paas nala pali me Gram Pali GP Pali | Approved | 243662.1 | 0 | 2025-03-23
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003033/WC/22012035255759 — Boulder check dam nirman karya Umashankar Upadhyay ke khet paas nala me gram Pali gp Pali | Approved | 244162.1 | 0 | 2025-03-23
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1709003033/WH/22012034939913 — Samudayik Khet Talab Lakhan Choudhri ke ghar pas gram Imaliya Mallju GP Pali | Approved | 0 | 0 | 2024-06-06