## Work List
Exported on: 2026-10-19 19:17:58
Filters applied:
Data source: VBGRAMG
District: PANNA
Block: All
Panchayat: NACHNE
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GUNOR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1709003077/AV/22012034650937 — शांति धाम निर्माण कार्य अमृत सरोवर के पास ग्राम नचने | Ongoing | 330972.38 | 0 | 2025-03-01
GUNOR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1709003077/AV/22012034650938 — शांति धाम निर्माण कार्य चकोढ़ा तालाब के पास सेल्हा | Ongoing | 330972.38 | 0 | 2025-03-01
GUNOR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1709003077/DP/22012034600132 — vashudha vatika nirman amrit sarowar nachne | Ongoing | 101609.01 | 0 | 2023-12-23
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325138 — Jalganga 2025 khet talab nirman karya fattu Kol/Kripal kol | Ongoing | 199899.55 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325165 — Jal ganga 2025 khet talab nirman karya Harbansa Kol/ganpatiya Kol | Ongoing | 199899.55 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325344 — Jal ganga 2025 khet talab nirman karya Tatilal kol/Nandi Lal Kol | Ongoing | 197588.39 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325361 — Jal ganga 2025 khet talab nirman karya Ramnaresh tripathi | Ongoing | 197878.57 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325369 — Jal ganga 2025 khet talab nirman karya Vitla Kol/Dhandu Kol | Ongoing | 197474.38 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325381 — Jal ganga 2025 khet talab nirman karya Hariprasad Lodhi | Ongoing | 199899.55 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325390 — Jal ganga 2025 khet talab nirman karya Sunita kol/Sukhnandan | Ongoing | 199752.17 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035325400 — Jal ganga 2025 khet talab nirman karya Ratilal kol/Lakkhu kol | Ongoing | 198616.83 | 0 | 2025-04-21
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379064 — Jal ganga khet talab nirman karya dayaram Vishwakarma/Ramnath | Ongoing | 199384.8 | 0 | 2025-05-08
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379084 — Jal ganga khet talab nirman karyaKusum Bai/ghamsyam Kol | Ongoing | 199597 | 0 | 2025-05-08
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379127 — Jal ganga khet talab nirman karya Ramniwsh Kol/Braj lal kol | Ongoing | 198111.58 | 0 | 2025-05-08
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379141 — Jal ganga khet talab nirman karya Kaliya Kol/radhe Kol | Ongoing | 198960.39 | 0 | 2025-05-08
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379167 — Jal ganga khet talab nirman karya Paduva Kol/madhova kol | Ongoing | 199172.6 | 0 | 2025-05-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379184 — Jal ganga khet talab nirman karya Sadhuva kol/madhuva kol | Ongoing | 199603.3 | 0 | 2025-05-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035379201 — Jal ganga khet talab nirman karya dhannu kol/mithuva Kol | Ongoing | 199597 | 0 | 2025-05-08
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035407955 — Jalganga khet talab nirman karya Bihari pal/heeralal pal | Approved | 199452.88 | 0 | 2025-04-14
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003077/IF/22012035516326 — Jal ganga 2025 khet talab nirman karya rambhuvan /gulla kol | Approved | 199581.07 | 0 | 2025-04-01
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5695194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127735719 | Ongoing | 27000 | 0 | 2025-08-28
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5695334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127735089 | Ongoing | 27000 | 0 | 2025-08-28
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5703227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134086757 | Ongoing | 27000 | 0 | 2025-08-30
GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5742390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126046550 | Approved | 27000 | 0 | 2025-02-27
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5743301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125853177 | Ongoing | 27000 | 0 | 2025-08-30
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5744307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129888753 | Ongoing | 27000 | 0 | 2025-08-30
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5748959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129637180 | Ongoing | 27000 | 0 | 2025-08-30
GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003077/IF/IAY/5748960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129637331 | Ongoing | 27000 | 0 | 2025-08-30
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153881 — bolder cheak dam nirman karya bitla kol ke khet ke pas selha | Ongoing | 250057.43 | 11400 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153884 — bolder cheak dam nirman karya ramsukh ke khet ke pas selha | Ongoing | 242253.38 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153887 — bolder cheak dam nirman karya rameshwari ke khet ke pas selha | Ongoing | 234449.33 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153888 — bolder cheak dam nirman karya ramesh kol ke khet ke pas selha | Ongoing | 246779.25 | 32400 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153890 — bolder cheak dam nirman karya shripat kol ke khet ke pas selha | Ongoing | 295654.67 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153891 — bolder cheak dam nirman karya pitta kol ke khet ke pas selha | Ongoing | 215703.24 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153893 — bolder cheak dam nirman karya gora kol ke khet ke pas selha | Ongoing | 229792.73 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153894 — bolder cheak dam nirman karya jhinnu kol ke khet ke pas selha | Ongoing | 234496.68 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003077/WC/22012035153901 — Bolder chaek dam nirman karya rajendra kol ke khet ke pas selha | Ongoing | 225166.13 | 0 | 2025-03-01
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1709003077/WC/22012035251600 — Samudayik Talab Machli palan asulkhe pe khet ke pass Nachne | New | 0 | 0 | 2025-01-26
GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1709003077/WC/22012035251601 — Samudayik Talab Machli palan asulkhe pe khet ke pass Nachne | New | 0 | 0 | 2025-01-26
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003077/WC/22012035281706 — Dugwell nirman karya gadesh g mandir ke pas nachne | Approved | 25899.46 | 0 | 2025-04-14
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003077/WC/22012035281711 — Dugwell nirman karya Ramjanki mandir ke pas nachne | Approved | 25899.46 | 0 | 2025-04-14
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003077/WC/22012035281718 — Dugwell nirman karya Dadu pal ke ghar ke pas nachne | Approved | 25899.46 | 0 | 2025-04-14
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003077/WC/22012035281720 — Dugwell nirman karya shankar g mandir ke pas selha | Approved | 25899.46 | 0 | 2025-04-14
GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003077/WC/22012035281726 — Dugwell nirman karya bihari g mandir ke pas selha | Approved | 25899.46 | 0 | 2025-04-14