## Work List
Exported on: 2026-09-14 02:20:38
Filters applied:
Data source: VBGRAMG
District: PANNA
Block: All
Panchayat: KAKARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAHNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1709005013/AV/GIS/34406 — Kakara- Shanti Dham Nirman Kary Mohara Sihar Nadi ke pass | Ongoing | 252107.07 | 0 | 2023-09-25
SHAHNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005013/IF/22012035157061 — KAKRA- Kapildhara koop-Sone lal /mohan patel | Ongoing | 326379.56 | 0 | 2023-10-08
SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1709005013/IF/22012035168686 — KAKRA-medbandhan Kary-Sone lal Patel | Ongoing | 119893.33 | 0 | 2023-10-08
SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005013/IF/22012035531222 — JGSA KAKRA Khet talab nirman kishun lal patel/moti lala | New | 0 | 0 | 2025-04-14
SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005013/IF/22012035531228 — JGSA KAKRA Khet talab nirman kishun lal patel/moti lala | Ongoing | 199365.76 | 0 | 2025-05-25
SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005013/IF/22012035531289 — JGSA KAKRA Khet talab nirman shiv singh /nathu lodhi | Ongoing | 199365.76 | 0 | 2025-05-23
SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005013/IF/22012035532345 — JGSA KAKRA Richarge fit kapildhara koop सुखलालपिता मनसुखा 1709005013/IF/1000053556 | Approved | 25899.46 | 0 | 2025-04-14
SHAHNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/1932097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3911397 | Approved | 27000 | 0 | 2018-08-25
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/4570962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116832636 | Ongoing | 27000 | 0 | 2024-11-18
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/4916967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117932530 | Ongoing | 27000 | 0 | 2025-03-04
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/4918142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116832539 | Ongoing | 27000 | 0 | 2025-03-04
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/4922303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143741976 | Physically Completed | 23490 | 0 | 2025-03-04 | 2026-07-26
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/4924112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129880743 | Ongoing | 27000 | 0 | 2025-03-17
SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/5017682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116832053 | Ongoing | 27000 | 0 | 2025-03-24
SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/5860285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116832471 | Ongoing | 27000 | 0 | 2025-12-01
SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005013/IF/IAY/5932379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118183867 | Ongoing | 27000 | 0 | 2026-05-10
SHAHNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1709005013/WC/VB/22012035334652 — Top Roof Water Harvesting Samudayak swachhata parisar Kakra | Ongoing | 30496.65 | 0 | 2026-09-12
SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1709005013/WH/22012034938066 — ककरा-मसान तलैया जीर्णोद्धार एवम बण्डविस्तार कार्य ककरा | Ongoing | 819000 | 0 | 2023-09-27