## Work List
Exported on: 2026-10-13 10:57:48
Filters applied:
Data source: MGNREGA + VBGRAMG
District: SAGAR
Block: All
Panchayat: GUWARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1710002066/AV/22012034650628 — KHEL MEDAN GWARI | Closed | 0 | 0 | 2023-10-02
KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1710002066/DP/22012034594236 — VASUDHABANDHAN VRAKSHAROPAN | Completed | 55847.4 | 22018.72 | 2023-09-14 | 2026-04-12
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1710002066/FR/22012034325088 — JGSA 2025 khet talab khasra no 314 | Ongoing | 486634.79 | 15138 | 2025-05-14
KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035188527 — KHET TALAB SHAKUN BAI GUWARI | Completed | 319036.72 | 146289 | 2024-02-24 | 2026-04-12
KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035203053 — KHET TALAB RAMSEWAK PITA SURATSINGH | Closed | 0 | 0 | 2023-10-02
KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035203072 — KHET TALAB SANMAN GUWARI | Closed | 385261.22 | 0 | 2024-01-25
KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035203082 — KHET TALAB LAXMI PRASAD GUWARI | Closed | 385861.22 | 0 | 2024-01-25
KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035203091 — KHET TALAB BADRIPRASAD GUWARI | Closed | 385261.22 | 0 | 2024-01-25
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1710002066/IF/22012035431779 — JGSA 2025 RECHARG STACTURE KAPILDHARA SHREE DEVNAYAK BABA KE SAMNE GOVT KOOP | Physically Completed | 27090.78 | 15558 | 2025-05-14 | 2026-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002066/IF/22012035452232 — JGSA 2025 khet talab recharg stracture kapil dhara gokal ahirwar | Approved | 27090.78 | 0 | 2025-04-14
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035516536 — JGSA 2025 KHET TALAB BADRI PRASAD AHIRWAR | Deleted | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035516590 — JGSA 2025 khet talab anand pita bhagirath | Deleted | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035516591 — JGSA 2025 khet talab anand pita bhagirath | Completed | 199510.49 | 53505 | 2025-06-07 | 2026-05-30
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002066/IF/22012035546843 — Jal Ganga Sambhardan Abhiyan Khet talab Badri Prasad | Physically Completed | 199510.49 | 32886 | 2025-06-07 | 2026-06-11
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002066/IF/22012035617855 — Ek Bagiya ma ke naam Laxmi Laxminarayan | Ongoing | 264026.75 | 32220 | 2025-09-12
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002066/IF/IAY/5823674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124437556 | Physically Completed | 23490 | 21924 | 2025-10-29 | 2026-06-06
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002066/IF/IAY/5844873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140743954 | Completed | 23490 | 23490 | 2025-10-29 | 2026-04-10
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002066/IF/IAY/5844874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140743998 | Completed | 23490 | 23229 | 2025-11-22 | 2026-04-23
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002066/IF/IAY/5844875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140744024 | Ongoing | 27000 | 14766 | 2025-10-29
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002066/IF/IAY/5844876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140748375 | Completed | 23490 | 23490 | 2025-10-29 | 2026-04-23
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002066/IF/IAY/5846069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140352815 | Completed | 23490 | 23207 | 2025-10-29 | 2026-04-23
KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1710002066/LD/22012034595096 — CC ROAD BHAGONI KE GHAR SE MANDIR KI | Closed | 176000 | 0 | 2023-04-17
KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002066/RC/22012034652852 — CC ROAD BHAGONI KE GHAR SE MANDIR KI OR | Completed | 88000 | 87958 | 2023-09-08 | 2023-12-20
KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002066/RC/22012034672600 — C C Road Nirman Dwarka Ke Makhan Se Makhan Ke Ghar Ki Or | Ongoing | 67000 | 66166.93 | 2024-01-26
KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002066/RC/22012034832684 — CC ROAD NALI NIRMAN HANUMAN JI MANDIR SE AGANWADI KI OR | Completed | 40000 | 36999.04 | 2025-01-06 | 2026-04-10
KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1710002066/WC/22012035147815 — SAMUDAYIK KHET TALAB GRAM GUWARI | Completed | 690593.29 | 264826.96 | 2024-02-26 | 2026-04-12
KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1710002066/WC/22012035174784 — SAMUDAYIK TALAB GUWARI THAKURBABA KE PASS | Closed | 0 | 0 | 2024-01-25
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1710002066/WC/22012035288529 — JGSA 2025 khet talab khasra no 316 | Ongoing | 492767.91 | 783 | 2025-05-14