## Work List
Exported on: 2026-10-08 13:22:42
Filters applied:
Data source: VBGRAMG
District: SAGAR
Block: All
Panchayat: KARAMPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1710002069/DP/22012034594123 — बसुधा बंदन प्राथमिक शाला के पास करमपुर | Ongoing | 55847.4 | 0 | 2023-09-16
KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1710002069/IF/22012035231611 — khet talab nirman munnalal / mulchand kushwaha karampur | Approved | 0 | 0 | 2024-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002069/IF/22012035355834 — jgsa2025 reacharge structure kapildhara balkuram | New | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002069/IF/22012035396354 — JGSA2025RECHARGE STRUCTURE jasbant | Approved | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1710002069/IF/22012035399166 — Kapildhara koop nirman nandkishor Kushwaha karampur | Approved | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1710002069/IF/22012035411233 — Khet Tablab Nirman Vishnu Gram Lamethi | Ongoing | 147621.16 | 0 | 2025-05-03
KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/4666957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150845171 | Physically Completed | 23490 | 0 | 2025-01-18 | 2026-08-02
KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/4726561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151054256 | Ongoing | 27000 | 0 | 2025-03-26
KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/4774351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126024945 | Ongoing | 27000 | 2100 | 2025-01-25
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/5826953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126024273 | Ongoing | 27000 | 0 | 2026-01-02
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/5845933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151054141 | Ongoing | 27000 | 0 | 2025-11-21
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/5845978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145754359 | Ongoing | 27000 | 0 | 2025-11-10
KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6011677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150616482 | Ongoing | 27000 | 0 | 2026-04-04
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6012686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149925861 | Ongoing | 27000 | 0 | 2026-03-13
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6017063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145438011 | Approved | 27000 | 0 | 2026-01-29
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6033812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149911055 | Approved | 27000 | 0 | 2026-03-08
KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6035738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149907195 | Ongoing | 27000 | 0 | 2026-04-04
KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6097311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145768782 | Approved | 27000 | 0 | 2026-03-18
KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6323017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150616216 | Approved | 27000 | 0 | 2026-05-11
KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002069/IF/IAY/6323077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149925869 | Approved | 27000 | 0 | 2026-05-21
KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1710002069/LD/22012034948964 — Samsan ghat nirman lamethi | Approved | 235393.34 | 0 | 2024-10-02
KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002069/RC/22012034651873 — CC ROAD NIRMAN AMIT ADIWASI KE GHAR SE PRAHALAD KI OR LAMETHI | Ongoing | 45000 | 0 | 2025-01-11
KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002069/RC/22012034653614 — CC ROAD NIRMAN KARYA HANUMAN MANDIR SE MEN ROAD KI OR KARAMPUR | Ongoing | 56100 | 0 | 2024-09-12
KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002069/RC/22012034653618 — CC ROAD NIRMAN KARYA BHUVNESHWARI MATA MANDIR SE MEN ROAD KI OR KARAMPUR | Ongoing | 31000 | 0 | 2024-05-14
KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1710002069/WC/22012035244543 — Samudayik khet talab Karmpur | New | 0 | 0 | 2024-10-02
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1710002069/WC/22012035280785 — JGSA2025RECHARGE STRUCTURE JASbant | New | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1710002069/WC/22012035280786 — JGSA2025RECHARGE STRUCTURE JASbant | New | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1710002069/WC/22012035280787 — JGSA2025RECHARGE STRUCTURE JASbant | New | 0 | 0 | 2025-04-14
KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1710002069/WC/22012035280788 — JGSA2025RECHARGE STRUCTURE JASbant | Approved | 0 | 0 | 2025-04-14