## Work List
Exported on: 2026-09-05 05:56:20
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: UNCHI AUNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TEONTHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1713002020/DP/22012034554070 — DRY BOLDER & PLANTATION KARYA PRAMOD SINGH/ KAMLAKAR SINGH KE KHET KE PAAS | Ongoing | 583190.8 | 0 | 2022-05-18
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713002020/IF/22012035534814 — JGSA khet talab niram kary Dinesh kewat ke khet me | Deleted | 0 | 0 | 2025-04-16
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713002020/IF/22012035534818 — JGSA khet talab niram kary Dinesh kewat ke khet me | Deleted | 0 | 0 | 2025-04-16
TEONTHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/2989981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4949640 | Ongoing | 27000 | 0 | 2026-06-18
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/4830979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142229517 | Ongoing | 27000 | 0 | 2025-05-19
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/5854284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144058876 | Ongoing | 27000 | 0 | 2026-01-12
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/5854683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145083662 | Ongoing | 27000 | 0 | 2025-11-10
TEONTHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/5854848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144072551 | Ongoing | 27000 | 0 | 2025-12-01
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/596828 — Construction of IAY House -IAY REG. NO. MP4326427 | Approved | 27000 | 0 | 2017-02-01
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/596834 — Construction of IAY House -IAY REG. NO. MP4436459 | Approved | 27000 | 0 | 2017-02-01
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/627350 — Construction of IAY House -IAY REG. NO. MP4038613 | Approved | 27000 | 0 | 2017-02-08
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/627372 — Construction of IAY House -IAY REG. NO. MP5076617 | Approved | 27000 | 0 | 2017-02-08
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/627411 — Construction of IAY House -IAY REG. NO. MP5030632 | Approved | 27000 | 0 | 2017-02-08
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/638591 — Construction of IAY House -IAY REG. NO. MP2376718 | Approved | 27000 | 0 | 2017-02-12
TEONTHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713002020/IF/IAY/689001 — Construction of IAY House -IAY REG. NO. MP1130339 | Approved | 27000 | 0 | 2017-03-19
TEONTHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713002020/RC/22012034443509 — पीसीसी रोड नि० रामदुलारे साहू के घर से अजय कुम्हार के घर तक नेदुरा | Ongoing | 75000 | 0 | 2019-04-10
TEONTHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713002020/RC/22012034443513 — पीसीसी रोड नि० श्रीनाथ के घर से रावेन्द्र के घर तक नेदुरा | Ongoing | 95000 | 0 | 2019-05-22
TEONTHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713002020/RC/22012034850380 — PCC ROAD NIRMAN PADRO BASTI ME SCHOOL SE SAMAY LAL KOL KE GHAR TAK | Approved | 110000 | 0 | 2025-10-02
TEONTHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713002020/RC/22012034850382 — PCC ROAD NIRMAN GANESH SINGH KE GHAR SE UMESH SINGH KE PAAS PRADHAN MANTRI SADAK TAK | Ongoing | 110000 | 0 | 2026-01-31
TEONTHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713002020/WH/22012034448558 — jal kshamta vriddhi evam vistarikaran gram bansati talab | Ongoing | 910257.01 | 0 | 2021-05-21
TEONTHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713002020/WH/22012034448559 — jal kshamta vriddhi evam vistarikaran gram parsadi talab | Ongoing | 829413.82 | 0 | 2021-05-21
TEONTHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713002020/WH/22012034920083 — Talab jirnoddhar partapa talab | Ongoing | 655000 | 0 | 2022-03-21
TEONTHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713002020/WH/22012034920138 — Talab jirnoddhar Garga Talab | Ongoing | 673000 | 0 | 2022-03-21
TEONTHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713002020/WH/22012034920146 — Talab jirnoddhar Dodak talab | Ongoing | 682000 | 0 | 2022-03-21