## Work List
Exported on: 2026-09-13 08:21:00
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: PARASI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GANGEV | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1713004066/FP/22012034636823 — नाली निर्माण हनुमना चबूतरा के पास | Ongoing | 83000 | 0 | 2023-10-07
GANGEV | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1713004066/IF/22012034731167 — MEDH BADHAN MOTI SINGH S/O GAJRAJ SINGH KE NIJI KHET ME | Ongoing | 46046.92 | 0 | 2021-05-18
GANGEV | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713004066/IF/22012034978567 — खेत तालाब निर्माण राजकुमार पाठक के भूमि पर | Ongoing | 116607.32 | 0 | 2022-05-25
GANGEV | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/3604580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4481838 | Approved | 27000 | 0 | 2022-01-07
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5247120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123418831 | Approved | 27000 | 0 | 2025-02-24
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5253175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123470912 | Approved | 27000 | 0 | 2025-02-24
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5254816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133125025 | Approved | 27000 | 0 | 2025-03-01
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5262296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125166595 | Ongoing | 27000 | 0 | 2025-12-02
GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5265117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123976015 | Ongoing | 27000 | 9300 | 2026-05-18
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5307052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123506619 | Physically Completed | 23490 | 0 | 2025-11-03 | 2026-08-09
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5314723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141725972 | Approved | 27000 | 0 | 2025-03-01
GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5328154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123688221 | Ongoing | 27000 | 12600 | 2026-07-08
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5336020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124930608 | Ongoing | 27000 | 4200 | 2025-11-03
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5399220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125179908 | Approved | 27000 | 0 | 2025-03-10
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5421307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123689797 | Approved | 27000 | 0 | 2025-03-10
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5421954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123687828 | Ongoing | 27000 | 0 | 2025-09-07
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5422248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123503780 | Approved | 27000 | 0 | 2025-02-24
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5492534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123479976 | Approved | 27000 | 0 | 2025-03-18
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5493184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125173173 | Ongoing | 27000 | 0 | 2025-07-26
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5588591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134142349 | Ongoing | 27000 | 0 | 2025-09-07
GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5651945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123682992 | Approved | 27000 | 0 | 2025-03-01
GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5677651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123687382 | Approved | 27000 | 0 | 2025-06-10
GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/5804713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121076543 | Ongoing | 27000 | 9300 | 2026-05-18
GANGEV | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/86993 — Construction of IAY House -IAY REG. NO. MP-13-004-066-004/193 | Approved | 27000 | 0 | 2015-09-26
GANGEV | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713004066/IF/IAY/86994 — Construction of IAY House -IAY REG. NO. MP-13-004-066-004/47 | Approved | 27000 | 0 | 2015-09-26
GANGEV | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713004066/RC/22012034531141 — खेत सडक निर्माण रपटा एवं मोतीलाल मिश्रा के खेत से आदिवासी बस्ती की ओर ग्राम रोजवाह | Ongoing | 647870.47 | 0 | 2020-11-25
GANGEV | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713004066/RS/22012034328679 — Repair old toilet Siyasaran Yadav/ Ragubeer | Ongoing | 0 | 0 | 2017-04-21
GANGEV | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1713004066/RS/22012034634726 — सामुदायिक स्वच्छता परिसर (शौचालय) निर्माण इटहई स्कूल के पास TS 4317/146747/20/01 | Ongoing | 100000 | 0 | 2022-01-07
GANGEV | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1713004066/RS/22012034672921 — Samudayik Swachchhata shauchaly Nirman parasi school me | Ongoing | 100000 | 0 | 2022-12-14