## Work List
Exported on: 2026-10-29 00:22:57
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: MAJANMANIKARAM
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
HANUMANA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713005029/AV/22012034503298 — shantidham nirman kary majan ramsharan | Ongoing | 281063.03 | 0 | 2020-01-28
HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1713005029/AV/22012034649235 — Puliya nirman karya Aganwadi kendra kramank 01 ke pass Majanramkripal | Physically Completed | 240000 | 0 | 2023-10-08 | 2026-08-05
HANUMANA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1713005029/AV/22012034662441 — Kota bhawan nirman karya majanmanikram | Physically Completed | 400000 | 0 | 2025-01-08 | 2026-08-05
HANUMANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1713005029/IF/22012034462201 — KAPIL DHARA KOOP NIRMAN KARYA SHANKARDAYAL MISHRA KI BHUMI PAR | Ongoing | 200000 | 0 | 2019-03-05
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1713005029/IF/22012035546747 — JGSA Khet Talab Nirman Karya Rajkush Dube ki Bhumi Par | Ongoing | 450885.64 | 0 | 2025-06-21
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713005029/IF/22012035633538 — Ek Bagiya Maa Ke Naam Shusheela Kushwaha ki bhumi par MP4687573 | Ongoing | 184644.48 | 37800 | 2025-11-02
HANUMANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4257346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147151968 | Ongoing | 27000 | 0 | 2022-11-22
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4629772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127589815 | Completed | 27000 | 4800 | 2025-01-10 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4629955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127623345 | Ongoing | 27000 | 0 | 2025-01-10
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4631019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127631551 | Ongoing | 27000 | 6300 | 2025-01-10
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4631522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127940807 | Completed | 27000 | 2100 | 2025-01-24 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4655640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147149530 | Completed | 23490 | 9600 | 2025-01-10 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4790375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120684 | Ongoing | 27000 | 3900 | 2025-01-10
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4797369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148559057 | Physically Completed | 27000 | 2100 | 2025-01-10 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/4878652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148237853 | Ongoing | 27000 | 0 | 2025-01-10
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5441368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148552233 | Completed | 23490 | 1827 | 2025-05-22 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5446198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127138832 | Physically Completed | 27000 | 2100 | 2025-05-22 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5447551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127603669 | Completed | 23490 | 0 | 2025-06-24 | 2026-08-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5449312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127942286 | Completed | 27000 | 2100 | 2025-08-10 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5451107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147149201 | Physically Completed | 27000 | 3900 | 2025-05-22 | 2026-10-20
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5567533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147152792 | Ongoing | 27000 | 2100 | 2025-05-22
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5569620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147145087 | Completed | 27000 | 19200 | 2025-05-22 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5569846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127576769 | Physically Completed | 27000 | 12900 | 2025-05-22 | 2026-10-20
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5632540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127123671 | Ongoing | 27000 | 4800 | 2026-08-26
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5677623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148552426 | Completed | 27000 | 2100 | 2025-06-19 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5677666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147150891 | Completed | 23490 | 6000 | 2025-06-19 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5727952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148559956 | Physically Completed | 27000 | 4200 | 2025-08-19 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5765894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148553865 | Ongoing | 27000 | 0 | 2025-10-16
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5765994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148549050 | Approved | 27000 | 0 | 2025-03-31
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5765996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148552393 | Completed | 23490 | 3600 | 2025-08-24 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5766589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127621460 | Ongoing | 27000 | 2100 | 2025-11-01
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5766983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141666884 | Physically Completed | 27000 | 2100 | 2025-08-24 | 2026-10-01
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127624878 | Completed | 27000 | 0 | 2026-01-10 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147145544 | Approved | 27000 | 0 | 2025-04-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127632890 | Completed | 27000 | 0 | 2025-10-16 | 2026-09-26
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127144601 | Completed | 23490 | 0 | 2025-10-16 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127598054 | Completed | 23490 | 3000 | 2025-10-29 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148558960 | Ongoing | 27000 | 2100 | 2025-10-16
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5767834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148559885 | Ongoing | 27000 | 2100 | 2025-08-27
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148552308 | Completed | 27000 | 0 | 2025-10-16 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147144987 | Approved | 27000 | 0 | 2025-03-19
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147145075 | Completed | 23490 | 2400 | 2025-09-20 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148511363 | Completed | 23490 | 4800 | 2025-08-24 | 2026-09-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127219371 | Ongoing | 27000 | 4800 | 2025-10-29
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147148459 | Completed | 23490 | 0 | 2025-08-24 | 2026-08-11
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147143564 | Approved | 27000 | 0 | 2025-03-29
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5768991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141203326 | Completed | 23490 | 0 | 2025-08-23 | 2026-08-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5769297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147149049 | Completed | 23490 | 0 | 2025-09-04 | 2026-08-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5785665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141668091 | Completed | 27000 | 0 | 2025-09-04 | 2026-10-04
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/5800685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147142817 | Completed | 23490 | 0 | 2025-09-09 | 2026-08-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6060866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127607660 | Approved | 27000 | 0 | 2025-04-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6061879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127464257 | Approved | 27000 | 0 | 2026-01-29
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6062142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147144938 | Completed | 23490 | 0 | 2026-05-11 | 2026-09-23
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6064329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148549144 | Completed | 27000 | 14400 | 2026-06-05 | 2026-09-23
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6064330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147145151 | Completed | 27000 | 0 | 2026-05-11 | 2026-09-23
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6065715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141671697 | Completed | 27000 | 0 | 2026-05-11 | 2026-09-23
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6267809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127458402 | Approved | 27000 | 0 | 2025-03-04
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6273600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141668128 | Approved | 27000 | 0 | 2026-01-29
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6289120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127220113 | Approved | 27000 | 0 | 2026-03-07
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6295083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127170219 | Approved | 27000 | 0 | 2026-04-27
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6386651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147142177 | Approved | 27000 | 0 | 2026-01-29
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6408022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127598900 | Approved | 27000 | 0 | 2025-07-27
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6409010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127459174 | Approved | 27000 | 0 | 2025-03-01
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6409221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126659218 | Approved | 27000 | 0 | 2025-03-01
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6411159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127626397 | Approved | 27000 | 0 | 2025-03-01
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6411551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127229035 | Approved | 27000 | 0 | 2026-02-11
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6413206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148618889 | Approved | 27000 | 0 | 2026-02-24
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6413249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148618853 | Approved | 27000 | 0 | 2026-01-29
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6416703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127461952 | Approved | 27000 | 0 | 2025-03-01
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6418549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151247946 | Approved | 27000 | 0 | 2025-04-24
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6418703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148250086 | Approved | 27000 | 0 | 2025-04-11
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6420300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148671713 | Approved | 27000 | 0 | 2025-03-01
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6420558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148671588 | Approved | 27000 | 0 | 2026-01-29
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6421190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127627792 | Approved | 27000 | 0 | 2025-03-04
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713005029/IF/IAY/6423184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127177004 | Approved | 27000 | 0 | 2025-04-11
HANUMANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1713005029/RC/22012034551147 — Sudoor sampark sadak nirman ramtej ke ghar se prathmik shala | Ongoing | 1413016.14 | 0 | 2020-12-15
HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1713005029/RS/22012035118838 — Nadep tanka 05 nug majanmanikram | Ongoing | 16000 | 0 | 2023-10-09
HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1713005029/RS/22012035119652 — Sok pit nirman karya 10 nug | Ongoing | 72000 | 0 | 2023-10-09