## Work List
Exported on: 2026-09-09 16:36:38
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: GOIRAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
HANUMANA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713005094/AV/22012034373147 — Panchyat Building | Ongoing | 579200 | 0 | 2018-09-25
HANUMANA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1713005094/AV/22012034391646 — AGANBADI BHAWAN NIRMAN KARYA GP GOIDAR ME | Ongoing | 312000 | 0 | 2018-10-05
HANUMANA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1713005094/AV/22012034534115 — गौशाला निर्माण कार्य ग्राम गोइडॉर में | Ongoing | 3784582.21 | 0 | 2021-01-21
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1713005094/DP/22012034587404 — Amrit Vatika Goirar Talab Ke Pas | Ongoing | 55847.4 | 0 | 2023-08-08
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005094/IF/22012035332405 — कपिल धारा कूप निर्माण कार्य संतदास कि भूमि पर | Approved | 0 | 0 | 2025-04-04
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713005094/IF/22012035599152 — एक बगिया मां के नाम अनुराधा की भूमि पर | Approved | 0 | 0 | 2025-08-15
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713005094/IF/22012035599200 — एक बगिया मां के नाम रश्मि शुक्ला की भूमि पर | Approved | 0 | 0 | 2025-08-15
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1713005094/IF/22012035599238 — एक बगिया मां के नाम फूलवती की भूमि पर | Approved | 0 | 0 | 2025-08-15
HANUMANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/4148584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126398596 | Approved | 27000 | 0 | 2022-05-24
HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/5017866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125962066 | Ongoing | 27000 | 0 | 2025-03-23
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/5273516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125957029 | Physically Completed | 23490 | 0 | 2025-04-07 | 2026-08-16
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/5766021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126392014 | Ongoing | 27000 | 0 | 2025-10-09
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/5766996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125971988 | Ongoing | 27000 | 0 | 2025-10-09
HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/5768052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125949831 | Physically Completed | 23490 | 0 | 2025-09-25 | 2026-08-16
HANUMANA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/6046891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125946410 | Ongoing | 27000 | 0 | 2026-05-27
HANUMANA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/88576 — Construction of IAY House -IAY REG. NO. MP-13-005-094-001/05 | Approved | 27000 | 0 | 2015-10-28
HANUMANA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/88577 — Construction of IAY House -IAY REG. NO. MP-13-005-094-004/42 | Approved | 27000 | 0 | 2015-10-28
HANUMANA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005094/IF/IAY/88579 — Construction of IAY House -IAY REG. NO. MP-13-005-094-005/10 | Approved | 27000 | 0 | 2015-10-28
HANUMANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Vermi Compost structure for Groups / Construction of Vermi Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713005094/RS/22012034595655 — varmi compost karya 10 NUG | Ongoing | 58000 | 0 | 2021-11-05
HANUMANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1713005094/RS/22012034596414 — Senigresation sed nirman karya Goidar me | Ongoing | 89700 | 0 | 2021-11-05
HANUMANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1713005094/WC/22012035166753 — खेत तालाब निर्माण कार्य रामसहोदर की भूमि पर | New | 0 | 0 | 2024-01-28
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167225 — बोल्डर चेक डैम निर्माण कार्य तालाब के पास | New | 0 | 0 | 2024-01-27
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167226 — बोल्डर चेक डैम निर्माण कार्य तालाब के पास | New | 0 | 0 | 2024-01-27
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167228 — बोल्डर चेक डैम निर्माण कार्य तालाब के पास | New | 0 | 0 | 2024-01-27
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167231 — बोल्डर चेक डैम निर्माण कार्य तालाब के पास | New | 0 | 0 | 2024-01-27
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167256 — bolder check dam nirman kary gram kon me | New | 0 | 0 | 2024-01-28
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1713005094/WC/22012035167351 — बोल्डर चेक डैम मरचिह्वा के पास | New | 0 | 0 | 2024-02-28
HANUMANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1713005094/WC/22012035167352 — talab nirman kary goidar me | New | 0 | 0 | 2024-01-27
HANUMANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1713005094/WC/22012035167353 — कूप निर्माण कार्य संतदास की भूमि पर | New | 0 | 0 | 2024-01-27
HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713005094/WC/22012035279391 — Rechange pit sarvajanik koop kundaliya nadi ke pas | Ongoing | 25899.46 | 0 | 2025-05-19
HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713005094/WC/22012035279407 — Rechange pit sarvajanik koop shivprasad saket ke ghar ke pas | Ongoing | 25899.46 | 0 | 2025-05-19