## Work List
Exported on: 2026-09-13 16:56:09
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: DUWAGAWADUWAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MAUGANJ | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1713006018/AV/22012034604206 — serrigation sad nirman kary adiwasi basti mudariya kapsan | Ongoing | 94000 | 0 | 2021-10-29
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713006018/IF/22012034980193 — SHG Sw Sahayata Samooh Pashu sed Nirman Kary Gulab kali ki bhumi par | Ongoing | 105982.64 | 0 | 2025-04-17
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713006018/IF/22012035541721 — खेत तालाब निर्माण कार्य शिवकंची पिता रामसुफल भूमि में ग्राम पंचायत दुबगवा दुवान | Approved | 0 | 0 | 2025-04-14
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713006018/IF/22012035544358 — Khet Talab Shivkanchi Ke bhumi me Dubgawa Duwan | Approved | 0 | 0 | 2025-04-14
MAUGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/2840594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4085756 | Approved | 27000 | 0 | 2021-02-03
MAUGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/2841745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4264807 | Ongoing | 27000 | 0 | 2022-02-17
MAUGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/3397967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4074829 | Ongoing | 27000 | 0 | 2022-02-16
MAUGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/3642530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5432469 | Approved | 27000 | 0 | 2022-01-30
MAUGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/3642531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5433372 | Approved | 27000 | 0 | 2022-01-30
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4075984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120562681 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4081272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121048374 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4081275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121049609 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4081276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121050044 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4081278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121051583 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4088152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126433386 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4090998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127241198 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4107845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148935484 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4112031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150041319 | Physically Completed | 23490 | 0 | 2025-06-23 | 2026-08-09
MAUGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4112032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150041650 | Approved | 27000 | 0 | 2022-05-11
MAUGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4759461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118663510 | Approved | 27000 | 0 | 2024-09-15
MAUGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4775186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125110432 | Approved | 27000 | 0 | 2024-09-21
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/4848934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121048059 | Physically Completed | 23490 | 0 | 2025-06-23 | 2026-08-09
MAUGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5009102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121818625 | Physically Completed | 23490 | 0 | 2025-03-25 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5009105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121820221 | Physically Completed | 23490 | 0 | 2025-06-12 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5010239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121046672 | Physically Completed | 23490 | 0 | 2025-05-23 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5434825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148935518 | Ongoing | 27000 | 0 | 2025-05-23
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5435472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150037994 | Physically Completed | 23490 | 0 | 2025-06-12 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5435550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121823106 | Physically Completed | 23490 | 0 | 2025-05-17 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5435683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121042708 | Ongoing | 27000 | 0 | 2025-05-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5435684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121045310 | Physically Completed | 23490 | 0 | 2025-05-10 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5435685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121045756 | Ongoing | 27000 | 0 | 2025-06-23
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5436795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120856089 | Ongoing | 27000 | 0 | 2025-06-12
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5437021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121047218 | Ongoing | 27000 | 0 | 2025-04-17
MAUGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5437960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121824843 | Physically Completed | 23490 | 0 | 2024-10-02 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5438513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121044695 | Physically Completed | 23490 | 0 | 2025-05-10 | 2026-08-09
MAUGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5439240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151481701 | Approved | 27000 | 0 | 2025-01-30
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5439518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121051124 | Physically Completed | 23490 | 0 | 2025-09-13 | 2026-08-02
MAUGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5517156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125109707 | Ongoing | 27000 | 0 | 2026-09-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5604581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150040561 | Approved | 27000 | 0 | 2025-04-11
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5618066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148946471 | Approved | 27000 | 0 | 2025-04-19
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5632799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127242047 | Approved | 27000 | 0 | 2025-05-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5632802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150040171 | Approved | 27000 | 0 | 2025-05-18
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149027442 | Approved | 27000 | 0 | 2025-05-18
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148946768 | Approved | 27000 | 0 | 2025-05-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151479056 | Approved | 27000 | 0 | 2025-05-18
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150040924 | Approved | 27000 | 0 | 2025-05-14
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151480861 | Physically Completed | 23490 | 0 | 2025-05-13 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5633724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126716303 | Physically Completed | 23490 | 0 | 2025-05-13 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5710882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150041166 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5711082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126725572 | Approved | 27000 | 0 | 2025-05-21
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5711133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124306704 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5711281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121053773 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5711427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123227382 | Approved | 27000 | 0 | 2025-05-21
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5716317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151480272 | Approved | 27000 | 0 | 2025-05-18
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5719803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127261697 | Approved | 27000 | 0 | 2025-07-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5720879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151258573 | Approved | 27000 | 0 | 2025-07-10
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5729557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121817949 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5729784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127268624 | Physically Completed | 23490 | 0 | 2025-07-10 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5967651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121045483 | Physically Completed | 23490 | 0 | 2025-08-04 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/5969444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148934420 | Approved | 27000 | 0 | 2025-10-31
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/6102757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121815838 | Physically Completed | 23490 | 0 | 2025-08-04 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/6107317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121827624 | Physically Completed | 23490 | 0 | 2025-07-10 | 2026-08-09
MAUGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713006018/IF/IAY/6110053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121048240 | Physically Completed | 23490 | 0 | 2025-07-10 | 2026-08-09
MAUGANJ | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713006018/RC/22012034389190 — पीसीसी सह नाली निर्माण कार्य लाल भाई मिश्रा के घर से मुदरिया मार्ग तक | Ongoing | 77000 | 0 | 2018-08-28
MAUGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1713006018/WC/22012035165011 — PLANTATION | New | 0 | 0 | 2024-04-14