## Work List
Exported on: 2026-10-27 16:24:48
Filters applied:
Data source: VBGRAMG
District: REWA
Block: All
Panchayat: BELA KAMOD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NAIGARHI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1713007028/AV/22012034665117 — AGANBADI BHAVAN NIRMAN KAARY SOHAI KAMATA | Ongoing | 637000 | 0 | 2025-04-04
NAIGARHI | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1713007028/FP/22012034641594 — Nali nirman kary men rod se sankarshan tiwari ke ghr tak Bela kamod | Approved | 132000 | 0 | 2024-12-04
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1713007028/IF/22012035190561 — Pashu sed nirman kary Sushila Tiwari ke bhumi me | Ongoing | 126902.19 | 0 | 2025-04-09
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1713007028/IF/22012035359533 — Koop nirman karya Krishnpal Singh S/O Pradyuman Singh ke bhumi me | Approved | 0 | 0 | 2025-04-14
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1713007028/IF/22012035359563 — Koop nirman karya Ramnaresh Kushwaha S/O Baishakhu ke bhumi me | New | 0 | 0 | 2025-04-14
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007028/IF/22012035594616 — एक बगिया मा के नाम लक्ष्मी बाई समूह हितग्राही गीता | Ongoing | 268737.85 | 11337.99 | 2025-08-29
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007028/IF/22012035594655 — एक बगिया मा के नाम रिया समूह हितग्राही ललिता | Ongoing | 268737.85 | 0 | 2025-09-12
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007028/IF/22012035594661 — एक बगिया मा के नाम तिरंगा समूह हितग्राही अर्चना | Ongoing | 268737.85 | 2065 | 2025-10-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007028/IF/22012035596582 — एक बगिया मा के नाम तिरंगा समूह हितग्राही माधुरी | Ongoing | 266577.25 | 3103 | 2025-10-09
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007028/IF/22012035614061 — एक बगिया मा के नाम लक्ष्मी बाई समूह हितग्राही चंद्रा | Ongoing | 198293.61 | 2136 | 2025-10-09
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4305265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123708743 | Ongoing | 27000 | 0 | 2025-05-22
NAIGARHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4314326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4627879 | Ongoing | 27000 | 0 | 2022-08-26
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4577121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118033605 | Approved | 27000 | 0 | 2024-09-15
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4577130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118034572 | Ongoing | 27000 | 1701 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4578191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118115472 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4578639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118061320 | Ongoing | 27000 | 1701 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4579308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118761559 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4582079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118723956 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4595130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122521736 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4595160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122525835 | Approved | 27000 | 0 | 2024-09-13
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4595164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122525982 | Ongoing | 27000 | 1458 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4597458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122528415 | Approved | 27000 | 0 | 2024-09-15
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308141 | Physically Completed | 27000 | 0 | 2024-09-15 | 2026-09-27
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308344 | Approved | 27000 | 0 | 2024-09-15
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123308558 | Ongoing | 27000 | 1827 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123309131 | Approved | 27000 | 0 | 2024-09-13
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123333544 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123335661 | Approved | 27000 | 0 | 2024-09-13
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4598656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122880400 | Physically Completed | 23490 | 0 | 2024-10-07 | 2026-07-19
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4599536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122607343 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4599549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122610246 | Approved | 27000 | 0 | 2024-09-15
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4602313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123441466 | Approved | 27000 | 0 | 2024-09-13
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4602372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123447915 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4603041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123722085 | Ongoing | 27000 | 0 | 2024-10-07
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4603048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123723345 | Physically Completed | 27000 | 0 | 2026-05-01 | 2026-09-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4625228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127329595 | Physically Completed | 23490 | 0 | 2025-05-22 | 2026-07-12
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4712373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127104331 | Ongoing | 27000 | 11772 | 2026-01-16
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4854820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123022494 | Ongoing | 27000 | 0 | 2025-02-06
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/4891729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127020608 | Ongoing | 27000 | 0 | 2025-08-13
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5114855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116285411 | Approved | 27000 | 0 | 2024-09-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5252136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127209211 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5258114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123046045 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5266758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125539221 | Physically Completed | 23490 | 0 | 2025-10-09 | 2026-07-26
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5268966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123329156 | Physically Completed | 27000 | 0 | 2025-05-22 | 2026-09-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5272015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126580266 | Physically Completed | 23490 | 0 | 2025-05-12 | 2026-07-26
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5273458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124419357 | Ongoing | 27000 | 5481 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5275462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124714580 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5279714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127056471 | Ongoing | 27000 | 1827 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5288292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124033559 | Ongoing | 27000 | 9918 | 2025-05-12
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5290730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118523925 | Ongoing | 27000 | 0 | 2026-05-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5300646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118742062 | Ongoing | 27000 | 13335 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5302081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123350009 | Physically Completed | 27000 | 0 | 2025-05-07 | 2026-10-04
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5306481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128509969 | Physically Completed | 27000 | 0 | 2026-05-08 | 2026-09-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5318546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118027072 | Ongoing | 27000 | 1566 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5331371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123327326 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5333707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127362195 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5339097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118728512 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5340039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123468154 | Ongoing | 27000 | 0 | 2025-05-07
NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/5604830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127360518 | Approved | 27000 | 0 | 2025-03-21
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6046980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127055147 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6047022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123723128 | Ongoing | 27000 | 0 | 2026-08-30
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6047216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127355846 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6047428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123350389 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6047535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122613947 | Ongoing | 27000 | 7332 | 2026-08-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6047691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123330990 | Approved | 27000 | 0 | 2026-02-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6077206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118057355 | Approved | 27000 | 0 | 2026-03-17
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6082931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122885197 | Approved | 27000 | 0 | 2026-03-10
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6083383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123348705 | Approved | 27000 | 0 | 2026-02-20
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6083386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123350704 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6083574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123470705 | Approved | 27000 | 0 | 2026-02-20
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6083576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123471324 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6083909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123722641 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6084356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124033763 | Approved | 27000 | 0 | 2026-02-24
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6084840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124417900 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6084844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124419902 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6085158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124647245 | Ongoing | 27000 | 7332 | 2026-08-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6085160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124648394 | Approved | 27000 | 0 | 2026-03-17
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127068142 | Approved | 27000 | 0 | 2026-02-20
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127103593 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127105929 | Approved | 27000 | 0 | 2026-02-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127329794 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127350959 | Approved | 27000 | 0 | 2026-03-12
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127353115 | Approved | 27000 | 0 | 2026-03-10
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6089942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127359496 | Approved | 27000 | 0 | 2026-03-17
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6090256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127581598 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6090686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127924960 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6090706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127934350 | Approved | 27000 | 0 | 2026-02-20
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6090991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128161665 | Approved | 27000 | 0 | 2026-03-12
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6091327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128519874 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6091349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128548134 | Ongoing | 27000 | 7332 | 2026-08-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6102198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141401131 | Approved | 27000 | 0 | 2026-03-12
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6102199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141401142 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6102495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127347414 | Approved | 27000 | 0 | 2026-03-12
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6102498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127356769 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6103191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127211912 | Approved | 27000 | 0 | 2026-02-27
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6103551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127349604 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6103553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127351426 | Approved | 27000 | 0 | 2026-03-12
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6103662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128520959 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6103964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127066095 | Approved | 27000 | 0 | 2026-02-24
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6104556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128512291 | Approved | 27000 | 0 | 2026-03-10
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6104998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127364009 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6106079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128511824 | Approved | 27000 | 0 | 2026-03-17
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6113984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118018316 | Ongoing | 27000 | 12600 | 2026-08-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6114040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118747832 | Approved | 27000 | 0 | 2026-03-10
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6114741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122878873 | Approved | 27000 | 0 | 2026-02-24
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6255028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118059937 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6256210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118816774 | Approved | 27000 | 0 | 2026-02-27
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6260990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123229311 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6261108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123335514 | Approved | 27000 | 0 | 2026-05-20
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6261441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123348130 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6262106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124034369 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6266176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127042245 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6266810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127062274 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6267643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127271627 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6267761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127363140 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6268220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127357688 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6269078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128543170 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6276463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147861535 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6279608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127371088 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6287880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127042783 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6295333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123722352 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6295861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122879398 | Approved | 27000 | 0 | 2026-02-18
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6320006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125767977 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6320049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127697622 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6331285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127345985 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6331408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127354932 | Approved | 27000 | 0 | 2026-04-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6331475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128534570 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6331698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127924407 | Approved | 27000 | 0 | 2026-04-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6332063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127925780 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6332169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127440343 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6332466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127367325 | Approved | 27000 | 0 | 2026-05-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6359651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124052077 | Approved | 27000 | 0 | 2026-03-23
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6359827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127124641 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6389229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128536269 | Approved | 27000 | 0 | 2026-03-10
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6389269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123708889 | Approved | 27000 | 0 | 2026-02-27
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6389344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123708617 | Ongoing | 27000 | 0 | 2026-10-13
NAIGARHI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6397918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123229932 | Approved | 27000 | 0 | 2026-04-01
NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/6422275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127067073 | Approved | 27000 | 0 | 2026-03-22
NAIGARHI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/88354 — Construction of IAY House -IAY REG. NO. MP-13-007-028-006/31467960 | Approved | 27000 | 0 | 2015-10-13
NAIGARHI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1713007028/IF/IAY/88355 — Construction of IAY House -IAY REG. NO. MP-13-007-028-008/26221327 | Approved | 27000 | 0 | 2015-10-13
NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of IHHL for Individual | Construction of Toilets | 1713007028/RS/22012034321327 — शौचालय मरम्मत कार्य रामानुज साहू के घर | Ongoing | 8800 | 0 | 2017-01-28
NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1713007028/RS/22012035122981 — Nali nirman kary keshav tiwari ke ghr se talab ki taraf | New | 0 | 0 | 2024-01-27
NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair & Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1713007028/WC/22012034691232 — Talab Gahrikaran and Saundrikaran bela kmod | Ongoing | 995875.58 | 0 | 2021-06-04
NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1713/RC/22012034562139 — Gravel marg nirman | Ongoing | 9575000 | 0 | 2021-03-13