## Work List
Exported on: 2026-09-05 20:18:32
Filters applied:
Data source: VBGRAMG
District: MANDSAUR
Block: All
Panchayat: PIPLYAVISHNIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MALHARGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1716002007/AV/22012034657607 — Shantidham vikas gram Arniyadev | New | 0 | 0 | 2024-06-14
MALHARGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716002007/DP/22012034604013 — Vasudha Vandan Amrit Watika shaskiy high school parisar pipliavishniya | Ongoing | 55847.4 | 0 | 2023-09-26
MALHARGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716002007/IF/22012035124374 — Nandan Flodhyan Purnesh banshilal | Ongoing | 161000 | 0 | 2023-07-26
MALHARGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716002007/IF/22012035519049 — JGSA2025 Dug well arjun | Ongoing | 25899.46 | 0 | 2025-05-18
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716002007/IF/22012035608807 — Ek bagiya Maa ke naam madhubai jagdish sarve n 387/1/1/2 | New | 0 | 0 | 2025-08-15
MALHARGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/124381 — Construction of IAY House -IAY REG. NO. MP-16-002-007-001/2 | Approved | 27000 | 0 | 2016-01-29
MALHARGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/2306068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5548818 | Ongoing | 27000 | 0 | 2019-10-30
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/4632559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129480940 | Ongoing | 27000 | 0 | 2025-05-15
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5113001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127870473 | Ongoing | 27000 | 0 | 2025-05-27
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5115161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128752209 | Ongoing | 27000 | 8874 | 2025-04-23
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5118934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123406406 | Ongoing | 27000 | 0 | 2025-04-14
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5131480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122400318 | Ongoing | 27000 | 10962 | 2026-08-11
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5504320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127824858 | Ongoing | 27000 | 0 | 2025-05-17
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141875597 | Ongoing | 27000 | 10962 | 2026-07-11
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127265900 | Ongoing | 27000 | 0 | 2026-05-23
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127747028 | Ongoing | 27000 | 1827 | 2026-06-01
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127857802 | Ongoing | 27000 | 5481 | 2026-04-26
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125315148 | Ongoing | 27000 | 5481 | 2026-06-16
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127495508 | Ongoing | 27000 | 2349 | 2026-04-26
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128210300 | Ongoing | 27000 | 5481 | 2026-04-26
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128212548 | Ongoing | 27000 | 5481 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118312838 | Ongoing | 27000 | 7569 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125341786 | Ongoing | 27000 | 5481 | 2026-05-23
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125851648 | Ongoing | 27000 | 1827 | 2026-05-23
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129174480 | Ongoing | 27000 | 10962 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128751833 | Ongoing | 27000 | 9135 | 2026-07-21
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127845269 | Ongoing | 27000 | 0 | 2026-05-23
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5967897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127851876 | Ongoing | 27000 | 0 | 2026-08-07
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141873057 | Ongoing | 27000 | 0 | 2026-04-26
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141873168 | Ongoing | 27000 | 5481 | 2026-07-08
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123456279 | Ongoing | 27000 | 0 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124873889 | Ongoing | 27000 | 10962 | 2026-07-08
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149849808 | Approved | 27000 | 0 | 2026-02-13
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127859472 | Ongoing | 27000 | 1566 | 2026-05-23
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126029854 | Ongoing | 27000 | 0 | 2026-06-01
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127825855 | Ongoing | 27000 | 7308 | 2026-06-16
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126257397 | Ongoing | 27000 | 7569 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127856226 | Ongoing | 27000 | 5481 | 2026-06-01
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127861092 | Ongoing | 27000 | 10701 | 2026-05-23
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127495036 | Approved | 27000 | 0 | 2026-02-06
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5968895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123469355 | Ongoing | 27000 | 0 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125861481 | Ongoing | 27000 | 5481 | 2026-06-10
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141873882 | Ongoing | 27000 | 5481 | 2026-07-11
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126521234 | Approved | 27000 | 0 | 2026-02-06
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127857008 | Ongoing | 27000 | 3654 | 2026-05-23
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129487527 | Approved | 27000 | 0 | 2026-02-13
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128210770 | Ongoing | 27000 | 0 | 2026-06-01
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/5969753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128209891 | Approved | 27000 | 0 | 2026-02-06
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6113686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151713242 | Ongoing | 27000 | 10962 | 2026-07-08
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6113710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123409276 | Ongoing | 27000 | 0 | 2026-06-01
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6115365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149737329 | Ongoing | 27000 | 0 | 2026-06-10
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6115469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149738973 | Approved | 27000 | 0 | 2026-02-06
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6203955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125332083 | Ongoing | 27000 | 10962 | 2026-07-16
MALHARGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6212507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149730974 | Approved | 27000 | 0 | 2026-03-14
MALHARGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/6234930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118083690 | Ongoing | 23490 | 10962 | 2026-07-08
MALHARGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/696575 — Construction of IAY House -IAY REG. NO. MP1381445 | Approved | 27000 | 0 | 2017-03-22
MALHARGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/741037 — Construction of IAY House -IAY REG. NO. MP2256998 | Approved | 27000 | 0 | 2017-03-22
MALHARGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716002007/IF/IAY/754343 — Construction of IAY House -IAY REG. NO. MP2700394 | Approved | 27000 | 0 | 2017-03-22
MALHARGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716002007/RC/22012034838305 — cc road nirman 15va vitt bholenath mandir se rajaram ke kup ki or | Ongoing | 45000 | 0 | 2025-04-26
MALHARGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716002007/RC/22012034841395 — cc road nirman 5va vitt nrega men road se babulal prajapti ke makan ki or | Ongoing | 10000 | 0 | 2025-06-24
MALHARGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716002007/RC/22012034846523 — cc road nirman 5va vitt nrega nageshwar ke makan se kanwarlal ke makan tak | Approved | 52000 | 0 | 2025-04-14
MALHARGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1716002007/WC/22012035209454 — Dug out pond nirman arniyadev | Approved | 496772.32 | 0 | 2024-06-12
MALHARGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716002007/WC/22012035305985 — JGSA2025 Dug well GIRID KE PASS | Ongoing | 25899.46 | 0 | 2025-05-18