## Work List
Exported on: 2026-09-10 12:16:50
Filters applied:
Data source: VBGRAMG
District: MANDSAUR
Block: All
Panchayat: BANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716004113/DP/22012034447854 — वृक्षारोपण कार्य शमशान घाट के उपर भाग 02 | Ongoing | 373989.79 | 0 | 2020-07-21
MANDSAUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716004113/DP/22012034490537 — वृक्षारोपण कार्य बड़े तालाब के पास | Ongoing | 677985.75 | 0 | 2020-07-11
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716004113/DP/22012034574173 — वृक्षारोपण कार्य खेल मैदान परिसर में | Ongoing | 407854.45 | 0 | 2023-08-19
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716004113/DP/22012034591541 — वसुधा वंदन अमृत वाटिका हाई स्कूल के पास बनी 23-24 | Ongoing | 55847.4 | 0 | 2023-09-25
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035090311 — निजी फलोद्यान भेरुलाल - नन्दलाल 2023-24 | Ongoing | 161000 | 0 | 2023-08-16
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035090316 — निजी फलोद्यान मांगीलाल - बालूजी बलाई 2023-24 | Ongoing | 161000 | 0 | 2023-12-06
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035090319 — निजी फलोद्यान मोहनलाल - भंवरलाल धाकड़ 2023-24 | Ongoing | 161000 | 0 | 2023-08-16
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035090322 — निजी फलोद्यान कैलाश - रामसुख धाकड़ 2023-24 | Ongoing | 161000 | 0 | 2023-07-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035137774 — निजी फलोद्यान बद्रीलाल - देवराम 23-24 | Ongoing | 161000 | 0 | 2023-10-10
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035137777 — निजी फलोद्यान हेमलताबाई - रामकिशन 23-24 | Ongoing | 130000 | 0 | 2023-09-21
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004113/IF/22012035140961 — निजी फलोद्यान नानालाल - भुवान 23-24 | Ongoing | 161000 | 0 | 2023-09-21
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004113/IF/22012035423962 — JGSA 2025 Dugwell Recharge कूप रिचार्ज राहुल पिता चंद्रशेखर ग्राम बनी | New | 0 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004113/IF/22012035424016 — JGSA 2025 Dugwell Recharge राहुल पिता चंद्रशेखर ग्राम बनी | New | 0 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004113/IF/22012035511217 — JGSA 2025 Dugwell Recharge कूप रिचार्ज रिचार्ज रामेश्वर पिता भेरुलाल धाकड़ ग्राम बनी | Approved | 0 | 0 | 2025-05-12
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004113/IF/22012035531557 — JGSA 2025 Dugwell recharge कूप रिचार्ज कविता बाई नरसिंह धाकड़ ग्राम बनी | Approved | 25899.46 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004113/IF/22012035536022 — JGSA 2025 KHet Talab Nirman विकास पिता चंद्रशेखर धाकड़ | Approved | 55865.38 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004113/IF/22012035540661 — JGSA 2025 खेत तालाब निर्माण परमानंद पिता रघुनाथ जी | Approved | 55865.38 | 0 | 2025-05-21
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004113/IF/22012035540669 — JGSA 2025 खेत तालाब निर्माण रमेश पिता सोहनलाल माली | Approved | 55865.38 | 0 | 2025-05-21
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/4777680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126792431 | Approved | 27000 | 0 | 2024-09-24
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5344866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149546599 | Ongoing | 27000 | 0 | 2025-04-29
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5351931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126830026 | Ongoing | 27000 | 0 | 2025-10-08
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5352221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126871475 | Ongoing | 27000 | 0 | 2025-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5354813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127216040 | Ongoing | 27000 | 0 | 2025-08-05
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5394926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123470214 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5403136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127145761 | Ongoing | 27000 | 0 | 2025-08-05
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5610484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126860813 | Approved | 27000 | 0 | 2025-03-03
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5649859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126862056 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5701918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149701987 | Approved | 27000 | 0 | 2025-07-01
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5802647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702902 | Approved | 27000 | 0 | 2025-03-03
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5802929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702750 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5991408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702576 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5991409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702670 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5991863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151006506 | Approved | 27000 | 0 | 2026-02-10
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5993016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128920266 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5995896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128153740 | Approved | 27000 | 0 | 2026-02-10
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/5997271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702249 | Ongoing | 27000 | 0 | 2026-09-03
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6089482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127117709 | Approved | 27000 | 0 | 2026-02-10
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6102206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126476456 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6102907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147164361 | Approved | 27000 | 0 | 2026-02-26
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6102964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126470731 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6107332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126810960 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6107501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126478631 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6108107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149701951 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6108108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702723 | Approved | 27000 | 0 | 2026-02-26
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6108109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702832 | Ongoing | 27000 | 4200 | 2026-04-10
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6178679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702696 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6179407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702638 | Approved | 27000 | 0 | 2026-03-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6182572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128150380 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6183059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123491536 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6183366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123474362 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6184442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702013 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6190873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702942 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6191211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702539 | Approved | 27000 | 0 | 2026-03-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6194115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146797066 | Approved | 27000 | 0 | 2026-03-11
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6203205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123472445 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6207647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145305795 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6212029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149702386 | Ongoing | 27000 | 4200 | 2026-07-23
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6230229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127149794 | Ongoing | 27000 | 4200 | 2026-08-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004113/IF/IAY/6230428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128149571 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004113/RC/22012034839074 — सीमेंट कांक्रीट रोड निर्माण वि.निधि+मनरेगा ग्राम बनी में ओडी धर्मशाला से भेरूबावजी के मंदिर की और | Approved | 53000 | 0 | 2024-08-15
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004113/RC/22012034845336 — सीसी रोड व नाली निर्माण मनरेगा एंव 5/15 वा वित्त ग्राम बनी में ब्रहामणों की गली में । | Approved | 44000 | 0 | 2025-04-01
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004113/RC/22012034845337 — सीसी रोड व नाली निर्माण मनरेगा एंव 5/15 वा वित्त ग्राम बनी में मेहतर गली में | Approved | 45000 | 0 | 2025-04-01
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004113/RC/22012034845339 — सीसी रोड व नाली निर्माण मनरेगा एंव 5/15 वा वित्त ग्राम बनी नानालाल के घर से मांगीलाल के घर तक | Approved | 86000 | 0 | 2025-04-01
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004113/WC/22012035265704 — JGSA 2025 Dugwell Recharge शासकीय कुप गोशाला के पास ग्राम बनी | Ongoing | 25899.46 | 0 | 2025-05-29
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004113/WC/22012035286379 — JGSA 2025 Dugwell Recharge कूप रिचार्ज शासकीय कूप श्मशान परिसर ग्राम बनी | Ongoing | 25899.46 | 0 | 2025-05-29
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004113/WC/22012035286802 — JGSA 2025 Dugwell Recharge कूप रिचार्ज राहुल पिता चंद्रशेखर ग्राम बनी | Approved | 25899.46 | 0 | 2025-04-25