## Work List
Exported on: 2026-10-19 11:03:35
Filters applied:
Data source: MGNREGA
District: MANDSAUR
Block: All
Panchayat: GALYAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1716004117/AV/22012034390328 — नवीन आगनवाडी भवन निर्माण दिलावरा 2018-19 | Completed | 312000 | 311298.3 | 2019-01-05 | 2024-03-19
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1716004117/AV/22012034390418 — खेल मैदान कार्य दिलावरा | Deleted | 320000 | 0 | 2017-12-04
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1716004117/AV/22012034390432 — खेल मैदान कार्य दिलावरा | Deleted | 0 | 0 | 2017-12-04
MANDSAUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1716004117/DP/22012034435494 — निर्मल नीर कुप निर्माण ग्राम दिलावरा 2018-19 | Completed | 535000 | 520292.76 | 2019-01-20 | 2019-07-11
MANDSAUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1716004117/DP/22012034486949 — डग आउट पोंड निर्माण गल्याखेड़ी | Completed | 420379.65 | 409871.04 | 2020-05-14 | 2021-09-20
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1716004117/DP/22012034487913 — डग आउट पोंड दिलावरा | Completed | 495267.59 | 490530.17 | 2020-06-06 | 2020-12-12
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1716004117/DP/22012034492624 — निर्मल नीर ग्राम दिलावरा | Completed | 559479.23 | 549083.5 | 2020-08-08 | 2022-08-03
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1716004117/DP/22012034522281 — नवीन डग आउट पोंड निर्माण जयराम मीणा के खेत के पास | Completed | 496165.06 | 425298 | 2021-01-20 | 2024-09-03
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004117/DP/22012034554293 — वृक्षारोपण कार्य पंचवन गल्याखेडी 2022-23 | Ongoing | 407718.19 | 306323 | 2022-05-20
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1716004117/DP/22012034576342 — निर्मल नीर कूप निर्माण (वृक्षारोपण के पास) गल्याखेडी | Completed | 645786.86 | 639125.26 | 2023-08-31 | 2024-02-12
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004117/DP/22012034588242 — वसुधा वंदन अमृत वाटिका पुराना डग आउट पोण्‍ड के पास 2023-24 | Closed | 55847.4 | 0 | 2023-08-01
MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004117/DP/22012034620629 — व़क्षारोपण कार्य बालाजी परिसर ग्राम गल्‍याखेडी 202425 | Approved | 0 | 0 | 2024-06-28
MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716004117/DP/22012034620630 — व़क्षारोपण कार्य कार्य पंचवन के पास भाग २ गल्‍याखेडी 202425 | Ongoing | 464147.17 | 155690 | 2024-09-10
MANDSAUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716004117/DP/64 — DROG PUROFING GALIYAKHADIE | Completed | 317000 | 49205.9 | 2008-04-02 | 2013-07-28
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1716004117/DW/9993657711 — Nirmal Neer kup nirman Galyakhedi | Completed | 683000 | 638454.75 | 2016-04-05 | 2017-08-30
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/1151 — बद्रीलाल व कवरंलाल पिता मांगीलाल | Deleted | 0 | 0 | 2009-02-16
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/1153 — kapil dhara premchand nandram badrilal nandram | Completed | 164000 | 167658 | 2009-03-23 | 2013-04-01
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012034363767 — वृक्षा रोपण दीलावरा | Completed | 335000 | 334770 | 2017-07-20 | 2022-08-03
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012034386487 — खेत तालाब निर्माण बाबूलाल - हीरालाल | Closed | 0 | 0 | 2018-04-04
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012034456944 — खेत तालाब निर्माण प्यारीबाई - सुखराम | Closed | 0 | 0 | 2019-04-14
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012034583236 — निजी फलोद्यान प्यारेलाल - भेरुलाल दिलावरा (2020-21) | Completed | 145000 | 141420 | 2020-07-29 | 2023-07-14
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012034583239 — निजी फलोद्यान बालमुकुन्द - किशनलाल दिलावरा (2020-21) | Completed | 145000 | 134271.54 | 2020-08-19 | 2023-07-14
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012034681316 — खेत तालाब निर्माण बाबूलाल - हीरालाल माली | Closed | 0 | 0 | 2021-01-26
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012034986479 — निजी फलोद्यान चुन्नीलाल - घासी (2022-23) | Physically Completed | 152000 | 102955 | 2022-05-20 | 2026-06-22
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012035088477 — निजी फलोद्यान कंवरलाल - बक्षीराम दिलावरा 2023-24 | Closed | 161000 | 0 | 2023-04-27
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012035088489 — निजी फलोद्यान द्रोपतीबाई - देवराम गल्याखेडी 2023-24 | Physically Completed | 188000 | 185410 | 2023-05-31 | 2026-05-20
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004117/IF/22012035173480 — निजी फलो उद्यान रामकन्‍याबाई- कंवरलाल 2023-24 | Physically Completed | 161000 | 86979 | 2023-10-06 | 2026-06-22
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035420968 — JGSA 2025 Dugwell Recharge Nagulal bherulal mali galyakhedi | Physically Completed | 25899.46 | 15381.76 | 2025-05-10 | 2026-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035421009 — JGSA 2025 Dugwell Recharge Rajaram jagdish mali galyakhedi | Physically Completed | 25899.46 | 24516.76 | 2025-05-10 | 2026-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035478507 — JGSA 2025 Dugwell Recharge Radha Bai kailash | Physically Completed | 25899.46 | 24777.76 | 2025-05-24 | 2026-04-14
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035478526 — JGSA 2025 Dugwell Recharge Madhu Bai jankilal | Closed | 25899.46 | 261 | 2025-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035479109 — JGSA 2025 Dugwell Recharge Prabhulal Radhakishan | Physically Completed | 25899.46 | 24777.76 | 2025-05-17 | 2026-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035479162 — JGSA 2025 Dugwell Recharge Shyamlal Amritram | Closed | 25899.46 | 261 | 2025-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035479176 — JGSA 2025 Dugwell Recharge viramlal bhwerlalji gyari | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035480763 — JGSA 2025 Dugwell Recharge ramubai w/o radheshyam | Closed | 25899.46 | 261 | 2025-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035496080 — JGSA 2025 Dugwell Recharge कूप रिचार्ज भेरुलाल भंवरलाल | Closed | 25899.46 | 261 | 2025-05-24
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035496094 — JGSA 2025 Dugwell Recharge कूप रिचार्ज दिलीप श्यामलाल | Approved | 25899.46 | 0 | 2025-05-08
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004117/IF/22012035496102 — JGSA 2025 Dugwell Recharge कूप रिचार्ज राधाबाई जानकिलाल | Closed | 25899.46 | 261 | 2025-05-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012035534346 — JGSA 2025 Mangilal Baluram | Approved | 0 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012035534352 — JGSA 2025 Khet Talab NIrman Tulsiram BHerulal | Approved | 55865.38 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1716004117/IF/22012035534461 — JGSA 2025 खेत तालाब मांगीलाल बालुराम माली | Ongoing | 55865.38 | 261 | 2025-06-02
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004117/IF/22012035550559 — JGSA 2025 khet talab Mankalal s/o Shankarlal | Approved | 55865.38 | 0 | 2025-04-25
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/299 — kup nirman chunilal gasi sitaram ghaci | Completed | 136000 | 215648 | 2008-05-15 | 2008-04-15
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/300 — KUP NIRMAN RADHSIYAM RAMLAL AND BHAGIRATH RAMALAL | Completed | 136000 | 207278.59 | 2008-05-16 | 2008-04-16
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/664 — कूप निर्माण सीताबाई, सीताराम, दौलतराम, गणपत सीताराम | Completed | 136000 | 158413.5 | 2008-05-19 | 2008-05-19
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/705 — कूपनिर्माण कारूलाल कनीराम जी गल्‍याखेडी | Completed | 186000 | 73095.42 | 2009-02-02 | 2013-02-20
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/706 — कूपनिर्माण नारायण भेरूलाल एंव प्रकाश नंदा जी दिलावरा | Completed | 159000 | 125361.44 | 2009-01-13 | 2009-01-13
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/874 — कूप निर्माण कारूलाल पिता कनीराम गल्‍याखेडी | Completed | 187000 | 138320 | 2009-02-23 | 2009-02-02
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/914 — कूप निर्माण मुकेश, जगदीश, भंवरलाल व रमेश्‍वर गल्‍याखेडी | Deleted | 136000 | 115830.2 | 2009-03-02
MANDSAUR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/915 — कूप निर्माण कैलाश पिता राधाकिशन गल्‍याखेडी | Completed | 164000 | 204240.35 | 2009-04-06 | 2013-04-01
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/916 — कूप निर्माण गोपाल, लालु पिता बगदीराम जी दिलावरा | Completed | 136000 | 48741.98 | 2009-02-23 | 2009-02-23
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004117/IF/917 — कूप निर्माण मांगीलाल पिता नानुराम गल्‍याखेडी | Deleted | 159000 | 119599.75 | 2009-03-02
MANDSAUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/9993678842 — Indra awas- gyarsibai w/o omprakash | Completed | 14310 | 13836 | 2015-10-05 | 2016-10-10
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1716004117/IF/9993679218 — Indra awas- babuukhan-yashinkhan | Completed | 14310 | 8268 | 2015-10-08 | 2016-10-10
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1716004117/IF/9993679221 — Indra awas-salim khas/o yashin kha | Completed | 14310 | 14280 | 2015-10-08 | 2016-08-04
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1716004117/IF/9993679222 — Indra awas-ajijkha s/o yashin kha | Completed | 14310 | 14280 | 2015-10-08 | 2016-08-03
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1716004117/IF/9993679252 — Indra awas- ramchandra s/o mangilal | Completed | 14310 | 14280 | 2015-10-08 | 2016-08-03
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1716004117/IF/9993679255 — Indra awas -kanhaiyalal s/o narayan | Completed | 14310 | 14280 | 2015-10-08 | 2016-08-04
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/1009920 — Construction of IAY House -IAY REG. NO. MP1556339 | Completed | 15480 | 15072 | 2017-10-28 | 2018-11-26
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/1048916 — Construction of IAY House -IAY REG. NO. MP3640727 | Completed | 15480 | 15248 | 2017-10-28 | 2018-09-27
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/1048922 — Construction of IAY House -IAY REG. NO. MP3641248 | Completed | 15480 | 15596 | 2017-10-28 | 2018-05-24
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/1049262 — Construction of IAY House -IAY REG. NO. MP3675870 | Completed | 15480 | 15072 | 2017-10-28 | 2018-09-27
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/116476 — Construction of IAY House -IAY REG. NO. MP-16-004-117-002/61 | Completed | 14310 | 14696 | 2016-07-04 | 2017-03-25
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/1914060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5093242 | Completed | 15660 | 14616 | 2018-10-27 | 2018-12-01
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/197586 — Construction of IAY House -IAY REG. NO. MP-16-004-117-002/3 | Completed | 14310 | 14028 | 2016-07-04 | 2016-10-10
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2149499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5253508 | Completed | 15840 | 15840 | 2019-07-19 | 2019-11-23
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2165390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5660271 | Completed | 15840 | 15664 | 2019-07-19 | 2020-03-25
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2166167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5676874 | Completed | 15840 | 15840 | 2019-07-19 | 2019-11-23
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2166172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5676907 | Completed | 15840 | 15840 | 2019-07-19 | 2019-12-02
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2166538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5685511 | Completed | 15840 | 15840 | 2019-07-19 | 2019-11-23
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/2166852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5696006 | Completed | 15840 | 15840 | 2019-07-19 | 2019-11-23
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/249774 — Construction of IAY House -IAY REG. NO. MP1868887 | Completed | 15030 | 14986 | 2017-02-04 | 2018-03-31
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3754941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412036 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-24
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3754945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412429 | Completed | 18360 | 17867 | 2022-11-11 | 2023-05-24
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3754948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412551 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-24
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3756355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119441733 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-24
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3783440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116594158 | Completed | 18360 | 18241 | 2022-06-17 | 2023-05-28
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3783448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116595923 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-28
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3783453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116597778 | Completed | 18360 | 18360 | 2022-06-17 | 2022-10-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3817696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117345389 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-28
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3817727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117349877 | Completed | 18360 | 18360 | 2022-05-20 | 2023-02-15
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3823011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119413182 | Completed | 18360 | 18241 | 2022-05-20 | 2024-02-15
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3826412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117638449 | Completed | 18360 | 18241 | 2022-05-20 | 2023-05-28
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3828386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117650258 | Completed | 18360 | 18360 | 2022-06-17 | 2022-10-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3828443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117652693 | Completed | 18360 | 18241 | 2022-08-12 | 2024-02-15
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3833094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117704807 | Completed | 18360 | 18360 | 2022-05-20 | 2022-10-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3835267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715323 | Completed | 18360 | 17922 | 2022-05-20 | 2024-07-25
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3835269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715374 | Completed | 18360 | 18360 | 2022-05-20 | 2022-10-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3835272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715440 | Completed | 18360 | 18241 | 2022-06-17 | 2023-07-11
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3835274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715501 | Completed | 18360 | 18241 | 2022-05-20 | 2023-06-27
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/3937604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119782050 | Completed | 18360 | 18258 | 2022-05-20 | 2024-02-08
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4225787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712624 | Completed | 18360 | 18241 | 2022-08-12 | 2023-06-07
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4227171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412161 | Completed | 18360 | 18241 | 2022-08-12 | 2023-05-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4227434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781522 | Completed | 18360 | 18258 | 2022-08-12 | 2023-05-15
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4227435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781653 | Completed | 18360 | 18241 | 2022-10-27 | 2023-05-15
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4296509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781003 | Completed | 18360 | 18258 | 2022-08-12 | 2023-05-15
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4393284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119782174 | Completed | 18360 | 18343 | 2023-04-12 | 2024-02-01
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4570255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116601479 | Completed | 23490 | 22518 | 2024-10-22 | 2025-09-01
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117692401 | Completed | 21870 | 21870 | 2024-11-09 | 2025-02-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117704723 | Completed | 23490 | 21978 | 2024-11-09 | 2025-09-13
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117704976 | Completed | 21870 | 21870 | 2024-10-22 | 2025-02-10
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713132 | Ongoing | 23490 | 13860 | 2024-11-09
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715036 | Completed | 23490 | 23490 | 2025-04-12 | 2025-09-13
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715172 | Completed | 23490 | 22860 | 2025-01-04 | 2026-03-11
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4574733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715220 | Completed | 21870 | 21870 | 2024-10-22 | 2025-02-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4583040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119782675 | Physically Completed | 23490 | 21978 | 2025-01-21 | 2026-06-16
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4752237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117351451 | Completed | 23490 | 21978 | 2024-11-21 | 2025-07-11
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4753030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117669323 | Completed | 21870 | 21870 | 2024-12-02 | 2025-02-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4757623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442054 | Completed | 21870 | 21627 | 2024-11-09 | 2025-02-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4757625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442946 | Completed | 21870 | 21870 | 2024-11-21 | 2025-02-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4759625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781765 | Completed | 21870 | 21627 | 2024-11-21 | 2025-01-29
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/4869911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442648 | Completed | 23490 | 22023 | 2025-02-13 | 2025-08-05
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5343971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119411769 | Physically Completed | 23490 | 23490 | 2025-08-27 | 2026-06-26
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5343972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119412685 | Completed | 23490 | 23490 | 2025-08-12 | 2025-10-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5343978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119440829 | Physically Completed | 23490 | 23490 | 2026-01-07 | 2026-06-26
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5343979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442415 | Completed | 23490 | 23490 | 2026-01-07 | 2026-03-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5343980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119443303 | Physically Completed | 23490 | 3654 | 2026-01-07 | 2026-03-29
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5346013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126089507 | Completed | 23490 | 23490 | 2025-08-27 | 2026-01-14
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5346375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117345408 | Ongoing | 23490 | 21924 | 2026-01-07
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5346376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117347026 | Completed | 23490 | 23490 | 2025-08-11 | 2025-11-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5346409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620657 | Completed | 23490 | 23490 | 2025-08-13 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5346912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117644779 | Completed | 23490 | 23490 | 2025-05-16 | 2025-11-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5348026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116599024 | Completed | 23490 | 23490 | 2025-07-25 | 2025-11-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5348154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116601456 | Completed | 23490 | 23490 | 2025-07-25 | 2025-10-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5348447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117704662 | Completed | 23490 | 23490 | 2025-08-12 | 2025-10-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5348449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117714925 | Ongoing | 23490 | 3654 | 2026-02-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5348450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117714990 | Completed | 23490 | 23490 | 2025-05-16 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5349571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117691294 | Completed | 23490 | 23490 | 2025-08-11 | 2026-01-14
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5349572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117691522 | Completed | 23490 | 23490 | 2025-08-27 | 2026-03-30
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5349573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117701074 | Completed | 23490 | 23238 | 2025-08-12 | 2026-02-02
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5350933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117670479 | Completed | 23490 | 23229 | 2025-05-10 | 2025-09-24
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5351400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117690975 | Completed | 23490 | 23490 | 2025-05-16 | 2026-01-14
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5353304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713089 | Completed | 23490 | 23490 | 2025-08-27 | 2025-12-02
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5353305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713192 | Ongoing | 23490 | 3654 | 2026-02-06
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5353306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713259 | Completed | 23490 | 23229 | 2026-01-07 | 2026-04-12
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5353331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117349996 | Completed | 23490 | 23490 | 2025-08-27 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5354203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117364756 | Completed | 23490 | 23490 | 2025-05-16 | 2025-09-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5354236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781414 | Completed | 23490 | 23490 | 2025-08-27 | 2025-11-04
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5354237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781927 | Physically Completed | 23490 | 23490 | 2025-10-03 | 2026-06-16
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5354300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715112 | Completed | 23490 | 23490 | 2025-05-16 | 2025-10-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5354301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117715284 | Completed | 23490 | 23490 | 2025-08-11 | 2026-01-14
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5355013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117360150 | Completed | 23490 | 23490 | 2025-08-13 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5355014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117360211 | Completed | 23490 | 23229 | 2025-07-17 | 2025-09-24
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5355015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117360247 | Completed | 23490 | 23490 | 2025-05-16 | 2025-09-01
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5355472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620305 | Completed | 23490 | 23490 | 2025-08-27 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5355817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620699 | Completed | 23490 | 23490 | 2025-08-13 | 2025-10-29
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5356291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119441196 | Physically Completed | 23490 | 23490 | 2026-01-22 | 2026-06-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5356292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442198 | Completed | 23490 | 23490 | 2026-01-07 | 2026-03-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5356293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117363382 | Completed | 23490 | 23490 | 2025-08-13 | 2025-10-13
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/556904 — Construction of IAY House -IAY REG. NO. MP3557919 | Completed | 15030 | 15718 | 2017-02-04 | 2018-04-20
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5647395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712771 | Completed | 23490 | 23490 | 2025-08-27 | 2025-10-28
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5697554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119411877 | Physically Completed | 23490 | 23490 | 2026-01-07 | 2026-06-16
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/5702089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119781325 | Ongoing | 23490 | 21141 | 2026-02-06
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/578200 — Construction of IAY House -IAY REG. NO. MP1869308 | Completed | 15030 | 15010 | 2017-02-04 | 2018-04-20
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117342745 | Approved | 23490 | 0 | 2026-02-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359321 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117359362 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117363589 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117363630 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6075814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117363757 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620138 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620255 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620579 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620784 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117644066 | Approved | 23490 | 0 | 2026-02-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117670308 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117671334 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6076469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713338 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119413293 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119439943 | Approved | 23490 | 0 | 2026-02-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119440160 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119442815 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119648912 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119655105 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119780852 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6079586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119782572 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6087998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126477141 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6091697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129138430 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117641295 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119782269 | Approved | 23490 | 0 | 2026-04-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119440401 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117639605 | Approved | 23490 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620446 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712708 | Approved | 23490 | 0 | 2026-04-08
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/6230909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117620992 | Approved | 23490 | 0 | 2026-02-13
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/86447 — Construction of IAY House -IAY REG. NO. MP-16-004-117-001/138 | Completed | 14310 | 14208 | 2016-11-21 | 2018-03-31
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/86448 — Construction of IAY House -IAY REG. NO. MP-16-004-117-001/53 | Completed | 14310 | 14208 | 2017-03-02 | 2018-03-31
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/86449 — Construction of IAY House -IAY REG. NO. MP-16-004-117-002/14 | Completed | 14310 | 13360 | 2016-07-04 | 2017-03-25
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004117/IF/IAY/86450 — Construction of IAY House -IAY REG. NO. MP-16-004-117-002/9 | Completed | 14310 | 13694 | 2016-07-04 | 2017-03-25
MANDSAUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1716004117/LD/22012034242856 — Antrik marg nirman (raod se shamshan road tak) c.p.t. evm shamshan bhumi leval | Completed | 479000 | 190309 | 2015-12-09 | 2017-08-30
MANDSAUR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1716004117/LD/3799406281 — Khel medan Galyakhedi | Completed | 473000 | 312225.3 | 2013-09-23 | 2016-06-28
MANDSAUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1716004117/LD/5 — मेढबंधान प्‍यारेलाल भेरा जी गल्‍याखेडी | Completed | 319000 | 6188 | 2009-01-19 | 2009-12-08
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1716004117/PG/9425896673 — खेल मैदान कार्य दिलावरा | Completed | 196000 | 185857.6 | 2017-09-03 | 2019-07-30
MANDSAUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034171348 — vidhayak + nregs devram ke makan se gopal ke makan | Completed | 110000 | 133906 | 2013-03-25 | 2014-03-30
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034179029 — panchparmeshaver CC Road Panchayat bhawan se mukesh balaram ke ghar tak | Completed | 120000 | 116512 | 2014-03-04 | 2015-01-30
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034180333 — panchparmeshaver CC Road Premchand ke ghar se jayram ke ghar tak | Completed | 128000 | 127625 | 2013-10-05 | 2015-01-30
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034180337 — panchparmeshaver CC Road Balaram ke ghar se Hamid khan ke ghar tak | Completed | 46000 | 45268 | 2013-09-24 | 2014-06-27
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034180340 — panchparmeshaver CC Road Kawarlal ke ghar se Ramesh sharmake ghar tak | Completed | 52000 | 51056 | 2013-09-23 | 2014-06-27
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034180344 — panchparmeshaver CC Road Mangilal ke ghar se Ramratan ke ghar tak | Completed | 46000 | 45276 | 2013-09-23 | 2014-09-02
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034187844 — panchparmeshawar CC Road Hamid khan keghar se jovr | Completed | 31000 | 28568 | 2013-10-04 | 2014-06-20
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034188063 — panchparmeshawar CC Road Bherulal mali ke ghar se | Completed | 27000 | 27152 | 2013-10-04 | 2014-06-27
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004117/RC/22012034291967 — Antrik Marg Nirman Dilawra nai abadi se Galyakhedi road tak (School bich me) | Completed | 975000 | 616734.17 | 2015-12-09 | 2017-08-30
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034321204 — सी सी रोड (पंचपरमेश्वर+मनरेगा) प्रधानमंत्री सडक से शमशान शेड तक दिलावरा | Completed | 14000 | 14852 | 2019-03-01 | 2020-05-20
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004117/RC/22012034342041 — सुदूर सड़क निर्माणग्राम गल्याखेड़ी से अचेरी गांव की कांकड़ तक | Completed | 1497000 | 1373197.31 | 2017-10-28 | 2021-04-01
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004117/RC/22012034342043 — सुदूर सड़क निर्माण ग्राम दिलावरा में दिलावरा से गुजरदा कांकड़ तक | Completed | 1498000 | 1480756.9 | 2017-06-21 | 2021-04-01
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034361678 — सीसी रोड व नाली निर्माण राम जानकी मंदीर से बावडी तक | Completed | 69000 | 70348 | 2017-09-27 | 2019-07-30
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034366709 — CC ROAD:-DILAWARA ME MANDIR CHOUK ME | Completed | 57000 | 56821.78 | 2017-11-26 | 2018-10-15
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034370638 — सीसी रोड निर्माण (पंचपरमेश्वर+मनरेगा) रामजानकी मंदिर से कंवरलाल गायरी के मकान तक | Completed | 43000 | 42846 | 2019-01-20 | 2020-05-20
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034381114 — सी सी सडक निर्माण( मनरेगा+विधायक नीधि) मातम जी मंदिर के सामने चौक में | Completed | 42000 | 41508 | 2018-04-06 | 2018-10-16
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034381141 — सी सी सडक निर्माण( मनरेगा+पंचपरमेश्वर) राम जानकी मंदिरसे रामचंद के बाड़े तक | Completed | 28000 | 26950 | 2018-07-20 | 2020-05-20
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034381144 — सी सी सडक निर्माण( मनरेगा+पंचपरमेश्वर) कैलाश माली के मकान से जमालपुरा रोड तक | Completed | 34000 | 33756 | 2018-07-03 | 2019-06-20
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034381146 — सी सी सडक निर्माण( मनरेगा+पंचपरमेश्वर) उदेराम चोकीदार के मकान से देवीलाल मीना के मकान तक | Completed | 22000 | 21924 | 2019-01-05 | 2020-05-20
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034438589 — सीसी रोड निर्माण | Closed | 0 | 0 | 2019-04-04
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034462556 — सीसी रोड निर्माण (पंचपर्मेश्वर+मनरेगा) सामुदायिद भवन से पीएम सडक की और | Completed | 15000 | 14784 | 2019-07-26 | 2020-05-20
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034471671 — सीसी रोड निर्माण (पंचपरमेश्वऱ+मनरेगा) जमालपुरा रोड से शमशान शेड तक | Completed | 35000 | 35024 | 2019-08-12 | 2020-06-02
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034507075 — सीसी रोड निर्माण (परफारमेंस ग्रांट+मनरेगा) चोक से जगदीश माली के मकान व देवनारायण मंदिर के चौक में | Completed | 40000 | 39952 | 2019-12-24 | 2023-08-19
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034507076 — सीसी रोड निर्माण (परफारमेंस ग्रांट+मनरेगा) कंवरलाल के घर से भागीरथ के घर तक | Completed | 15000 | 15010 | 2020-08-08 | 2021-10-10
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034507077 — सीसी रोड निर्माण (परफारमेंस ग्रांट+मनरेगा) मांगीलाल के घर से चुन्नीलाल के घर तक | Completed | 49000 | 48928 | 2019-12-06 | 2020-07-20
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034515955 — सीसी रोड निर्माण (पंचपरमेश्वर+मनरेगा) कंवरलाल गायरी के घर से जमालपुरा रोड तक | Closed | 20490 | 0 | 2019-10-02
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004117/RC/22012034549971 — सुदूर ग्राम संपर्क सड़क ग्राम दिलावरा में पुरानी सुदूर सड़क से गुजरदा कांकड़ कोचवी रोड तक | Completed | 1861393.39 | 1858967.45 | 2020-12-23 | 2023-07-06
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034627634 — सीसी रोड व नाली निर्माण मनरेगा + १५ वा वित् शोभाराम,वरदीचंद , कालूराम के मकान से मंदिर चोक | Completed | 27000 | 26537 | 2023-07-31 | 2023-08-19
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034665158 — सीसी रोड व नाली निर्माण मनरेगा+ ५,१५,वां वित्‍त बालकिशन के घर से बालाजी की ओर | Completed | 26000 | 20111 | 2023-10-07 | 2024-02-12
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034665195 — सीसी रोड व नाली निर्माण मनरेगा+ ५,१५,वां वित्‍त घीसालाल के मकान से कचरू के घर की ओर | Closed | 23000 | 0 | 2023-09-25
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034665215 — सीसी रोड व नाली निर्माण मनरेगा+ ५,१५,वां वित्‍त तुलसीराम के मकान से नानालाल के घर तक | Completed | 82000 | 81328 | 2023-10-07 | 2024-09-26
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/22012034823945 — सीसी रोड व नाली निर्माण 5/15वि+मनरेगा ग्राम गल्याखेडी में प्राथमिक विद्यालय से कैलाश माली के घर कीऔर | Completed | 83000 | 82376.8 | 2024-08-26 | 2024-09-26
MANDSAUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004117/RC/275 — panchparmeshwar sitaram ke makan se kaniram mali k | Completed | 277000 | 275431 | 2012-06-03 | 2014-06-27
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004117/RS/22012034605048 — ड्रेनेज चेनल निर्माण (१५वावित्त+मनरेगा) गल्याखेडी में मदनलाल के मकान से पुलिया तक | Completed | 133000 | 132793 | 2021-11-09 | 2023-08-19
MANDSAUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004117/WC/22012034323564 — water conservation (pmksy)stopdam ,dilavara sarve no.66 | Completed | 718000 | 730521.66 | 2017-05-09 | 2019-01-05
MANDSAUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1716004117/WC/22012034330053 — ग्राम दिलावरा नई आबादी के पास तालाब की पाल एवं वेस्‍ट वियर मरम्‍मत | Completed | 304000 | 213489.75 | 2017-06-20 | 2018-12-10
MANDSAUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004117/WC/22012034384819 — water conservation (pmksy) check dam DILAVARA sarve no 66 | Completed | 531000 | 528930.61 | 2018-01-05 | 2018-12-20
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004117/WC/22012034478694 — सोकपिट निर्माण हैण्डपम्प पंचायत भवन ,गल्याखेडी | Closed | 0 | 0 | 2019-07-22
MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004117/WC/22012034696892 — कूप रिचार्ज निर्मलनीर कूप नील मगरे के पास दिलावरा | Completed | 14467.3 | 10422 | 2021-07-31 | 2021-08-30
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004117/WC/22012034961720 — CTR डग आउट पोंड निर्माण खेल मैदान के पास गल्याखेडी | Closed | 0 | 0 | 2022-04-01
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004117/WC/22012035062616 — डग आउट पोंड (वृक्षारोपण के पास) गल्याखेडी | Physically Completed | 704875.95 | 363480 | 2023-08-17 | 2026-06-24
MANDSAUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004117/WC/9993664101 — Parcolation tank talab nirman galyakhedi | Completed | 471000 | 468863 | 2016-01-05 | 2016-08-13
MANDSAUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004117/WC/9993664102 — Parcolation tank talab nirman dilawara | Completed | 471000 | 135468 | 2016-01-07 | 2017-08-30
MANDSAUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1716004117/WC/9993668463 — parkolation tank | Deleted | 0 | 0 | 2015-10-02
MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1716004117/WH/22012034449042 — CTR पुराना तालाब जीर्णोधार गल्याखेडी | Completed | 617813.92 | 576618.5 | 2021-07-31 | 2023-03-20