## Work List
Exported on: 2026-10-12 11:41:25
Filters applied:
Data source: MGNREGA
District: MANDSAUR
Block: All
Panchayat: BHARDAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1716004118/AV/22012034579447 — डाइनिंग हाल विकास कार्य ग्राम भरड़ावद | Completed | 16093.2 | 2702 | 2021-08-17 | 2024-03-19
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1716004118/AV/22012034628271 — नवीन शमशान शेड निर्माण तालाब के पास भरडावद | Completed | 210221.55 | 198060.72 | 2023-06-28 | 2024-03-27
MANDSAUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716004118/DP/104 — वक्षारोपन रतनागीर मगरा भरडावद | Completed | 485000 | 16940 | 2008-07-14 | 2013-08-10
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1716004118/DP/22012034442271 — सीपीटी व् कंटूर ट्रेंच निर्माण भरडावद | Completed | 250000 | 239888 | 2019-06-01 | 2020-06-20
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1716004118/DP/22012034483135 — डग आउट पोंड निर्माण नीलगिरी मगरे के पास | Completed | 392536.4 | 354108 | 2019-12-14 | 2022-03-10
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1716004118/DP/22012034483136 — डग आऊट पौंड निर्माण करोली रास्ते के पास | Suspended | 392536.4 | 18444 | 2019-11-28
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1716004118/DP/22012034483145 — निर्मलनीर कूप निर्माण कार्य स्कूल परिसर | Closed | 541990.89 | 0 | 2019-08-15
MANDSAUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1716004118/DP/22012034487929 — निर्मलनीर कूप निर्माण तालाब की पाल के पास | Completed | 559462.87 | 569927.89 | 2020-06-29 | 2021-06-25
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1716004118/DP/22012034553436 — वृक्षारोपण कार्य शमशान परिसर | Closed | 0 | 0 | 2022-04-01
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004118/DP/22012034555513 — वृक्षारोपण कार्य शमशान परिसर 2022-23 | Ongoing | 407718.19 | 174080 | 2022-05-23
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004118/DP/22012034588146 — वसुधा वंदन अमृत वाटिका मा.वि. परिसर ग्राम भरडावद 2023-24 | Ongoing | 55847.4 | 26741 | 2023-09-27
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004118/DP/22012034611044 — व़क्षारोपण कार्य कब्रिस्‍तान परिसर ग्राम भरडावद 2023-24 | Ongoing | 427106.07 | 182720 | 2023-10-09
MANDSAUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1716004118/DP/43 — Varksharopan bhardavad | Completed | 408000 | 85471 | 2008-05-22 | 2013-03-27
MANDSAUR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1716004118/DW/9993633685 — nirmal kup nirman bhadawad me | Deleted | 0 | 0 | 2014-05-20
MANDSAUR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1716004118/DW/9993633686 — Nirmal Neer kup nirman Bhardawad | Completed | 603000 | 593352.9 | 2014-06-04 | 2017-08-30
MANDSAUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1716004118/DW/9993658696 — nirmal nir Bhardawad 2015-16 | Completed | 603000 | 379846.98 | 2016-03-19 | 2018-07-18
MANDSAUR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/1272 — कपिलधारा कुप निर्माण नाहरखा जमाल खा भरडावद | Completed | 323000 | 340375 | 2011-09-26 | 2013-02-08
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004118/IF/22012034298326 — Nanda Flodhyan Salim , Mohammad - Gafur | Completed | 165000 | 79958 | 2016-09-23 | 2019-08-03
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/22012034308226 — Indira Awas janat / Ibrahim | Completed | 14310 | 11434 | 2017-03-04 | 2018-08-16
MANDSAUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Lining of Water Courses/Field Channel / Lining of water courses Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1716004118/IF/22012034308411 — Indira Awas Fatma bee / ishak | Completed | 15000 | 17364 | 2017-03-04 | 2017-08-30
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1716004118/IF/22012034308412 — Indira Awas Shamim bee / Ramjan | Deleted | 14310 | 0 | 2016-04-01
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1716004118/IF/22012034308413 — Indira Awas Sugara / shabbeer | Deleted | 14310 | 0 | 2016-04-05
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1716004118/IF/22012034308414 — Indira Awas Bano bee / Ahmad | Deleted | 1431 | 0 | 2016-04-07
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/22012034322292 — कपिल धारा सह खेत तालाब तयब हबीब इस्माइल | Completed | 230000 | 229262 | 2017-02-22 | 2018-05-30
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004118/IF/22012034345644 — व़क्षा रोपण स्‍कुल परिसर भरडावद | Completed | 335000 | 291651 | 2017-06-01 | 2023-07-25
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004118/IF/22012034371044 — वक्रशा रोपण कार्य सडक के ि‍किनारे भरडावद | Completed | 335000 | 264414 | 2017-08-15 | 2022-08-12
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034386464 — खेत तालाब निर्माण अशरफ - नाहर खा | Closed | 0 | 0 | 2017-04-01
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034456883 — खेत तालाब निर्माण राधेश्याम - भेरुलाल | Closed | 0 | 0 | 2019-04-14
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034496593 — खेत तालाब निर्माण रमेश - भग्गा जी | Closed | 0 | 0 | 2019-07-22
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034497865 — खेत तालाब निर्माण तय्य्ब - लाडू | Closed | 0 | 0 | 2019-07-22
MANDSAUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034501542 — खेत तालाब निर्माण हुराबाई - नाहर खा | Closed | 310385.56 | 0 | 2019-08-15
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034553399 — खेत तालाब निर्माण हीरालाल - दयाराम | Completed | 332572.21 | 226879 | 2020-05-22 | 2022-03-11
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034557432 — खेत तालाब निर्माण गनी - राजू | Completed | 332572.21 | 149340 | 2020-06-12 | 2022-03-11
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034557434 — खेत तालाब निर्माण युसूफ - ईस्माइल | Closed | 332572.21 | 0 | 2020-04-26
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034560401 — खेत तलाब निर्माण राधेश्याम - गणेशराम | Completed | 332572.21 | 327140 | 2020-06-06 | 2022-03-11
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034560402 — खेत तलाब निर्माण ईश्वर - अमृतराम | Deleted | 0 | 0 | 2020-05-05
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034560405 — खेत तालाबं निर्माण किशोर - अमृतराम | Completed | 332572.21 | 321580 | 2020-06-28 | 2021-06-25
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004118/IF/22012034575371 — निजी फलो उद्यान पन्नालाल - कनीराम 2020-21 | Closed | 145000 | 0 | 2020-04-01
MANDSAUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004118/IF/22012034575626 — निजी फलो उद्यान अब्बास - नूर गेहलोद 2020-21 | Closed | 145000 | 0 | 2020-04-01
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034985585 — खेत तालाब निर्माण जेना बी - अय्यूब | Completed | 356340.1 | 285804 | 2022-05-26 | 2024-05-28
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012034999346 — खेत तालाब निर्माण शकीना - अजीज 2022-23 | Completed | 356340.1 | 240533 | 2022-12-24 | 2024-10-23
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004118/IF/22012035086199 — खेत तालाब निर्माण गफूर - लाडू | Closed | 0 | 0 | 2023-04-15
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012035088919 — खेत तालाब निर्माण तयब- इस्माइल 2023-24 | Ongoing | 386916.22 | 56950 | 2023-07-07
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035449109 — JGSA 2025 Dugwell Recharge हबीब मोमिनपिता मोहम्मद मोमिन | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1716004118/IF/22012035449131 — JGSA 2025 Dugwell Recharge रजिया बी पति अजीज शाह | Closed | 25899.46 | 522 | 2025-05-13
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035449143 — JGSA 2025 Dugwell Recharge सुगरा बी पति अल्लाराख | Physically Completed | 25899.46 | 22533.32 | 2025-05-13 | 2026-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035449160 — JGSA 2025 Dugwell Recharge नाहर खा पिता जमाल | Physically Completed | 25899.46 | 18774.76 | 2025-05-13 | 2026-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035533804 — JGSA 2025 Dugwell Recharge Nasurauddin s/o Raju Gehlot | Physically Completed | 25899.46 | 13815.76 | 2025-05-24 | 2026-05-17
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035533818 — JGSA 2025 Dugwell Recharge Ayyub s/o Gafur | Closed | 25899.46 | 261 | 2025-05-24
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035533835 — JGSA 2025 Dugwell Recharge Ibrahim s/o Allarakha | Physically Completed | 25899.46 | 25560.8 | 2025-05-24 | 2026-05-17
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012035533855 — JGSA 2025 खेत तालाब निर्माझा शब्‍बीर हुसैन पिता इब्राहीम | Closed | 55865.38 | 261 | 2025-05-27
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/IF/22012035533869 — JGSA 2025 खेत तालाब निर्माण ईब्राहीम पिता फकरू | Approved | 55865.38 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1716004118/IF/22012035537799 — JGSA 2025 Khet talab Ismail ajmeri | Completed | 55865.38 | 36801 | 2025-05-24 | 2026-05-12
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035545065 — JGSA 2025 Dugwell Recharge कूप रिचार्ज फ़क़ीरचंद -रामा भरडावद | New | 0 | 0 | 2025-05-22
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035545069 — JGSA 2025 Dugwell Recharge कूप रिचार्ज फ़क़ीरचंद -रामा भरडावद | Approved | 25899.46 | 0 | 2025-05-22
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035545271 — JGSA 2025 Dugwell Recharge Ibrahim s/o Alla Rakha CHouhan | Approved | 0 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004118/IF/22012035545276 — JGSA 2025 Dugwell Recharge Rukaiya w/o Mohammad Chouhan | Approved | 0 | 0 | 2025-04-25
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/690 — कपिलधारा पन्‍नालाल कनीराम जी | Completed | 54000 | 255202.97 | 2008-10-06 | 2008-10-06
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/691 — कपिलधारा शांतिलाल मोहनलाल | Completed | 136000 | 272009.96 | 2008-10-06 | 2008-10-06
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/692 — कपिलधरा, राधेश्‍याम पिता भेरूलाल जी | Completed | 136000 | 157061.95 | 2008-10-06 | 2008-10-06
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/779 — कूप निर्माण नारूलाल पिता रामलाल जी व शिवलाल पिता कनीराम जी भरडावद | Completed | 136000 | 56573.9 | 2009-02-10 | 2012-11-12
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/780 — कूप निर्माण रतनबाई पति मांगीलाल जी भरडावद | Completed | 136000 | 110379.13 | 2009-02-23 | 2009-02-23
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/781 — कूप निर्माण रामप्रसाद कोदर जी व राजाराम कोदर जी भर | Completed | 445000 | 20741 | 2009-02-16 | 2014-03-30
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/782 — कूप निर्माण मांगीलाल पिता दयाराम व जिवाबाई पति गणेशराम भरडावद | Completed | 136000 | 101086.7 | 2009-02-16 | 2009-02-16
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/783 — कूप निर्माण किशनलाल पिता अब्‍बाजी व गंगाराम पिता अब्‍बजी भरडावद | Completed | 136000 | 161187.96 | 2009-02-10 | 2009-02-10
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/792 — कूप निर्माण शब्‍बीर पिता फरीयाद जी भरडावद | Completed | 136000 | 111147.6 | 2009-02-23 | 2009-02-23
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/793 — कूप निर्माण गफुर पिता पिरू व याकुब पिता निमा जी भरडावद | Completed | 136000 | 116810 | 2009-03-02 | 2009-03-02
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/794 — कूप निर्माण सीताबाई पति कारू जी भरडावद | Completed | 139000 | 375881 | 2009-03-02 | 2013-02-23
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/795 — कूप निर्माण श्‍यामलाल पिता फकीरचंद जी भरडावद | Completed | 136000 | 141128 | 2009-03-02 | 2009-03-02
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/796 — कूप निर्माण हरीराम, नानुराम व देवीलाल हरीराम भरडावद | Completed | 136000 | 166109 | 2009-03-16 | 2008-05-28
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/797 — कूप निर्माण दिनेश, वरदीचंद पिता नाथु जी भरडावद | Completed | 159000 | 131029 | 2009-02-16 | 2009-02-16
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/798 — कूप निर्माण शुगरा बी पिता फकरू बी | Completed | 136000 | 54376.2 | 2009-02-28 | 2009-02-28
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1716004118/IF/799 — कूप निर्माण राधेश्‍याम, शांतिलाल पिता कचरू जी भरडावद | Completed | 136000 | 68695.86 | 2009-02-27 | 2008-02-28
MANDSAUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/9993677379 — INDRA AVAS hurabee-vali mohammad | Completed | 14000 | 16842 | 2015-09-28 | 2016-10-10
MANDSAUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/9993677382 — INDRA AVAS pushapa bai-rajudas | Completed | 14000 | 16842 | 2015-09-28 | 2016-10-10
MANDSAUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/9993677384 — INDRA AVAS AKILA-TYAAB | Completed | 14000 | 16842 | 2015-09-28 | 2016-10-10
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1002123 — Construction of IAY House -IAY REG. NO. MP1583681 | Completed | 15480 | 15406 | 2017-12-22 | 2018-06-29
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1084775 — Construction of IAY House -IAY REG. NO. MP2664715 | Completed | 15480 | 174 | 2018-06-04 | 2020-06-20
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1098992 — Construction of IAY House -IAY REG. NO. MP3808051 | Completed | 15480 | 15160 | 2018-01-05 | 2018-04-13
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1206114 — Construction of IAY House -IAY REG. NO. MP3839020 | Completed | 15480 | 16182 | 2018-04-21 | 2018-06-22
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1206115 — Construction of IAY House -IAY REG. NO. MP3840898 | Completed | 15480 | 14790 | 2018-04-26 | 2018-06-28
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1206116 — Construction of IAY House -IAY REG. NO. MP3844549 | Completed | 15480 | 16182 | 2018-04-12 | 2018-06-19
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1409223 — Construction of IAY House -IAY REG. NO. MP2672405 | Completed | 15480 | 15660 | 2018-04-26 | 2018-07-12
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1419071 — Construction of IAY House -IAY REG. NO. MP2723936 | Completed | 15480 | 15834 | 2018-05-07 | 2018-10-17
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1522061 — Construction of IAY House -IAY REG. NO. MP3837204 | Completed | 15480 | 14964 | 2018-04-20 | 2018-07-12
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1522661 — Construction of IAY House -IAY REG. NO. MP3852372 | Completed | 15480 | 15312 | 2018-04-26 | 2018-06-29
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1522664 — Construction of IAY House -IAY REG. NO. MP3852400 | Completed | 15480 | 15312 | 2018-04-26 | 2018-07-20
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1523460 — Construction of IAY House -IAY REG. NO. MP3868733 | Completed | 15480 | 15660 | 2018-05-07 | 2018-10-17
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1804005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3845733 | Completed | 15660 | 13572 | 2018-06-24 | 2018-11-15
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1899646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5536764 | Completed | 15660 | 15138 | 2018-09-30 | 2019-01-09
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/1930719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5520686 | Completed | 15660 | 12208 | 2018-12-15 | 2019-06-08
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/242212 — Construction of IAY House -IAY REG. NO. MP1585191 | Completed | 15030 | 15136 | 2017-10-31 | 2018-04-03
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/242256 — Construction of IAY House -IAY REG. NO. MP1586935 | Completed | 15030 | 14804 | 2017-12-22 | 2018-04-13
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/3736770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755124 | Completed | 18360 | 18241 | 2022-05-23 | 2023-05-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/3757899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127191400 | Completed | 18360 | 18156 | 2022-08-04 | 2022-10-08
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/4263435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118734017 | Completed | 18360 | 18241 | 2022-08-25 | 2023-05-18
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/4264615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117348580 | Completed | 18360 | 18241 | 2022-08-13 | 2023-05-18
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/4576480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118580974 | Completed | 23490 | 22104 | 2025-02-17 | 2025-04-24
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/4767017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123510666 | Completed | 23490 | 21717 | 2025-02-17 | 2025-05-07
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/482907 — Construction of IAY House -IAY REG. NO. MP2025337 | Completed | 15030 | 14620 | 2017-10-10 | 2018-03-31
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/527695 — Construction of IAY House -IAY REG. NO. MP2744711 | Completed | 15030 | 15320 | 2017-12-22 | 2018-04-13
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5350407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123585064 | Completed | 23490 | 20568 | 2025-09-19 | 2026-03-30
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5351543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126308579 | Ongoing | 23490 | 21924 | 2025-09-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5356209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146505893 | Ongoing | 23490 | 0 | 2025-09-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5806884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121410653 | Physically Completed | 23490 | 12528 | 2025-09-19 | 2026-05-31
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5806885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121411631 | Ongoing | 23490 | 3654 | 2025-11-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5806970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126043327 | Physically Completed | 23490 | 13050 | 2025-09-23 | 2026-02-27
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5807235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127476103 | Physically Completed | 23490 | 5742 | 2025-09-23 | 2026-03-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5807236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127476662 | Physically Completed | 23490 | 14616 | 2025-09-23 | 2026-01-29
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5807339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146471108 | Ongoing | 23490 | 3654 | 2025-11-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5808127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043090 | Ongoing | 23490 | 19575 | 2025-09-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5808128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043103 | Ongoing | 23490 | 10962 | 2025-09-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5808163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127464298 | Ongoing | 23490 | 13833 | 2025-09-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5808251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124238767 | Physically Completed | 23490 | 19575 | 2025-09-23 | 2026-03-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5808276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127478800 | Physically Completed | 23490 | 21924 | 2025-09-23 | 2026-03-22
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5848578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126041381 | Ongoing | 23490 | 6786 | 2025-11-13
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5867763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121618689 | Approved | 23490 | 0 | 2025-03-03
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5867772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123511283 | Approved | 23490 | 0 | 2025-02-24
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5867921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118580948 | Physically Completed | 23490 | 0 | 2025-02-24 | 2026-05-03
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5867922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126809174 | Approved | 23490 | 0 | 2025-07-17
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5868004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129909218 | Approved | 23490 | 0 | 2025-02-24
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5868065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126041005 | Ongoing | 23490 | 2871 | 2026-05-06
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5868228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127477645 | Approved | 23490 | 0 | 2025-03-03
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5868455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125830938 | Physically Completed | 23490 | 0 | 2025-03-03 | 2026-07-12
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/5868594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118580912 | Physically Completed | 23490 | 0 | 2025-02-24 | 2026-04-19
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/86451 — Construction of IAY House -IAY REG. NO. MP-16-004-118-001/23 | Completed | 14310 | 14696 | 2017-01-01 | 2019-07-25
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/86452 — Construction of IAY House -IAY REG. NO. MP-16-004-118-001/3 | Completed | 14310 | 13326 | 2017-03-04 | 2018-10-05
MANDSAUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/86453 — Construction of IAY House -IAY REG. NO. MP-16-004-118-001/39a | Completed | 14310 | 14929 | 2017-01-02 | 2018-03-31
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/985179 — Construction of IAY House -IAY REG. NO. MP2646983 | Completed | 15480 | 15394 | 2017-12-22 | 2018-06-29
MANDSAUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/985230 — Construction of IAY House -IAY REG. NO. MP2699483 | Completed | 15480 | 15312 | 2018-05-10 | 2018-10-12
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/986078 — Construction of IAY House -IAY REG. NO. MP3891215 | Completed | 15480 | 15136 | 2017-12-08 | 2018-03-31
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/986085 — Construction of IAY House -IAY REG. NO. MP3895558 | Completed | 15480 | 14104 | 2017-10-10 | 2018-03-31
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/994745 — Construction of IAY House -IAY REG. NO. MP2648749 | Completed | 15480 | 14128 | 2018-01-04 | 2018-04-13
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/994885 — Construction of IAY House -IAY REG. NO. MP2699564 | Completed | 15480 | 15320 | 2017-12-08 | 2018-04-13
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/995056 — Construction of IAY House -IAY REG. NO. MP2762184 | Completed | 15480 | 15200 | 2018-01-26 | 2018-06-15
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/995057 — Construction of IAY House -IAY REG. NO. MP2762451 | Completed | 15480 | 15718 | 2017-12-08 | 2018-06-15
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/995288 — Construction of IAY House -IAY REG. NO. MP2833698 | Completed | 15480 | 12040 | 2018-01-05 | 2018-04-03
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/995432 — Construction of IAY House -IAY REG. NO. MP2889478 | Completed | 15480 | 15136 | 2017-10-10 | 2018-03-31
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/995442 — Construction of IAY House -IAY REG. NO. MP2895059 | Completed | 15480 | 15590 | 2018-01-05 | 2018-09-29
MANDSAUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004118/IF/IAY/997553 — Construction of IAY House -IAY REG. NO. MP3808043 | Completed | 15480 | 15534 | 2017-12-08 | 2018-06-15
MANDSAUR | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1716004118/LD/9926709487 — Khel Maidan Bhardawad | Completed | 390000 | 275822 | 2014-06-18 | 2016-02-07
MANDSAUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1716004118/RC/126 — Bhardawad Gav ko Richhavara sadak se jodne hetu sadak nirman bhardawad | Completed | 251000 | 179378 | 2011-05-08 | 2012-03-27
MANDSAUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/209 — panchparmeshwar mangilal ke makan se khawara ke kuwe tak CC Road bhardawad | Completed | 92000 | 130976 | 2012-04-09 | 2013-10-27
MANDSAUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034158375 — Panchparmeshwar CC Road Jora Babji mandir se Gaffu | Completed | 166000 | 164536 | 2012-12-15 | 2014-06-27
MANDSAUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034160894 — Panchparmeshwar CC Road गफुर के मकान से नूर के मका | Completed | 72000 | 71637 | 2013-01-19 | 2014-06-27
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034171254 — vihdayak+nregs Dhangar mohalle me c c road | Completed | 107000 | 106946 | 2013-06-14 | 2013-12-21
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034179164 — Panchparmeshwar CC Road Mangilal ke makan se Khawra Kup tak ka Atirikt Shesh Karya | Completed | 36000 | 35200 | 2013-09-16 | 2013-11-12
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034179171 — Panchparmeshwar CC Road Pradhan Mantri Sadak se Pu | Completed | 169000 | 131877 | 2013-09-16 | 2014-06-27
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034182994 — Panchparmeshwar Pradhanmantri Road se Fariyad ke m | Completed | 166000 | 166231 | 2013-09-16 | 2014-08-30
MANDSAUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034189601 — panchparmeshawar CC Road PMGSY se Eidgah tak | Deleted | 88000 | 0 | 2013-04-14
MANDSAUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034219984 — panchparmeshwar cc road ishabnur ke makan se pm sa | Completed | 59000 | 59109.9 | 2014-06-04 | 2015-01-30
MANDSAUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034219988 — panchparmeshwar cc road pm sadak se idgah tak | Completed | 88000 | 73332 | 2014-06-04 | 2015-01-30
MANDSAUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034293616 — Panch parmeshwer c c rode fariyad bhai ke Makan se madra | Completed | 36000 | 28620 | 2015-12-22 | 2016-05-10
MANDSAUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034318422 — MNREGA + PANCH PARMESHVER CC ROAD NIRMAN AJA BASTI SE ISHAK KE MAKAN TAK | Deleted | 0 | 0 | 2016-10-02
MANDSAUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034318425 — MNREGA + PANCH PARMESHVER CC ROAD NIRMAN AJA BASTI SE ISHAK KE MAKAN TAK | Deleted | 107000 | 0 | 2016-10-02
MANDSAUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034318427 — MGNREGA + PANCH PARMESHVER CC ROAD AJA BASTI ME GANPAT KE MAKAN SE PATELA BA KI MAKAN KI AUR | Completed | 52000 | 51895 | 2017-01-12 | 2017-11-02
MANDSAUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034318434 — MANREGA + PANCH PARMESHVER CC ROAD NIRMAN AJA BASTI ISHAK KE MAKAN SE | Completed | 107000 | 109482 | 2017-01-30 | 2017-11-02
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034321064 — सीसी रोड निर्माण (पंचपर्मेश्वर+मनरेगा) प्रधान्मंत्री रोड से अजीज शाह के घर तक | Closed | 34000 | 0 | 2017-04-25
MANDSAUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034321443 — SUDUR GRAM SAMAPARK SADAK BHARDAWAD SE KATKADI KANKAD TAK | Closed | 1486000 | 0 | 2016-10-02
MANDSAUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034343791 — CC Road NIrman jaya haji ke makan se Farukha ke makan tak | Completed | 549000 | 64500 | 2017-08-03 | 2017-10-25
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034368123 — सीसी रोड निर्माण | Closed | 0 | 0 | 2018-04-01
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034387381 — सीसी रोड निर्माण (मनरेगा + पंच परमेश्वर इशाक फकरू के मकान से कासम मुखिया के मकान तक | Completed | 33000 | 28188 | 2018-04-21 | 2018-08-13
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034387395 — सीसी रोड निर्माण (मनरेगा + विधायक निधि प्रधानमंत्री सड़क से अर्जुन धनगर के मकान की और | Completed | 163000 | 149742 | 2018-05-05 | 2018-09-10
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034393621 — सीसी रोड निर्माण (मनरेगा + पंच परमेश्वर तयब लाडू के मकान से उंकारलाल के मकान तक | Completed | 14000 | 13050 | 2018-09-26 | 2018-11-05
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034393622 — सीसी रोड निर्माण (मनरेगा + पंच परमेश्वर शरीफ खा के मकान से अम्बालाल के मकान तक | Completed | 38000 | 33564.6 | 2018-09-27 | 2018-11-11
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034393623 — सीसी रोड निर्माण (मनरेगा + पंच परमेश्वर प्रधानमंत्री रोड से नूर पोकरिया के मकान तक | Completed | 28000 | 25578 | 2018-09-27 | 2018-11-15
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034438564 — सीसी रोड निर्माण | Closed | 0 | 0 | 2019-04-01
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034444404 — सीसी रोड निर्माण मनरेगा + पंच परमेश्वर प्रधानमंत्री रोड से अम्बालाल के मकान से होते हुए इशक गफूर के | Completed | 67000 | 68068 | 2019-03-04 | 2019-06-30
MANDSAUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034444405 — सीसी रोड निर्माण मनरेगा + पंच परमेश्वर प्रधानमंत्री रोड से इस्माइल ताजू के मकान तक | Completed | 34000 | 33866 | 2019-03-04 | 2019-06-30
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034477652 — सीसी रोड निर्माण (पंचपर्मेश्वर+मनरेगा) प्रधान्मंत्री रोड से लीयाकत शाह के घर तक | Closed | 14000 | 0 | 2019-04-26
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034479631 — सीसी रोड निर्माण (पंचपरमेश्वर+मनरेगा) इस्माईल जमाल की दुकान से हनुमानजी मंदिर होते हुए पीएम सड़क तक | Completed | 88000 | 49906 | 2019-10-29 | 2020-07-20
MANDSAUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034507825 — ग्रेवल रोड प्रधानमंत्री रोड से शमशान होते हुये कब्रिस्तान तक | Closed | 0 | 0 | 2019-10-02
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034550480 — सीसी रोड व् नाली निर्माण (14वा वित्त+मनरेगा) नाहर खा जमाल के मकान से तय्यब के मकान तक | Completed | 70000 | 66063 | 2020-12-09 | 2021-06-25
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034550481 — सीसी रोड व् नाली निर्माण (14वा वित्त+मनरेगा) फारुख हाजी के मकान से कासम मुखिया के मकान तक | Completed | 36000 | 29830 | 2020-11-29 | 2021-06-26
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034566379 — सुदूर ग्राम सम्पर्क ग्रेवल सड़क ग्राम भरडावद में खाखरी कुए से कोचवी सीमा तक | Completed | 1634030.7 | 1632005.14 | 2021-05-06 | 2022-11-25
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034569738 — सुदूर ग्राम सम्पर्क सड़क ग्राम भरडावद में खान्खरो के कुओ से कोचवी सीमा तक | Closed | 0 | 0 | 2021-04-15
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034587773 — सीसी रोड व नाली निर्माण (15वा वित्त+मनरेगा) गणपत के मकान से रमेश के मकान की और | Completed | 19000 | 17949 | 2021-11-28 | 2022-01-17
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034587774 — सीसी रोड व नाली निर्माण (15वा वित्त+मनरेगा) पीएम रोड से अजीजशाह के मकान की और | Completed | 32000 | 31845 | 2021-11-28 | 2021-12-30
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034646736 — नाली निर्माण मनरेगा + १५ व वित् अबरार के घर से सरकारी हेंडपंंप तक | Completed | 19000 | 14586 | 2023-08-11 | 2024-02-12
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034655891 — सीसी रोड व नाली निर्माण मनरेगा+ ५,१५,वां वित्‍त इस्‍माईल के घर से युसूफ के घर की ओर | Completed | 52000 | 47023 | 2023-09-25 | 2025-07-03
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034669136 — सीसी रोड व नाली निर्माण १५वि+मनरेगा ग्राम भावगढ़ में ,मोडीराम के मकान से शांतिबाई के मकान तक | Deleted | 25000 | 0 | 2023-08-15
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034825938 — सीसी रोड एंव नाली निर्माण मनरेगा एंव 15 वा वित्त मोहम्मद बापू के घर से अशरफ के घर की ओर ग्राम भरडावद | Ongoing | 53000 | 49085 | 2025-04-12
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004118/RC/22012034835204 — सीसी रोड व नाली निर्माण मनरेगा व 15 वा वित्त मद से ग्राम भरडावद में युसूफ अली के घर से शाबीर इशाक के | Ongoing | 69000 | 45414 | 2025-09-02
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034839072 — सुदूर सडक निर्माण ग्राम भरडावद में नूर पोकरिया के मकान से कटकडी राजस्थान सीमा तक | Approved | 0 | 0 | 2025-03-01
MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004118/RC/22012034839417 — खेत सड़क निर्माण ग्राम भरडावद में नूरजी पोकरिया के मकान से कटकड़ी राजस्थान सीमा तक ग्रेवल सड़क निर्माण | Ongoing | 1300000 | 1251712.8 | 2025-04-17
MANDSAUR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1716004118/RC/33 — सडक निर्माण भरडावद | Completed | 301000 | 319617.4 | 2008-10-13 | 2013-03-27
MANDSAUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1716004118/RC/92 — BHARDAVAD SE KAROLI SADAK | Completed | 300000 | 513558 | 2010-09-20 | 2011-07-21
MANDSAUR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1716004118/RC/93 — BHARADWAD SE RICHHAVARA SADAK NIRMAN | Completed | 352000 | 355432 | 2011-01-01 | 2011-04-27
MANDSAUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1716004118/RC/94 — BHARDAWAD SE KOCHVI SADAK NIRMAN | Completed | 241000 | 362472 | 2011-10-03 | 2012-07-31
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1716004118/RS/22012034497601 — नाला निर्माण (ड्रेनेज चेनेल) (पंचपरमेश्वर+मनरेगा) ग्राम भरडावद में खोरी मोहल्ले में | Closed | 192000 | 0 | 2020-09-28
MANDSAUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1716004118/RS/22012034497602 — नाला निर्माण (ड्रेनेज चेनेल) (पंचपरमेश्वर+मनरेगा) ग्राम भरडावद में खोरी मोहल्ले मेन रोड पर | Completed | 200000 | 12160 | 2020-09-29 | 2025-02-17
MANDSAUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004118/RS/22012034620020 — नाली निर्माण कार्य (१५वावित्+मनरेगा) गणपत के मकान से कचरू के मकान की और | Completed | 8000 | 7913 | 2021-12-05 | 2022-03-05
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004118/RS/22012034694821 — नाला निर्माण मनरेगा +१५ व वित्त चोकीदार के घर की और ग्राम भरडावद | Completed | 132000 | 131233.54 | 2023-05-29 | 2023-11-29
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004118/RS/22012035118537 — यू शेप नाली निर्माण मनरेगा+ 5/15 वा वित्‍त फारूख भाई के घर से कंवरलाल अहिरवार की ओर | Completed | 36000 | 34869 | 2023-10-09 | 2024-10-16
MANDSAUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1716004118/WC/10 — Recharge peet Bhardavad | Completed | 333000 | 108403 | 2008-06-04 | 2008-06-04
MANDSAUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004118/WC/129 — Nirmal Nir kup Nirman Bhardawad | Completed | 370000 | 183800 | 2011-04-04 | 2011-07-03
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034478697 — सोकपिट निर्माण हैण्डपम्प स्कूल के पास,स्कूल के अंदर1,भरडावद | Closed | 0 | 0 | 2019-07-22
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034487555 — सोकपिट निर्माण हेंड्पुम्प सरकारी स्कुल मे | Completed | 4848.98 | 3872 | 2019-11-27 | 2020-05-20
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034487557 — सोकपिट निर्माण हेंड्पुम्प सरकारी स्कुल मे 02 | Completed | 4848.98 | 4576 | 2019-11-27 | 2020-05-20
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034487559 — सोकपिट निर्माण हेंड्पुम्प जोडा बवजी | Completed | 4848.98 | 3872 | 2019-11-27 | 2020-05-20
MANDSAUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034487561 — सोकपिट निर्माण हेंड्पुम्प घाटी उपर | Completed | 4848.98 | 2464 | 2019-12-02 | 2020-05-20
MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034696885 — कूप रिचार्ज निर्मलनीर कूप तालाब के पास भरडावद | Completed | 14467.3 | 10350 | 2021-08-30 | 2022-08-01
MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034696889 — कूप रिचार्ज निर्मलनीर कूप खामड के पास भरडावद | Completed | 14467.3 | 10488 | 2021-08-30 | 2022-08-01
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034948903 — डग आउट पोंड निर्माण मगरा पर | Completed | 195181.98 | 166872 | 2022-05-24 | 2023-07-25
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004118/WC/22012034971239 — डग आउट पोंड निर्माण कार्य ग्राम भरडावद | Closed | 0 | 0 | 2022-05-01
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004118/WC/22012034971254 — चेक डेम कार्य खाल पर | Closed | 0 | 0 | 2022-05-01
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004118/WC/22012035286066 — JGSA 2025 Dugwell Recharge निर्मल नीर कूप कब्रिस्तान | Approved | 25899.46 | 0 | 2025-04-10
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004118/WC/22012035286076 — JGSA 2025 Dugwell Recharge निर्मल नीर कुँव आजम लाला के घर के पास | Closed | 25899.46 | 1044 | 2025-06-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004118/WC/22012035292385 — JGSA 2025 Dugwell Recharge नुरजा बी पति इस्माइल | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1716004118/WC/9993668729 — Parcolation Tank Bhardawad | Deleted | 0 | 0 | 2015-10-02
MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1716004118/WH/22012034452329 — तालाब मरम्मत शमशान के पास | Closed | 0 | 0 | 2021-10-02
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1716004118/WH/22012034931045 — चेकडेम कार्य खाल पर | Closed | 0 | 0 | 2022-04-01