## Work List
Exported on: 2026-09-06 10:26:45
Filters applied:
Data source: MGNREGA + VBGRAMG
District: MANDSAUR
Block: All
Panchayat: BHOOKHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1716004121/AV/22012034650554 — शमशान शेड निर्माण नदी के किनारे ग्राम भूखी | Completed | 226381.46 | 224368.89 | 2024-06-10 | 2026-04-12
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716004121/DP/22012034572787 — व़क्षारोपण कार्य भुखी | Ongoing | 411833.91 | 216867 | 2023-01-12
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004121/DP/22012034575872 — निर्मल नीर कूप निर्माण ग्राम भूखी नई आबादी 2023-24 | Completed | 623477.53 | 543371 | 2023-09-11 | 2026-04-12
MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004121/DP/22012034580760 — वृक्षारोपण कार्य निर्मल नीर कूप के पास ग्राम भूखी 2023-24 | Ongoing | 428242.09 | 206304 | 2024-08-20
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004121/DP/22012034588287 — वसुधा वंदन अमृत वाटिका नवीन तालाब परिसर के पास 2023-24 | Physically Completed | 55847.4 | 26029 | 2023-08-23 | 2026-06-28
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1716004121/DP/22012034609037 — सामुदायिक पोषण वा‍टिका कार्य तालाब के पास ग्राम भूखी 2023-24 | Closed | 849655.89 | 0 | 2023-10-04
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035055953 — खेत तालाब निर्माण कारी बाई -बसन्तीलाल | Closed | 0 | 0 | 2023-01-01
MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035055956 — खेत तालाब निर्माण बापूलाल -रतनलाल गुर्जर | Closed | 0 | 0 | 2023-01-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035088678 — खेत तालाब निर्माण बापूलाल -रतनलाल गुर्जर | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035088680 — खेत तालाब निर्माण कंवरलाल - किशनलाल | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035088682 — खेत तालाब निर्माण जगदीश - शवराम 2023-24 | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035090133 — खेत तालाब निर्माण गीता बाई -रतनलाल 2023-24 | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035090134 — खेत तालाब निर्माण कारी बाई -बसन्तीलाल | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035090137 — खेत तालाब निर्माण प्रकाश -तुलसीराम | Closed | 385261.22 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035090145 — खेत तालाब निर्माण प्रभुलाल -जग्गनाथ | Closed | 0 | 0 | 2023-05-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035096845 — निजी फलो उद्यान सुगनलाल -प्रभुलाल कीर 2023-24 | Physically Completed | 161000 | 63890 | 2023-07-08 | 2026-06-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097353 — निजी फलो उद्यान चुन्नीलाल -देवा कीर 2023-24 | Physically Completed | 161000 | 63528.94 | 2023-06-30 | 2026-06-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097358 — निजी फलो उद्यान घीसालाल-धन्ना कीर 2023-24 | Physically Completed | 161000 | 59761.98 | 2023-06-11 | 2026-06-25
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097363 — निजी फलो उद्यान दिलीप -शवराम कीर 2023-24 | Physically Completed | 161000 | 25194 | 2023-06-08 | 2026-06-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097366 — निजी फलो उद्यान कनीराम -मांगीलाल 2023-24 | Physically Completed | 161000 | 26078 | 2023-06-26 | 2026-06-30
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097374 — निजी फलो उद्यान डालुराम -घासी 2023-24 | Physically Completed | 161000 | 27490 | 2023-06-11 | 2026-06-30
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035097379 — निजी फलो उद्यान गीताबाई -रतनलाल सूर्यवंशी 2023-24 | Closed | 161000 | 0 | 2023-04-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035103372 — खेत तालाब निर्माण कारी बाई -बसन्तीलाल 2023-24 | Ongoing | 360117.09 | 228981.5 | 2023-06-20
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035108527 — निजी फलो उद्यान सोहन बाई -बगदीराम 2023-24 | Physically Completed | 161000 | 25963 | 2023-07-12 | 2026-06-30
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035108534 — निजी फलो उद्यान जगदीश -रतनलाल कीर 2023-24 | Closed | 130000 | 0 | 2023-04-29
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035110149 — निजी फलो उद्यान शांतिबाई - सुखलाल 2023-24 | Physically Completed | 161000 | 74135 | 2023-06-22 | 2026-06-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035118483 — खेत तालाब निर्माण प्रकाश -तुलसीराम मेगवाल | Closed | 0 | 0 | 2023-06-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035125143 — निजी फलो उद्यान बगदीबाई -शवराम कीर 2023-24 | Physically Completed | 130000 | 73073.98 | 2023-07-08 | 2026-06-28
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035129225 — निजी फलो उद्यान गट्टू बाई -कारुलाल 2023-24 | Closed | 130000 | 0 | 2023-06-01
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035129230 — निजी फलो उद्यान बंशीलाल -बगदीराम कीर 2023-24 | Physically Completed | 161000 | 18564 | 2023-08-09 | 2026-06-28
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035132202 — निजी फलो उद्यान गीताबाई बाई बेवा बंशीलाल 2023-24 | Physically Completed | 130000 | 21870 | 2024-07-04 | 2026-06-30
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1716004121/IF/22012035132205 — निजी फलो उद्यान गीताबाई बेवा रंगलाल गुर्जर 2023-24 | Closed | 161000 | 0 | 2023-08-05
MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004121/IF/22012035137295 — निजी फलो उद्यान बापुलाल- धन्‍नाजी गुर्जर 2023-24 | Ongoing | 161000 | 140910 | 2023-08-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035348756 — JGSA 2025 Dugwell Recharge बापुलाल पिता धन्ना जी | Physically Completed | 25899.46 | 23211.76 | 2025-05-23 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490179 — JGSA 2025 Dugwell Recharge Gopal Mangilal | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490193 — JGSA 2025 Dugwell Recharge Prabulal Gotam | New | 0 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490225 — JGSA 2025 Dugwell Recharge Ramesh Rupa | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490238 — JGSA 2025 Dugwell Recharge Sugan Prabhulal | New | 0 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490246 — JGSA 2025 Dugwell Recharge Raniwas Shankarlal | New | 0 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490263 — JGSA 2025 Dugwell Recharge Shantilal Gopal | New | 0 | 0 | 2025-04-25
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035490269 — JGSA 2025 Dugwell Recharge Ambalal Dulichand | New | 0 | 0 | 2025-04-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537222 — JGSA2025 DUGWELL RECHARGE RAMNIVAS SHANKARLAL | New | 0 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537230 — JGSA2025 DUGWELL RECHARGE RAMNIVAS SHANKARLAL | Approved | 25899.46 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537251 — JGSA 2025 PRABHULAL GOTAM JI | Approved | 0 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537276 — JGSA 2025 DUGWELL GOPAL MANGILAL GURJAR | Physically Completed | 25899.46 | 21451.84 | 2025-05-23 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537298 — JGSA 2025 DUGWELL SUGANLAL PRABHULAL GIR | Physically Completed | 25899.46 | 21490.72 | 2025-05-23 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537321 — JGSA 2025 DUGWELL MOHANLAL BHERA JI GIR | Approved | 25899.46 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537341 — JGSA 2025 DUGWELL JAGDISH SHAVRAM JI GIR | New | 0 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537342 — JGSA 2025 DUGWELL JAGDISH SHAVRAM JI GIR | Physically Completed | 25899.46 | 21451.84 | 2025-05-23 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1716004121/IF/22012035537369 — JGSA 2025 DUGWELL LILABAI BHERULAL | Approved | 25899.46 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537402 — JGSA 2025 KHET TALAB BANSHILAL HUDDI BAI BHANVARLAL KIR | Approved | 55865.38 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537432 — JGSA 2025 KHET TALAB JAGDISH SHAVRAM | Approved | 55865.38 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716004121/IF/22012035537472 — JGSA 2025 KHET TALAB BANSHILAL GOPAL MANGILAL | Approved | 55865.38 | 0 | 2025-05-15
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035541657 — JGSA 2025 Dugwell Recharge Prabhulal gotam | Physically Completed | 25899.46 | 19863.48 | 2025-05-30 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035541674 — JGSA 2025 Dugwell Recharge Shantilal gopal | Approved | 25899.46 | 0 | 2025-05-21
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716004121/IF/22012035541687 — JGSA 2025 Dugwell Recharge Ambalal dulichand | Physically Completed | 25899.46 | 9396 | 2025-05-30 | 2026-06-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/4774390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126034218 | Completed | 23490 | 21717 | 2024-11-21 | 2026-01-30
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/4774440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126049335 | Physically Completed | 23490 | 21924 | 2025-01-14 | 2026-06-21
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/4779859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127971237 | Physically Completed | 23490 | 22626 | 2024-12-11 | 2026-06-26
MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/4779862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127971701 | Completed | 23490 | 22410 | 2025-02-02 | 2026-01-30
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/5824712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126626190 | Physically Completed | 23490 | 23490 | 2025-10-29 | 2026-06-26
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/5844881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141939940 | Physically Completed | 23490 | 23490 | 2025-10-29 | 2026-06-26
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/5844930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126020283 | Ongoing | 27000 | 22707 | 2025-10-29
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6124874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126265655 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6126676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127199666 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6141575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126275676 | Ongoing | 27000 | 8400 | 2026-02-25
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6173688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125521861 | Ongoing | 27000 | 0 | 2026-02-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6184448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128657858 | Approved | 27000 | 0 | 2026-03-11
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6197544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126065169 | Approved | 27000 | 0 | 2026-03-11
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127587551 | Ongoing | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120355578 | Approved | 27000 | 0 | 2026-03-21
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126018401 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125835456 | Approved | 27000 | 0 | 2026-03-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125524075 | Approved | 27000 | 0 | 2026-03-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126642974 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125530556 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126632382 | Approved | 23490 | 0 | 2026-04-27
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141939687 | Approved | 23490 | 0 | 2026-04-27
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141939838 | Ongoing | 23490 | 0 | 2026-04-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141939884 | Approved | 27000 | 0 | 2026-03-25
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141939961 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125527051 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127476341 | Approved | 23490 | 0 | 2026-04-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144861647 | Approved | 27000 | 0 | 2026-03-25
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126269127 | Approved | 23490 | 0 | 2026-04-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126299298 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126854224 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125800403 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125533483 | Approved | 27000 | 0 | 2026-03-23
MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716004121/IF/IAY/6230867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127513628 | Ongoing | 23490 | 3900 | 2026-04-27
MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1716004121/RC/22012034644088 — सुदूर ग्राम संपर्क सड़क निर्माण कार्य ग्राम भूखी से कुमारिया तक | Completed | 2446974.93 | 2253103 | 2023-08-23 | 2025-03-28
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004121/RC/22012034674843 — सीमेंट कांक्रीट रोड व नाली निर्माण 5/15वि+मनरेगा ग्राम भूखी में प्रभुलाल के घर से पुलिया की और | Completed | 17000 | 16940.6 | 2024-08-19 | 2024-10-16
MANDSAUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716004121/RC/22012034824833 — सीसी रोड व नाली निर्माण मनरेगा एंव १५ वा वित्‍त ग्राम भूखी में अम़तराम के मकान प्रभुलाल के मकान तक | Physically Completed | 62000 | 52092 | 2025-01-10 | 2026-06-22
MANDSAUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004121/RS/22012034690334 — नाली निर्माण मनरेगा + १५ वा वित् हेंड पंप से ढीकोला रास्ते तक | Closed | 18000 | 0 | 2023-02-12
MANDSAUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004121/RS/22012034690335 — नाली निर्माण मनरेगा + १५ व वित् सुरजपुरी के घर से हेंड पंप तक | Closed | 3000 | 0 | 2023-02-14
MANDSAUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1716004121/RS/22012034690336 — नाली निर्माण मनरेगा + १५ व वित् बालाजी मंदिर से देवीलाल गुर्जर के घर तक | Closed | 3000 | 0 | 2023-02-13
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004121/WC/22012035024638 — परकोलेशन टेंक कुमारिया भुखी | Closed | 0 | 0 | 2022-10-02
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004121/WC/22012035024963 — डग आउट पोंड कार्य भुखी सर्वे न. 29 | Completed | 498645.8 | 489754 | 2023-07-28 | 2023-11-29
MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004121/WC/22012035037610 — अमृत सरोवर कार्य ग्राम भूखी | Closed | 0 | 0 | 2023-01-01
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1716004121/WC/22012035044112 — अमृत सरोवर तालाब निर्माण स्कुल के पास ग्राम भूखी | Completed | 2005000 | 1789759.5 | 2023-08-18 | 2025-01-27
MANDSAUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1716004121/WC/22012035089898 — डग आउट पोंड निर्माण ग्राम कुम्हारिया | Closed | 672569.77 | 0 | 2023-06-01
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004121/WC/22012035310334 — JGSA 2025 Dugwell Recharge Nirmal nir Nai Abadi Bhuki | Physically Completed | 25899.46 | 23994.76 | 2025-05-31 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004121/WC/22012035310340 — JGSA 2025 Dugwell Recharge Nirmal Nir Nai Abadi Karulal ke khet ke pass | Physically Completed | 25899.46 | 22689.76 | 2025-05-31 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004121/WC/22012035310342 — JGSA 2025 Dugwell Recharge NIrmal NIr Rundi Par | Physically Completed | 25899.46 | 21906.76 | 2025-05-30 | 2026-04-11
MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716004121/WC/22012035310346 — JGSA 2025 Dugwell Recharge Nirman Nir Kumhariya Nai Abadi | Physically Completed | 25899.46 | 22689.76 | 2025-05-31 | 2026-04-11