## Work List
Exported on: 2026-10-22 00:05:20
Filters applied:
Data source: VBGRAMG
District: MANDSAUR
Block: All
Panchayat: GADARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1716005019/AV/22012034658076 — NANDAN FALODHYAN KACHRULAL GANESH RAM BALAI GAADRIYA | New | 0 | 0 | 2024-04-15
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1716005019/AV/22012034658566 — niji khet par nandan kacharulal maganlal meena | New | 0 | 0 | 2024-04-01
SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1716005019/AV/22012034668234 — Shanti Dham Shed Nirman Kolavi | New | 0 | 0 | 2025-08-15
SITAMAU | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716005019/DP/22012034566820 — Vraksharopan shantidham Gadriya | Ongoing | 441799.65 | 0 | 2022-09-15
SITAMAU | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716005019/DP/22012034566822 — Vraksharopan shantidham Chota Gadriya | Ongoing | 441799.65 | 0 | 2022-09-15
SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716005019/DP/22012034566823 — Vraksharopan shantidham kolwi | Ongoing | 441799.65 | 0 | 2023-06-09
SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1716005019/DP/22012034580820 — Vraksharopan prathimik vidhyalay kolwi boundaryvall me | Ongoing | 411964.38 | 0 | 2023-08-08
SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1716005019/DP/22012034580821 — Vraksharopan panchayat bhawan boundaryvall me gadriya | Ongoing | 777232.78 | 7450 | 2023-09-24
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1716005019/DP/22012034624261 — Vraksharopan Ekikrat Madhyamik Shala Elvi | Ongoing | 604599.42 | 0 | 2024-09-12
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1716005019/DP/22012034624268 — Vraksharopan Narsingh Mataji ke Pass Chhota Gadriya | Approved | 0 | 0 | 2024-06-08
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005019/IF/22012035255051 — निजी खेत में नंदन फलोउद्यान लालसिंह रामसिंह | Ongoing | 189000 | 7163.52 | 2024-09-12
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005019/IF/22012035255059 — निजी खेत में नंदन फलोउद्यान जीतेन्द्र मदनलाल | Ongoing | 189000 | 11650.08 | 2024-09-12
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005019/IF/22012035257708 — निजी खेत में नंदन फलोउद्यान कचरूलाल गणेशराम | Ongoing | 156000 | 0 | 2024-09-26
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005019/IF/22012035257720 — निजी खेत में नंदन फलोउद्यान कचरूलाल मगन | Approved | 156000 | 0 | 2024-06-08
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005019/IF/22012035257773 — निजी खेत में नंदन फलोउद्यान कंचनबाई रामनारायण | Ongoing | 156000 | 0 | 2024-09-26
SITAMAU | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/125194 — Construction of IAY House -IAY REG. NO. MP-16-005-019-003/15 | Approved | 27000 | 0 | 2016-01-27
SITAMAU | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/125195 — Construction of IAY House -IAY REG. NO. MP-16-005-019-003/18 | Approved | 27000 | 0 | 2016-01-27
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6176280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123448169 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6176651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125003625 | Ongoing | 27000 | 12000 | 2026-08-06
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6176667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126362202 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6177395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126170950 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6177483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126748799 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6177826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127248197 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6178005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124999431 | Ongoing | 27000 | 7800 | 2026-04-18
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6178435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124946863 | Ongoing | 27000 | 15600 | 2026-05-16
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6178799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126163211 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118805416 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127259885 | Ongoing | 27000 | 12000 | 2026-06-15
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126172948 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126149935 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125168159 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6180858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127125458 | Ongoing | 27000 | 24000 | 2026-07-31
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6181811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125145842 | Ongoing | 27000 | 12000 | 2026-07-21
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6182171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125176426 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6182316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127353229 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6184016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124995609 | Ongoing | 27000 | 16800 | 2026-07-11
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6184315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126165546 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6184697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127204469 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6184913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127266577 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6185026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125127436 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6185709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126397746 | Ongoing | 27000 | 3600 | 2026-08-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6185873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127351693 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6186729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125177266 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6186742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125004201 | Ongoing | 27000 | 4200 | 2026-09-23
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6186822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126321327 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6186841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125148921 | Ongoing | 27000 | 0 | 2026-05-16
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6188355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123447640 | Ongoing | 27000 | 12600 | 2026-08-06
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6188573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126360451 | Ongoing | 27000 | 7200 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6188754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125155134 | Ongoing | 27000 | 7800 | 2026-06-01
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6189327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126158560 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6189420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125157143 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6189530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126428073 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6190340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125125597 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6191435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126299375 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6191976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126037822 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6192222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126748299 | Ongoing | 27000 | 25200 | 2026-07-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6193546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123447120 | Ongoing | 27000 | 8400 | 2026-08-06
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6193586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125175674 | Ongoing | 27000 | 7800 | 2026-05-16
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6193695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126428762 | Ongoing | 27000 | 12000 | 2026-05-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6193702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125162822 | Ongoing | 27000 | 9300 | 2026-06-01
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6193907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127356917 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6194034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127116680 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6194219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126353794 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125174880 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127349827 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126404710 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125173547 | Ongoing | 27000 | 0 | 2026-06-01
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126160859 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6195987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118353107 | Physically Completed | 27000 | 0 | 2026-05-11 | 2026-09-20
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6196130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127260732 | Ongoing | 27000 | 27000 | 2026-07-21
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6196210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126153103 | Ongoing | 27000 | 0 | 2026-05-16
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6196792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125001511 | Ongoing | 27000 | 15600 | 2026-05-16
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6197681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124964333 | Ongoing | 27000 | 4200 | 2026-09-23
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6197843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126302343 | Ongoing | 27000 | 3600 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6198601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127207376 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6198627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127159976 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6198635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125581830 | Ongoing | 27000 | 7800 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6199391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125161000 | Ongoing | 27000 | 7800 | 2026-08-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6200892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125178006 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6201169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125151136 | Ongoing | 27000 | 4200 | 2026-05-16
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6201793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127265642 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6202707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124991700 | Ongoing | 27000 | 0 | 2026-09-23
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6202802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127258134 | Ongoing | 27000 | 12000 | 2026-08-06
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6202846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126396639 | Ongoing | 27000 | 7200 | 2026-04-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126334668 | Ongoing | 27000 | 7200 | 2026-08-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125171386 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125002631 | Ongoing | 27000 | 3600 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127202354 | Physically Completed | 27000 | 0 | 2026-05-11 | 2026-09-20
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126747355 | Ongoing | 27000 | 0 | 2026-05-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6203924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127249017 | Ongoing | 27000 | 7800 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6204193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125158044 | Ongoing | 27000 | 12000 | 2026-06-15
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6204880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127256585 | Ongoing | 27000 | 7500 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6206045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126698671 | Ongoing | 27000 | 12000 | 2026-08-06
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6207138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126166624 | Ongoing | 27000 | 12000 | 2026-07-31
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6209365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124956930 | Ongoing | 27000 | 7800 | 2026-04-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6209378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125160049 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6209603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126151045 | Ongoing | 27000 | 7800 | 2026-06-15
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6209820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126747812 | Ongoing | 27000 | 15600 | 2026-07-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6210780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125163830 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6211008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120789 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6211504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126152192 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6211575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127254934 | Ongoing | 27000 | 7800 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6211903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125584344 | Ongoing | 27000 | 7800 | 2026-08-25
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6211912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127334956 | Ongoing | 27000 | 12000 | 2026-07-21
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6212533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127246599 | Ongoing | 27000 | 9300 | 2026-05-16
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6213207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125164761 | Ongoing | 27000 | 4200 | 2026-05-16
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6213719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125154136 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6213889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125152006 | Ongoing | 27000 | 0 | 2026-06-15
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6214119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124965141 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6215186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118805305 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6215305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127255740 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6216677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125003130 | Ongoing | 27000 | 7800 | 2026-05-16
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6216753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126157403 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6216797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126147609 | Ongoing | 27000 | 15600 | 2026-08-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6217277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125169928 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6217400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127264735 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6262781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125159018 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6263232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124845546 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6264910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126352640 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6265331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126403804 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6267047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127151713 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6267755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127356206 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6268250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127377445 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6280848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127152496 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6284068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127376261 | Approved | 27000 | 0 | 2026-02-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6285104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126400975 | Approved | 27000 | 0 | 2026-02-22
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6291629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127115995 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6297603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126148700 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6297936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126164386 | Approved | 27000 | 0 | 2026-02-07
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6343573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125135100 | Approved | 27000 | 0 | 2026-07-02
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005019/IF/IAY/6343600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127126622 | Approved | 27000 | 0 | 2026-07-02
SITAMAU | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005019/RC/22012034822146 — cc sadak mata ji chabutre se hansraj meena ke makan tk chota gadariya | Approved | 69000 | 0 | 2024-04-15
SITAMAU | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005019/RC/22012034822148 — cc sadak bakshuram ke makan se radheshyam banjara ke makanki our alvi | Approved | 64000 | 0 | 2024-04-15
SITAMAU | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1716005019/RC/22012034838690 — Greval Sadak Gadriya Abadi se Elvi sadak ki or Kanaiyalal ke khet se Elvi gram Abadi tak | Approved | 0 | 0 | 2024-10-02
SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1716005019/RC/22012034840309 — Gravel Sadak Gadriya Aabadi se Elvi sadak ki or kanaiyalal ke khet se Elvi gram Abadi Tak | Ongoing | 1536000 | 0 | 2025-04-14