## Work List
Exported on: 2026-09-07 01:07:44
Filters applied:
Data source: VBGRAMG
District: MANDSAUR
Block: All
Panchayat: KACHRIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SITAMAU | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1716005086/DP/22012034569163 — वृक्षारोपण निर्माण कार्य ( शासकीय तलाई के पास ) काचरिया | Ongoing | 408025.29 | 0 | 2022-11-28
SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1716005086/DP/22012034577350 — निर्मल नीर कूप निर्माण खेल मैदान के पास | Ongoing | 648422.71 | 0 | 2023-06-20
SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1716005086/IF/22012035342095 — khet talab lalsingh jujharsingh | Ongoing | 147621.16 | 0 | 2025-06-05
SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716005086/IF/22012035514784 — khet talab amarsingh bherusingh | Ongoing | 147621.16 | 0 | 2025-05-19
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716005086/IF/22012035514806 — khet talab sohankunver gulabsingh | New | 0 | 0 | 2025-04-14
SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1716005086/IF/22012035517551 — kapil dhara kailash utsavlal par dug well richarj | New | 0 | 0 | 2025-04-01
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716005086/IF/22012035519268 — khet talab sohankunver gulabsingh | Ongoing | 25899.46 | 0 | 2025-05-20
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716005086/IF/22012035540249 — khet talab raghusingh kacharusingh | Approved | 147621.16 | 0 | 2025-04-01
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716005086/IF/22012035551763 — Khet talab bagdiram ramlal | New | 0 | 0 | 2025-04-14
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1716005086/IF/22012035551788 — Khet talab bagdiram ramlal | Approved | 0 | 0 | 2025-04-14
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716005086/IF/22012035609714 — Ek Bagiya Ma ke Nam Pushpa Bai darji | Ongoing | 235664.27 | 0 | 2025-09-11
SITAMAU | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/130405 — Construction of IAY House -IAY REG. NO. MP-16-005-086-002/25 | Approved | 27000 | 0 | 2016-02-03
SITAMAU | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/130406 — Construction of IAY House -IAY REG. NO. MP-16-005-086-002/7 | Approved | 27000 | 0 | 2016-02-03
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/4778567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127422266 | Physically Completed | 23490 | 0 | 2024-11-24 | 2026-08-16
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/4781322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128949440 | Ongoing | 27000 | 0 | 2025-02-05
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5113661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137248483 | Approved | 27000 | 0 | 2025-02-20
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5114903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125432139 | Physically Completed | 23490 | 0 | 2025-06-28 | 2026-08-02
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5116114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131083986 | Ongoing | 27000 | 0 | 2025-04-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5116117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131084450 | Ongoing | 27000 | 0 | 2025-04-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5116118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131084563 | Ongoing | 27000 | 0 | 2025-04-25
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5116119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131084597 | Ongoing | 27000 | 0 | 2025-04-25
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5117851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123589172 | Approved | 27000 | 0 | 2025-02-23
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5120733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128934270 | Physically Completed | 23490 | 0 | 2025-06-15 | 2026-07-05
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5126631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124554093 | Ongoing | 27000 | 0 | 2025-04-11
SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5128667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127424241 | Approved | 27000 | 0 | 2025-02-19
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5130949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123601145 | Ongoing | 27000 | 0 | 2025-05-23
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5131974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129737011 | Ongoing | 27000 | 0 | 2025-05-19
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5134113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128945123 | Ongoing | 27000 | 0 | 2025-05-19
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5177795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127421894 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-08-09
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5200992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124565359 | Ongoing | 27000 | 0 | 2025-04-11
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5267211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148810945 | Ongoing | 27000 | 0 | 2025-05-23
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/5412475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128918975 | Ongoing | 27000 | 0 | 2025-06-15
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6130327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148153215 | Ongoing | 27000 | 5100 | 2026-08-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6130436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128947556 | Physically Completed | 23490 | 0 | 2026-04-19 | 2026-08-23
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6130448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129029130 | Ongoing | 27000 | 4800 | 2026-05-09
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6131679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124541607 | Ongoing | 27000 | 9300 | 2026-07-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6131715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130629729 | Physically Completed | 23490 | 0 | 2026-04-19 | 2026-08-09
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6132179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130910008 | Ongoing | 27000 | 0 | 2026-04-19
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6132690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127423436 | Ongoing | 27000 | 0 | 2026-06-12
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6135441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148856270 | Ongoing | 27000 | 0 | 2026-05-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6137467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131083801 | Ongoing | 27000 | 9300 | 2026-05-09
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6137677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128920511 | Ongoing | 27000 | 0 | 2026-04-19
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6137681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128929037 | Ongoing | 27000 | 0 | 2026-04-19
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6137684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128933455 | Ongoing | 27000 | 5100 | 2026-05-27
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6137686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128937874 | Approved | 27000 | 0 | 2026-02-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6140144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123599892 | Ongoing | 27000 | 0 | 2026-05-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6140150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123604193 | Ongoing | 27000 | 7500 | 2026-05-27
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6140801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128119741 | Approved | 27000 | 0 | 2026-01-29
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6141410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128958205 | Ongoing | 27000 | 5100 | 2026-05-27
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6143533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124549141 | Ongoing | 27000 | 9300 | 2026-06-12
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6144481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128147668 | Ongoing | 27000 | 10200 | 2026-08-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6148046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137248521 | Ongoing | 27000 | 9300 | 2026-05-27
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6148749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142728880 | Ongoing | 27000 | 0 | 2026-08-07
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6152371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125425369 | Approved | 27000 | 0 | 2026-01-29
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6152374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125426128 | Ongoing | 27000 | 4200 | 2026-05-27
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6152375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125426819 | Approved | 27000 | 0 | 2026-01-29
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6152377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125428225 | Physically Completed | 23490 | 0 | 2026-04-19 | 2026-08-02
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6152613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125428952 | Ongoing | 27000 | 0 | 2026-08-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6155085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148816247 | Ongoing | 27000 | 0 | 2026-04-19
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6157752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127428819 | Approved | 27000 | 0 | 2026-02-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6158162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130652694 | Ongoing | 27000 | 9300 | 2026-05-27
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6158163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130652730 | Ongoing | 27000 | 0 | 2026-05-09
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6160723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127423820 | Ongoing | 27000 | 0 | 2026-06-12
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6160758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128961152 | Ongoing | 27000 | 5100 | 2026-08-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6161904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130642868 | Ongoing | 27000 | 5100 | 2026-08-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6161906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130642885 | Ongoing | 27000 | 5100 | 2026-06-12
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6162705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128935536 | Ongoing | 27000 | 5100 | 2026-05-27
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6162918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123596077 | Physically Completed | 23490 | 0 | 2026-04-19 | 2026-07-05
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6163742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146033003 | Ongoing | 27000 | 0 | 2026-05-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6164551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128931739 | Ongoing | 27000 | 5100 | 2026-07-11
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6168866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148863929 | Ongoing | 27000 | 5100 | 2026-06-12
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6171781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148814540 | Ongoing | 27000 | 0 | 2026-05-27
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6174727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130648479 | Ongoing | 27000 | 0 | 2026-05-08
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6174899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128951057 | Ongoing | 27000 | 300 | 2026-04-19
SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6180569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127417815 | Ongoing | 27000 | 4200 | 2026-07-11
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6194990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128929435 | Approved | 27000 | 0 | 2026-03-02
SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1716005086/IF/IAY/6201784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137251189 | Approved | 27000 | 0 | 2026-01-29
SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1716005086/RC/22012034846550 — 15wa vitt mgnrega mukhy marg se prakashdas ke makan ki aur cc rod | Ongoing | 52000 | 0 | 2025-09-03
SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1716005086/RC/22012034848914 — 05 wa vitt mgnrega narayansingh ke makan se mataji ke mandir ki aur kachariya nali nirman | Ongoing | 30000 | 0 | 2025-09-16
SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716005086/WC/22012035290152 — nirmalnir bakli raste par dug well richarj | Approved | 25899.46 | 0 | 2025-04-14
SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1716005086/WC/22012035306551 — nirmalnir khel medhan ke pas par dug well richarj | Approved | 25899.46 | 0 | 2025-04-01
SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1716005086/WH/22012034940364 — TALAB JIRNODWAR MAHUWA RASTE KE PAAS KACHRIYA | Approved | 0 | 0 | 2024-06-08