## Work List
Exported on: 2026-09-06 02:35:05
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: PARMARKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718001030/DP/22012034444571 — Samudayik kup paramara khedi | Ongoing | 535000 | 0 | 2019-03-08
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001030/IF/22012034447414 — kup nirman dola-bhagga | Ongoing | 210000 | 0 | 2019-03-08
KHACHAROD | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/3387791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1870582 | Approved | 27000 | 0 | 2021-12-02
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/4576350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118565198 | Physically Completed | 23490 | 7308 | 2025-02-17 | 2026-08-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/4765895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802472 | Ongoing | 27000 | 8400 | 2026-07-02
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5247104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116807961 | Physically Completed | 23490 | 7308 | 2025-10-30 | 2026-08-25
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5259729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573045 | Physically Completed | 23490 | 0 | 2026-02-07 | 2026-08-23
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5270532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116157543 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-07-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5304064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387178 | Physically Completed | 23490 | 3654 | 2026-01-10 | 2026-08-16
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5309231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116157967 | Physically Completed | 23490 | 0 | 2025-11-15 | 2026-08-02
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5322219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572936 | Completed | 23490 | 0 | 2025-10-31 | 2026-07-29
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5336198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802613 | Completed | 23490 | 0 | 2025-10-30 | 2026-07-17
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5359365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573061 | Completed | 23490 | 0 | 2025-10-30 | 2026-07-29
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5368143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802015 | Ongoing | 27000 | 4200 | 2025-10-30
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5424061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529523 | Completed | 23490 | 0 | 2025-10-31 | 2026-07-29
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5428953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387287 | Completed | 23490 | 0 | 2025-10-31 | 2026-07-29
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5430954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116154155 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-07-19
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5514062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116157355 | Completed | 23490 | 0 | 2025-10-31 | 2026-07-17
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5620666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116808122 | Ongoing | 27000 | 4450 | 2025-10-31
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5710911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116804691 | Ongoing | 27000 | 8400 | 2026-07-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121781074 | Physically Completed | 23490 | 0 | 2026-05-08 | 2026-08-02
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126397582 | Physically Completed | 23490 | 0 | 2026-05-25 | 2026-08-09
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116157389 | Ongoing | 27000 | 1800 | 2026-01-10
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387252 | Ongoing | 27000 | 8400 | 2026-07-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529593 | Physically Completed | 23490 | 0 | 2026-04-10 | 2026-08-02
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5711524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529629 | Ongoing | 27000 | 0 | 2026-04-10
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5716758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118601702 | Ongoing | 27000 | 0 | 2026-08-17
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/5878107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387278 | Physically Completed | 23490 | 0 | 2026-05-25 | 2026-08-09
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6101582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806791 | Physically Completed | 23490 | 3654 | 2026-05-12 | 2026-08-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126396512 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120923829 | Physically Completed | 23490 | 4200 | 2026-05-18 | 2026-08-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120923905 | Ongoing | 27000 | 2100 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116805119 | Completed | 23490 | 0 | 2026-05-04 | 2026-07-29
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116805282 | Physically Completed | 23490 | 3654 | 2026-05-12 | 2026-08-25
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116805727 | Physically Completed | 23490 | 0 | 2026-05-12 | 2026-08-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116807930 | Physically Completed | 23490 | 3654 | 2026-05-12 | 2026-08-25
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116808763 | Physically Completed | 23490 | 0 | 2026-05-12 | 2026-08-25
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6102889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755786 | Ongoing | 27000 | 4200 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6103670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573407 | Physically Completed | 23490 | 0 | 2026-05-18 | 2026-08-25
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6103910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387153 | Ongoing | 27000 | 7554 | 2026-05-12
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6104441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812399 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6104493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811518 | Physically Completed | 23490 | 3654 | 2026-05-19 | 2026-08-25
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6104561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812119 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6104870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123580540 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124092298 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117572985 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573423 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123580154 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387174 | Ongoing | 27000 | 8400 | 2026-06-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387272 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6105862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387297 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6106137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811618 | Ongoing | 27000 | 8400 | 2026-05-04
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6106353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811844 | Approved | 27000 | 0 | 2026-02-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6106355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812712 | Physically Completed | 23490 | 3600 | 2026-05-12 | 2026-08-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6108679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118566038 | Ongoing | 27000 | 8100 | 2026-05-19
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6108759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116804960 | Ongoing | 27000 | 2800 | 2026-05-12
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6108833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118623555 | Ongoing | 27000 | 0 | 2026-05-04
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6111891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126394987 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6112564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116299308 | Ongoing | 27000 | 0 | 2026-05-04
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6112711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573295 | Ongoing | 27000 | 8400 | 2026-06-12
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6112764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529051 | Ongoing | 27000 | 7854 | 2026-05-04
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6113864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387158 | Ongoing | 27000 | 3654 | 2026-05-12
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6114298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120924024 | Ongoing | 27000 | 4200 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6114731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117573155 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6114852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124089452 | Ongoing | 27000 | 8400 | 2026-06-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6115138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387165 | Ongoing | 27000 | 0 | 2026-06-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6115139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117387235 | Ongoing | 27000 | 8400 | 2026-05-18
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6115190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124090632 | Ongoing | 27000 | 7854 | 2026-05-04
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6115568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116808322 | Ongoing | 27000 | 8100 | 2026-07-02
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001030/IF/IAY/6243490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118793411 | Ongoing | 23490 | 4200 | 2026-08-13