## Work List
Exported on: 2026-10-28 04:53:28
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: ARJALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001074/AV/22012034370406 — Aganwadi bhwan | Deleted | 0 | 0 | 2017-05-07
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1718001074/AV/22012034392439 — Aganwadi bhwan | Ongoing | 180000 | 128371 | 2019-01-25
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001074/AV/22012034468502 — Aganwadi bhwan | Deleted | 0 | 0 | 2019-08-15
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001074/AV/22012034505246 — Aganwadi bhawan | Suspended | 180000 | 0 | 2020-02-02
KHACHAROD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001074/DP/1अर्जला जे — अर्जला जेट्रोफा व़क्षारोपण कार्य अर्जला | Deleted | 76000 | 0 | 2008-08-23
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001074/DP/22012034240878 — Vrakhshropn santidhamparisar g.p.arjala | Completed | 335000 | 11084 | 2017-05-13 | 2018-07-04
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/DP/22012034538308 — व्रक्षा रोपण सामुदायिक मड़ावदा रोड पर | Closed | 685575.78 | 0 | 2021-08-16
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718001074/DW/22012034295631 — Samudayak kup nirman | Completed | 380000 | 45306 | 2017-03-03 | 2018-07-04
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001074/IF/22012035075324 — Vikaram navin kup niraman gram arjala | Completed | 280343.16 | 247978.68 | 2023-04-20 | 2024-03-11
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573312 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR CHATAR SINGH KESAR SINGH ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573313 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR MANGU SINGH BHERU JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573315 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR KUSHAL SINGH RAGHUBAR JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573317 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR KAMAL SINGH BALVANT JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573318 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR RAJENDRA SINGH BHUVAN JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573323 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR AMRU NANDA JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573326 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR UMRAV NANDA JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573330 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR MATHURA LAL MANGILAL JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573333 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR PRAKASH BHARAT JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573338 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR KAMALABAI CHANDAR JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718001074/IF/22012035573342 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR VIKRAM MEGHA JI ARJALA | Approved | 25899.46 | 0 | 2025-05-10
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/9993679292 — Raju bai IAY | Completed | 14310 | 14170 | 2015-10-08 | 2016-08-22
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/9993679309 — Sankarlal /Iya | Completed | 14310 | 14170 | 2015-10-08 | 2016-08-22
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1218391 — Construction of IAY House -IAY REG. NO. MP2260182 | Completed | 15480 | 14592 | 2018-03-01 | 2018-06-28
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1218392 — Construction of IAY House -IAY REG. NO. MP2260230 | Completed | 15480 | 14604 | 2018-03-01 | 2018-06-28
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1218465 — Construction of IAY House -IAY REG. NO. MP2313415 | Completed | 15480 | 15660 | 2018-03-01 | 2018-08-21
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1218467 — Construction of IAY House -IAY REG. NO. MP2317179 | Completed | 15480 | 14616 | 2018-03-01 | 2018-07-21
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410524 — Construction of IAY House -IAY REG. NO. MP2912649 | Completed | 15480 | 14964 | 2018-04-02 | 2018-09-15
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410534 — Construction of IAY House -IAY REG. NO. MP2943250 | Completed | 15480 | 14964 | 2018-04-02 | 2018-08-23
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410540 — Construction of IAY House -IAY REG. NO. MP2955696 | Completed | 15480 | 14616 | 2018-04-02 | 2018-07-11
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410559 — Construction of IAY House -IAY REG. NO. MP2969512 | Completed | 15480 | 15660 | 2018-04-02 | 2018-07-08
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410567 — Construction of IAY House -IAY REG. NO. MP2998757 | Completed | 15480 | 15660 | 2018-04-20 | 2018-09-15
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410625 — Construction of IAY House -IAY REG. NO. MP3125849 | Completed | 15480 | 14616 | 2018-04-02 | 2018-06-15
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1410855 — Construction of IAY House -IAY REG. NO. MP3676523 | Completed | 15480 | 15660 | 2018-04-02 | 2018-09-20
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1483761 — Construction of IAY House -IAY REG. NO. MP2910309 | Completed | 15480 | 15486 | 2018-04-02 | 2018-08-23
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1485211 — Construction of IAY House -IAY REG. NO. MP2970592 | Completed | 15480 | 14442 | 2018-04-02 | 2018-07-28
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1485374 — Construction of IAY House -IAY REG. NO. MP2976807 | Completed | 15480 | 14616 | 2018-04-02 | 2018-06-28
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1489000 — Construction of IAY House -IAY REG. NO. MP3126248 | Completed | 15480 | 15660 | 2018-04-02 | 2018-07-11
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1544837 — Construction of IAY House -IAY REG. NO. MP3972062 | Completed | 15480 | 14616 | 2018-04-02 | 2018-10-30
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1560267 — Construction of IAY House -IAY REG. NO. MP2906862 | Completed | 15480 | 16530 | 2018-04-20 | 2018-12-17
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1560338 — Construction of IAY House -IAY REG. NO. MP2969685 | Completed | 15480 | 15660 | 2018-04-02 | 2018-07-03
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1858961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4368017 | Completed | 15660 | 15486 | 2018-06-30 | 2018-10-11
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1859357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4390140 | Completed | 15660 | 14964 | 2018-06-30 | 2018-10-11
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1859358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4390102 | Completed | 15660 | 15138 | 2018-07-13 | 2018-10-11
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1863241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4310734 | Completed | 15660 | 14616 | 2018-06-30 | 2018-10-30
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1863475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4717979 | Completed | 15660 | 14616 | 2018-07-06 | 2018-10-30
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1863476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4718126 | Completed | 15660 | 14976 | 2018-07-13 | 2019-04-29
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/1864074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5385209 | Completed | 15660 | 16182 | 2018-06-30 | 2018-09-20
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2127586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4721073 | Completed | 15840 | 15984 | 2019-07-10 | 2020-05-23
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2127786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4728975 | Completed | 15840 | 14784 | 2019-07-10 | 2020-01-21
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2127789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4729045 | Completed | 15840 | 15664 | 2019-07-10 | 2020-01-07
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2128053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4739994 | Completed | 15840 | 16008 | 2019-07-10 | 2020-05-23
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2128121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4741906 | Completed | 15840 | 14784 | 2019-07-10 | 2020-01-21
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2128367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4751221 | Completed | 15840 | 14784 | 2019-07-10 | 2020-01-21
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2129456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4722378 | Completed | 15840 | 15664 | 2019-07-10 | 2020-01-07
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2129541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4728926 | Completed | 15840 | 15840 | 2019-07-10 | 2019-09-19
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2129721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4756327 | Completed | 15840 | 14952 | 2019-07-10 | 2020-06-10
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2151400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5303728 | Completed | 15840 | 15840 | 2019-07-10 | 2019-09-19
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2151999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5314546 | Completed | 15840 | 15664 | 2019-07-10 | 2020-01-07
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2152003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5314637 | Completed | 15840 | 15840 | 2019-07-10 | 2020-02-19
KHACHAROD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/2152366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5324137 | Completed | 15840 | 14784 | 2019-07-10 | 2020-01-21
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/3664318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878179 | Completed | 18360 | 17952 | 2022-06-27 | 2022-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/3670176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113654379 | Completed | 18360 | 17952 | 2022-06-27 | 2022-11-24
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/3717171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120896838 | Completed | 18360 | 18360 | 2022-07-16 | 2022-11-23
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/3717173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120896921 | Completed | 18360 | 18037 | 2022-06-27 | 2023-09-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/3787738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130735118 | Completed | 18360 | 18275 | 2022-06-27 | 2023-07-16
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4062914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464651 | Completed | 18360 | 18360 | 2022-06-27 | 2022-12-30
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4140113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113648042 | Completed | 18360 | 17663 | 2022-06-27 | 2023-07-14
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001074/IF/IAY/4141211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878251 | Ongoing | 27000 | 0 | 2023-09-12
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4170625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141505206 | Completed | 18360 | 18258 | 2022-07-16 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4175429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106469870 | Completed | 18360 | 17544 | 2022-06-27 | 2023-04-20
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4187673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113654445 | Completed | 18360 | 18360 | 2022-06-27 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4188141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878083 | Completed | 18360 | 18292 | 2022-07-16 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4188259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464440 | Completed | 18360 | 17544 | 2022-06-27 | 2022-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4196098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121771609 | Completed | 18360 | 17867 | 2022-10-29 | 2023-07-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4202033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141255799 | Completed | 18360 | 18156 | 2022-10-29 | 2023-03-21
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4202308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127909971 | Completed | 18360 | 17544 | 2022-06-27 | 2022-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4205684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148827304 | Completed | 18360 | 18190 | 2022-07-16 | 2023-09-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4360513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114958358 | Completed | 18360 | 18190 | 2022-11-12 | 2023-07-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4362406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130731865 | Completed | 18360 | 18700 | 2022-11-12 | 2023-10-18
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4386625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464986 | Completed | 18360 | 18241 | 2022-12-16 | 2023-09-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4386626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106465110 | Completed | 18360 | 18241 | 2022-12-16 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4389246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141512450 | Completed | 18360 | 18567 | 2023-01-10 | 2023-12-22
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4489959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141512465 | Completed | 23490 | 22608 | 2025-01-20 | 2026-02-20
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4545474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106477594 | Completed | 21870 | 21870 | 2024-10-23 | 2025-03-17
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4553332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113648865 | Completed | 23490 | 21384 | 2024-11-12 | 2025-10-16
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4554938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113660395 | Completed | 23490 | 22482 | 2025-01-20 | 2025-10-16
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4637389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130724023 | Completed | 21870 | 21870 | 2024-11-11 | 2025-03-17
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4689085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106942959 | Completed | 21870 | 21627 | 2024-11-11 | 2025-03-06
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4741084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878036 | Completed | 21870 | 21627 | 2024-11-11 | 2025-02-19
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4743124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113847590 | Completed | 21870 | 21627 | 2024-11-11 | 2025-02-19
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4791251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142036260 | Completed | 21870 | 21627 | 2024-11-11 | 2025-02-19
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4791252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142036655 | Completed | 21870 | 21870 | 2024-11-19 | 2025-03-06
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4791253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142036671 | Completed | 21870 | 21870 | 2024-11-11 | 2025-02-19
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4792376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141512485 | Completed | 23490 | 21384 | 2024-11-11 | 2026-02-01
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4792378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141514436 | Completed | 23490 | 20412 | 2024-11-19 | 2026-02-20
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/4872756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464867 | Completed | 23490 | 20412 | 2025-01-09 | 2026-02-20
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5146774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464559 | Physically Completed | 23490 | 17226 | 2025-04-18 | 2026-02-14
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5151870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120896753 | Completed | 23490 | 22707 | 2025-04-27 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5162873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130731892 | Completed | 23490 | 21402 | 2025-04-18 | 2026-04-28
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5173647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130735146 | Physically Completed | 23490 | 10962 | 2025-08-21 | 2026-02-26
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5177014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121705261 | Completed | 23490 | 23229 | 2025-08-11 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5225891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142131971 | Completed | 23490 | 21402 | 2025-04-27 | 2025-10-16
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5227764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141517117 | Physically Completed | 23490 | 17226 | 2025-04-18 | 2026-02-14
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001074/IF/IAY/5242150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878144 | Completed | 23490 | 20097 | 2025-04-18 | 2026-07-22
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5259076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106921161 | Completed | 23490 | 23490 | 2025-07-10 | 2026-03-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001074/IF/IAY/5267064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113647900 | Ongoing | 27000 | 14601 | 2025-04-27
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5267548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142037641 | Completed | 23490 | 22446 | 2025-07-10 | 2026-03-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5271300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113645163 | Completed | 23490 | 21402 | 2025-06-11 | 2026-04-28
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5272431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142037238 | Completed | 23490 | 23229 | 2025-08-21 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5273588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878206 | Completed | 23490 | 21924 | 2025-07-10 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5277661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106883877 | Completed | 23490 | 21924 | 2025-08-21 | 2026-04-05
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5279973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142038025 | Completed | 23490 | 20358 | 2025-04-18 | 2025-10-16
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5280237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464746 | Completed | 23490 | 23490 | 2025-06-11 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5288276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130731826 | Completed | 23490 | 23229 | 2025-04-25 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5290102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113645258 | Completed | 23490 | 22446 | 2025-04-18 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5304562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106921097 | Completed | 23490 | 20097 | 2025-07-10 | 2025-10-16
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5328757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114958384 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5329522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120592184 | Completed | 23490 | 21402 | 2025-04-27 | 2026-02-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5340863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130724087 | Completed | 23490 | 23490 | 2025-06-11 | 2026-03-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5342256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113658362 | Physically Completed | 23490 | 20097 | 2025-07-10 | 2026-05-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001074/IF/IAY/5464330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142037857 | Approved | 27000 | 0 | 2025-04-08
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5620571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148886354 | Completed | 23490 | 23490 | 2025-06-11 | 2026-02-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5621535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106472728 | Completed | 23490 | 21924 | 2025-08-11 | 2026-02-07
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5621751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142037002 | Completed | 23490 | 21924 | 2025-08-11 | 2026-04-06
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5621858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127909038 | Completed | 23490 | 21924 | 2025-07-10 | 2025-12-31
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5621866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106465040 | Completed | 23490 | 21141 | 2025-06-11 | 2026-02-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5621908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106454813 | Completed | 23490 | 23229 | 2025-06-11 | 2026-03-11
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/5625987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130731806 | Completed | 23490 | 21924 | 2025-08-01 | 2025-12-31
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/584064 — Construction of IAY House -IAY REG. NO. MP1336565 | Completed | 15030 | 15128 | 2017-02-20 | 2018-02-21
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/584086 — Construction of IAY House -IAY REG. NO. MP1343437 | Completed | 15030 | 15295 | 2017-02-05 | 2018-03-31
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/722263 — Construction of IAY House -IAY REG. NO. MP1757011 | Completed | 15030 | 15480 | 2017-05-07 | 2018-03-31
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/722479 — Construction of IAY House -IAY REG. NO. MP1762637 | Completed | 15030 | 15480 | 2017-05-07 | 2018-03-31
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/739204 — Construction of IAY House -IAY REG. NO. MP2209330 | Completed | 15030 | 15480 | 2017-05-07 | 2018-04-10
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/740325 — Construction of IAY House -IAY REG. NO. MP2237679 | Completed | 15030 | 19780 | 2017-05-07 | 2018-04-10
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/740626 — Construction of IAY House -IAY REG. NO. MP2245260 | Completed | 15030 | 15480 | 2017-05-07 | 2018-03-31
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/740627 — Construction of IAY House -IAY REG. NO. MP2245264 | Completed | 15030 | 15540 | 2017-05-07 | 2018-04-24
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/988210 — Construction of IAY House -IAY REG. NO. MP1403519 | Completed | 15480 | 15848 | 2017-05-07 | 2018-04-20
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/988216 — Construction of IAY House -IAY REG. NO. MP1404864 | Completed | 15480 | 14508 | 2017-05-20 | 2018-04-24
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/988372 — Construction of IAY House -IAY REG. NO. MP1457205 | Completed | 15480 | 15672 | 2017-05-07 | 2018-04-24
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/989397 — Construction of IAY House -IAY REG. NO. MP1746982 | Completed | 15480 | 15492 | 2017-05-07 | 2018-04-20
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/989398 — Construction of IAY House -IAY REG. NO. MP1747037 | Completed | 15480 | 15552 | 2017-05-07 | 2018-04-22
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/989786 — Construction of IAY House -IAY REG. NO. MP1853916 | Completed | 15480 | 14964 | 2017-05-07 | 2018-02-21
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/992955 — Construction of IAY House -IAY REG. NO. MP2209323 | Completed | 15480 | 15996 | 2017-05-07 | 2017-12-07
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/992956 — Construction of IAY House -IAY REG. NO. MP2209342 | Completed | 15480 | 15528 | 2017-05-07 | 2018-04-20
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001074/IF/IAY/993147 — Construction of IAY House -IAY REG. NO. MP2243143 | Completed | 15480 | 15612 | 2017-05-07 | 2018-04-28
KHACHAROD | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001074/LD/3799392657 — शातिधामपरिसरअर्जला४.९१३ | Completed | 491300 | 333132 | 2013-06-05 | 2016-06-20
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1718001074/PG/22012034312210 — Khel medan midil school arjala | Completed | 180000 | 5160 | 2017-05-28 | 2018-06-14
KHACHAROD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001074/RC/1/अर्जला स — अर्जला से बरलाई काकड पहुच मार्ग | Completed | 250000 | 104361 | 2010-06-07 | 2013-09-19
KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/1/मनरेगा प — मनरेगा+पंच परमेश्‍वर सीसी व नाली निर्माण कार्य १.३ | Completed | 138000 | 116351 | 2012-06-08 | 2013-07-30
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034188118 — तीसरी किशत मनरेगा अम्‍बामात मदिरसे नरसिह मार्ग के | Completed | 23900 | 23713 | 2014-02-19 | 2014-05-15
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034188122 — चोथी किशत मनरेगा रामचन्‍द्र के घर से भैसासुरीमदि | Completed | 157000 | 157311.9 | 2013-12-28 | 2014-04-14
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034201366 — पाचवीकिशत बालुकाशीराम केघरसेअम्‍बामाता मदिरतकअर्ज | Completed | 94300 | 88754 | 2014-02-26 | 2014-09-25
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034209514 — Antrik marag murmikarad nali nirman Arjala | Completed | 476300 | 227344 | 2014-02-28 | 2016-06-16
KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034264171 — panchparmeswar | Deleted | 0 | 0 | 2014-10-02
KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034264177 — panchparmeswar | Deleted | 0 | 0 | 2014-10-02
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034293801 — Panchparmeswar+narega | Deleted | 0 | 0 | 2015-12-10
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034294488 — lokendra s ke ghar se bhuwan ske ghar ki our | Completed | 100000 | 52764 | 2016-03-16 | 2018-06-06
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034301698 — मनरेगा | Deleted | 0 | 0 | 2016-04-01
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034327363 — teja ji mandir setalab nale ki our | Completed | 132750 | 67134 | 2017-02-28 | 2017-12-07
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034328845 — Gendalal ke ghar se gordhan ke ghar tak | Completed | 60000 | 53106 | 2017-02-28 | 2017-12-07
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034339368 — सी0सी0रोड नालि निर्माण मागंुकेघर से कनिरा के घर की ओर | Completed | 36000 | 35432 | 2017-06-01 | 2018-04-26
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034339370 — सी0सी0 रोड एवं नाली निर्माण रमेश के घर से भुवान के घर तक | Completed | 53000 | 46704 | 2017-06-01 | 2018-07-07
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034350927 — cc road nali nirman gordhan ke ghar se gama bai ke ghar ki our | Completed | 47000 | 46440 | 2017-08-25 | 2017-12-07
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001074/RC/22012034373737 — Sudur Sam park sadsk | Deleted | 0 | 0 | 2017-06-07
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034373917 — सीसी राेड | Deleted | 0 | 0 | 2018-01-26
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034390823 — chandra ke ghar se magu ke ghar ki our cc road | Completed | 62775 | 64554 | 2018-07-18 | 2026-02-27
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034390925 — men road se dalpat singh ke ghar ki our | Completed | 74062 | 73776 | 2018-10-06 | 2019-02-27
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034441520 — Cc road | Deleted | 0 | 0 | 2019-01-27
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034441778 — मरम्मत सी सी रोड | Deleted | 0 | 0 | 2019-01-26
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034449446 — सीसी राेड | Deleted | 0 | 0 | 2018-04-14
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034463600 — मेन रोड से शांति परिसर तक(5.92500) | Deleted | 0 | 0 | 2019-01-26
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034463699 — men road se santidham parisar tak | Completed | 88875 | 90992 | 2019-06-11 | 2020-06-26
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034513797 — मरम्मत सी सी रोड | Deleted | 0 | 0 | 2019-10-02
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034535173 — बलवंतसिंह के घर रामसिंह के घर की ओर सीसीरोड निर्माण | Deleted | 0 | 0 | 2020-04-14
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034535268 — बलवंतसिंह के घर रामसिंह के घर की ओर सीसीरोड निर्माण | Completed | 77500 | 67210 | 2020-08-29 | 2021-06-09
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034553396 — पंचायत प्रागण मे सीसी निर्माण कार्य | Completed | 34000 | 32022 | 2020-12-29 | 2021-10-02
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034569399 — सीसी रोड माध्यमिक शाला प्राथमिक शाला भवन अर्जला | Deleted | 0 | 0 | 2021-04-14
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034569400 — सीसी रोड निर्माण माध्यमिक शाला/प्राथमिक शाला भवन अर्जला | Completed | 84000 | 86202 | 2021-05-26 | 2021-11-24
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034625802 — cc road rukhama ke ghar se hoapital chorahe ki our ripering | Completed | 94650 | 92802 | 2023-06-19 | 2024-02-22
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034629472 — नाली निर्माण रुकमा के घर से अस्पताल चौराहे की ओर | Completed | 56850 | 55250 | 2023-05-29 | 2024-02-22
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034629586 — बालू काशीराम के घर से उपस्वास्थ केंद्र तक सीसी रोड+नाली निर्माण | Completed | 106000 | 104533 | 2023-07-06 | 2024-07-27
KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034629588 — रमेश बगदीराम के घर से मेन रोड तक सीसी रोड+नाली निर्माण | Closed | 0 | 0 | 2022-10-02
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034629589 — रमेश बगदीराम के घर से मेन रोड तक सीसी रोड+नाली निर्माण | Completed | 104000 | 103564 | 2023-10-06 | 2026-02-27
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034835875 — ciment conkrit road ram janki mandir chok | Approved | 0 | 0 | 2024-10-04
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718001074/RC/22012034837475 — cc rode nirman bhwar singh ke ghar se shree ram janki mandir ki our | Approved | 0 | 0 | 2024-10-04
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Road for Community | Construction of Road and Culvert | 1718001074/RC/22012034837955 — cc road bhawar singh ke ghar se shreeram janki mandir ki or | Approved | 45031 | 0 | 2024-04-01
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Road for Community | Construction of Road and Culvert | 1718001074/RC/22012034837960 — cc road shreeram janki mandir chok | Approved | 47317 | 0 | 2024-04-01
KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001074/RC/42/मनरेगा — मनरेगा पचपरमेश्‍वर दितीयकिशतअर्जला 101300 | Completed | 101500 | 94754 | 2013-02-12 | 2013-10-03
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034307207 — Shochalay Nirman Arjla जगदीश दास 120 | Completed | 9800 | 9038 | 2016-11-27 | 2018-05-11
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034307980 — शौचालयनिर्मण मांगुसिंहपिता भेरूसिंह 116 | Completed | 10800 | 8371 | 2016-11-27 | 2018-05-14
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034309738 — Sochlay nirman jadish sankar 1200 | Completed | 9800 | 9504 | 2017-03-09 | 2018-05-11
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329581 — Sochlay nirman vikram megha1200 | Completed | 9800 | 9504 | 2017-03-09 | 2018-05-11
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329586 — Sochlay nirman kaniram hariram2200 | Completed | 9800 | 9504 | 2017-03-09 | 2018-05-11
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329589 — Sochlay nirman dayaram magu2200 | Deleted | 10800 | 0 | 2016-04-08
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329591 — Sochlay nirman balu magu 2200 | Completed | 9800 | 9504 | 2017-03-09 | 2018-05-11
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329592 — Sochlay nirman puna fatt2200 | Completed | 9800 | 9564 | 2017-04-08 | 2018-07-12
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034329593 — Sochlay vardram hariram2200 | Completed | 9800 | 8502 | 2017-03-09 | 2018-07-12
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034338997 — Sochlay nirman ratanlal nagga 2200 | Completed | 9800 | 9314 | 2017-04-08 | 2018-07-12
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034339001 — Sochlay nirman chandra nagu2200 | Completed | 9800 | 9486 | 2017-04-08 | 2018-07-12
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034339003 — Sochlay manu bai 2200 | Completed | 9800 | 9736 | 2017-04-08 | 2018-05-06
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034339004 — Sochlay nirman nanuram nagu2200 | Completed | 9800 | 2211 | 2017-04-08 | 2023-04-11
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034339015 — Sochlay gordhan lal bagdiram2200 | Completed | 9800 | 9708 | 2017-04-08 | 2018-05-06
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034341142 — Sochlay nirman balu kashiram 2200 | Deleted | 0 | 0 | 2017-05-04
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034341144 — Sochlay nirman gendalal naharji 2200 | Completed | 9800 | 9564 | 2017-05-04 | 2018-07-12
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034341146 — Sochlay badri hira2200 | Completed | 9800 | 8420 | 2017-05-23 | 2018-05-11
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034341147 — Sochlay nirman rames sankar2200 | Completed | 9800 | 9564 | 2017-05-26 | 2018-05-11
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034347529 — Sochlay nirman sampat bai rama2200 | Completed | 9800 | 9220 | 2017-05-23 | 2018-05-14
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001074/RS/22012034348607 — Sochlay nirman arjun madak 2200 | Completed | 9800 | 7034 | 2017-05-26 | 2018-07-12
KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718001074/RS/22012034658162 — Samudayik shochalay niraman | Completed | 88000 | 50320 | 2022-05-28 | 2024-07-31
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of Panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1718001074/SK/9993648286 — Bharat Nirman Rajeev Gandhi Sewa Kendra,ARJALA | Completed | 1285000 | 969035.22 | 2016-01-13 | 2019-07-02
KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1718001074/WC/22012034447190 — पानी निकासी एवं स्टोरेज हेतु नाला निर्माण दौलतराम के खेत से तालाब नाले तक | Physically Completed | 157000 | 87324 | 2019-03-11 | 2020-07-09
KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034487251 — जल सवर्धन | Deleted | 0 | 0 | 2019-08-15
KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1718001074/WC/22012034516401 — Nala trenching | Completed | 107395.2 | 68820 | 2020-01-23 | 2024-03-04
KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1718001074/WC/22012034516403 — Nala trenching | Deleted | 0 | 0 | 2019-10-02
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1718001074/WC/22012034529962 — nala trenchig dinesh ke khet se rajendra singh ke khet ki our | Completed | 53837.44 | 42180 | 2020-05-02 | 2020-07-09
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034553022 — छतरसिंह के खेत से राजेंद्रसिंह के खेत की ओर नाला निर्माण | Completed | 101521.86 | 93570 | 2020-06-04 | 2026-02-15
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001074/WC/22012034600018 — नाला टचिंग राजेन्द्रसिह के खेत से भवरसिह खेत की और ग्राम अर्जला | Completed | 111108.07 | 101892 | 2021-02-01 | 2021-11-24
KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1718001074/WC/22012034600021 — रीर्चार्ज पोंड तालाब नाले के पास ग्राम अर्जला | Closed | 0 | 0 | 2020-10-28
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001074/WC/22012034620811 — नाला टेंचिग भवरसिंह के खेत से कनीराम के खेत की ओर ग्राम अर्जला | Completed | 199501.23 | 174531 | 2021-03-10 | 2022-03-03
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1718001074/WC/22012034710867 — लक्ष्मण सिंह के खेत से कारू के खेत कि और नाला निर्माण | Deleted | 0 | 0 | 2021-04-14
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001074/WC/22012034710928 — नाला ट्रेंचिगकार्यलक्ष्मण सिंह के खेत से कारू केखेत कि और ग्राम अर्जला | Completed | 113858.15 | 116784 | 2022-03-08 | 2023-02-05
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034844241 — सोखता गड्ढा प्राथमिक विद्यालय ग्राम अर्जला | Deleted | 0 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1718001074/WC/22012034844245 — सोखता गड्ढा माद्यमिक विद्यालय ग्राम अर्जला | Deleted | 0 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1718001074/WC/22012034844246 — सोखता गड्ढा माद्यमिक विद्यालय ग्राम अर्जला | Deleted | 0 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851283 — CTR सोखता गड्ढा 1 अर्जला | Completed | 14467.3 | 9264 | 2021-10-25 | 2022-12-26
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851298 — CTR सोखता गड्ढा 2 अर्जला | Completed | 14467.3 | 9264 | 2021-10-25 | 2022-12-26
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851307 — CTR सोखता गड्ढा 3 अर्जला | Completed | 14467.3 | 8878 | 2021-10-25 | 2021-12-05
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851325 — CTR सोखता गड्ढा 4 अर्जला | Completed | 14467.3 | 10422 | 2021-10-25 | 2022-12-26
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851334 — CTR सोखता गड्ढा 5 अर्जला | Completed | 14467.3 | 9264 | 2021-10-25 | 2023-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1718001074/WC/22012034851343 — CTR सोखता गड्ढा 6 अर्जला | Completed | 14467.3 | 8878 | 2021-10-25 | 2021-12-05
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851349 — CTR सोखता गड्ढा 7 अर्जला | Closed | 14467.3 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851356 — CTR सोखता गड्ढा 8 अर्जला | Closed | 14467.3 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718001074/WC/22012034851361 — CTR सोखता गड्ढा 9 अर्जला | Closed | 14467.3 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1718001074/WC/22012034851367 — CTR सोखता गड्ढा 10 अर्जला | Closed | 14467.3 | 0 | 2021-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1718001074/WC/22012034920067 — रिचार्ज पौंड मगरा पर ग्राम अर्जला | Closed | 0 | 0 | 2022-01-26
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034923463 — तालाब जीर्णोधार कार्य ग्राम अर्जला ,44/188 | Deleted | 64000 | 0 | 2022-01-24
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034923465 — तालाब जीर्णोधार कार्य ग्राम अर्जला ,44/188 | Deleted | 0 | 0 | 2022-01-24
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034923466 — तालाब जीर्णोधार कार्य ग्राम अर्जला ,44/188 | Deleted | 0 | 0 | 2022-01-24
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001074/WC/22012034924906 — talab marmat arjala | Completed | 64000 | 47092 | 2022-03-13 | 2022-12-26
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1718001074/WC/22012034944820 — बग आउट पोंड निर्माण मगरे के पास ग्राम अर्जला | Deleted | 0 | 0 | 2022-04-08
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1718001074/WC/22012034944822 — बग आउट पोंड निर्माण मगरे के पास ग्राम अर्जला | Deleted | 0 | 0 | 2022-04-08
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034954684 — रिचार्ज पौंड राम सिंह के खेत के पास अर्जला | Deleted | 0 | 0 | 2022-04-14
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034954685 — रिचार्ज पौंड राम सिंह के खेत के पास अर्जला | Completed | 265781.03 | 199826 | 2022-05-09 | 2024-08-21
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718001074/WC/22012034954689 — रिचार्ज पौंड राम सिंह के खेत के पास अर्जला | Deleted | 0 | 0 | 2022-04-14
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718001074/WC/22012034954705 — नाला निर्माण कारू के खेत से कमल सिंह के खेत की ओर अर्जला | Closed | 0 | 0 | 2022-04-14
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1718001074/WC/22012035133576 — nala nirman jagdish ke khet se vakiya ki our | Ongoing | 193495.31 | 38575 | 2024-01-21
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718001074/WC/22012035133582 — nala nirman bhuwan ke khet se talab ki our | Completed | 202860.93 | 64077 | 2024-02-06 | 2026-04-05
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1718001074/WC/22012035133590 — nala nirman sajan singh ke khet se lal singh ke khet ki our | Closed | 198178.12 | 0 | 2023-10-02
KHACHAROD | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718001074/WC/VB/22012035331335 — Aaganwadi bhawan arjala Roof Top Rain Water Harvesting Structure for Community arjala | Ongoing | 30496.65 | 3000 | 2026-08-13