## Work List
Exported on: 2026-10-10 18:59:04
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: CHAMBALPADLAYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001080/AV/22012034373090 — Anganwadi Bhawan nirman Chambal padlya | Completed | 312000 | 310433.4 | 2018-05-22 | 2022-09-01
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001080/AV/22012034508133 — Aganwadi bhawan nirman | Completed | 180000 | 127552 | 2021-12-04 | 2025-12-28
KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718001080/AV/22012034619408 — kabrishtan nirman chambal padlya | Closed | 509922.49 | 0 | 2022-04-14
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655421 — sokata gadda saskiya partamik school handpam ke pas | Completed | 14600 | 6495.77 | 2015-08-21 | 2015-12-25
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655490 — sokhta gadda midil school ke pass | Deleted | 1460000000 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655491 — sokhta gadda nae abadi hedpamp ke pass | Deleted | 1460000000 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655494 — secdirasta choke par hed pamp ke pas | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655495 — sokhta gadda nae abadi aganvadi ke pas hed pamp | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655496 — secdi rasta chok par hed pamp | Deleted | 1460000000 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655497 — sokhta gadda nae abadi me kaluram ke gar ke pas | Deleted | 1460000000 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655498 — nayakheda raste par | Deleted | 1460000000 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655499 — nae abadi aanvadi ke pas hed pamp | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655500 — sokhta gadda sekdi rasta chok par hed pamp | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655501 — सोक्ता गड्डा निर्माण मा.वि.केपास हेंड्पम्प पर | Completed | 14600 | 6491.94 | 2015-10-16 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655502 — sokhta gadda nae abadi kaluram ke gar ke pass hedpamp par | Completed | 14600 | 6495.77 | 2015-10-09 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655503 — sokhta gadda nae abadi nale par | Completed | 14600 | 6498.72 | 2015-10-09 | 2015-12-25
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655504 — sokhta gadda sekdi rasta choke par hedpamp ke pass | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655505 — sokhta gadda sekdi rasta choke par hed pamp | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Drinking Water | Soak Pits / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718001080/DW/9993655623 — sokhta gadda sekdi rasta choke par hed pamp | Deleted | 0 | 0 | 2015-04-18
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655670 — Sokhta GaddhaSekdi Rasta Chowk handpamp ke pas | Completed | 14600 | 6471.94 | 2015-10-16 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655671 — Sokhta Gaddha Nai Aabadi Anganwadi Ke pass | Completed | 14600 | 6495.77 | 2015-10-09 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655672 — Sokhta Gaddha Nai Aabadi BajrangKheda par Handpump ke pass | Completed | 14600 | 6512.83 | 2015-10-09 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655673 — Sokhta Gaddha Nai aabadi Me Bajrang Kheda Par Handpump keDai Or | Completed | 14600 | 6480.7 | 2015-10-16 | 2015-12-25
KHACHAROD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/DW/9993655674 — Sokhta gaddha Naya Kheda Raste pr | Completed | 14600 | 6491.89 | 2015-10-16 | 2015-12-25
KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001080/IF/22012034354161 — व़क्षारोपण | Completed | 335000 | 43732 | 2017-06-22 | 2020-09-01
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001080/IF/22012034422704 — राधेश्‍याम मांगीलाल के खेत पर वृक्षारोपण | Deleted | 145000 | 0 | 2018-04-14
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001080/IF/22012034423098 — सेवाराम शंंकरलाल के खेत वृक्षारोपण | Completed | 145000 | 92474 | 2018-08-08 | 2021-10-01
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001080/IF/22012034423119 — शम्भु शंंकरलाल के खेत पर वृक्षारोपण | Completed | 145000 | 84244 | 2018-08-08 | 2021-11-15
KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001080/IF/22012034427995 — निजी खेत मे फलोधान राधंश्‍याम मांगीलाल | Completed | 145000 | 72572 | 2018-08-08 | 2022-03-28
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034592812 — Nandan falodhyan ramesh mangilal | Deleted | 41702 | 0 | 2020-04-14
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034592816 — Nandan falodhyan Gabbaji shankarlal | Deleted | 41702 | 0 | 2020-04-14
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034592823 — Nandan falodhyan jagdish mangilal | Deleted | 41702 | 0 | 2020-04-14
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034605765 — styanarayan ramprasad nandan falodhyan | Completed | 142545 | 82934 | 2021-09-02 | 2024-08-08
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034605943 — Ratanlal bheraji nandan falodhyan | Completed | 113357 | 78768 | 2020-09-17 | 2024-08-08
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718001080/IF/22012034605945 — Shankarlal manna nandan falodhyan | Completed | 113357 | 89964 | 2020-09-10 | 2024-08-08
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718001080/IF/22012035514389 — JGSA 2025 Khet Talab Nirman BAPU SINGH BHAVAR SINGH | Deleted | 0 | 0 | 2025-04-20
KHACHAROD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001080/IF/2चम्‍बलपाड — चम्‍बलपाडल्‍या नवीन कुप निर्माण निर्भयसिंह नरसिंह | Completed | 57292 | 109185 | 2009-01-27 | 2013-02-07
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/9993698005 — इंदिरा आवस निर्माण समपतबाई | Completed | 14310 | 12864 | 2016-01-08 | 2017-05-03
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/9993701686 — शायर बाई इंदिरा आवास | Completed | 14310 | 14170 | 2016-01-08 | 2017-02-02
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001080/IF/9993716822 — navin kup meharbansingh | Deleted | 0 | 0 | 2016-04-01
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001080/IF/9993717011 — ketal sed ramji ruga | Deleted | 0 | 0 | 2016-04-01
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001080/IF/9993717012 — ketal sed rajesh | Deleted | 0 | 0 | 2016-04-01
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718001080/IF/9993748109 — khet talab ranchod nandaji | Deleted | 0 | 0 | 2016-06-14
KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718001080/IF/9993748114 — khet talab ramesh nandaji | Deleted | 0 | 0 | 2016-04-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3922713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106917413 | Completed | 18360 | 18241 | 2022-07-16 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3928908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115102889 | Completed | 18360 | 18241 | 2022-07-16 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3928929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115113419 | Completed | 18360 | 18360 | 2022-07-17 | 2023-03-24
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3928938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115122129 | Completed | 18360 | 18360 | 2022-08-31 | 2023-03-24
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3929161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113489632 | Completed | 18360 | 18156 | 2022-08-02 | 2023-03-24
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3929174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113492394 | Completed | 18360 | 18360 | 2022-08-01 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3929217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113505919 | Completed | 18360 | 18020 | 2022-07-26 | 2023-06-19
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3934977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106725435 | Completed | 18360 | 18343 | 2022-09-08 | 2023-07-14
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3935685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114089621 | Completed | 18360 | 18249 | 2023-09-14 | 2024-10-08
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3940500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119854840 | Completed | 18360 | 18225 | 2024-10-14 | 2024-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3940519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119866155 | Completed | 18360 | 18360 | 2022-07-16 | 2023-06-19
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3940544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119876899 | Completed | 18360 | 18360 | 2022-08-10 | 2023-03-24
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3969460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115106259 | Completed | 18360 | 18360 | 2022-08-02 | 2023-06-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3972926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115878746 | Completed | 18360 | 18020 | 2022-07-29 | 2023-06-19
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/3990962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122452329 | Completed | 18360 | 18312 | 2024-10-21 | 2024-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4037048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106724421 | Completed | 18360 | 18020 | 2022-07-26 | 2023-06-19
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4041529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115879006 | Completed | 18360 | 18190 | 2022-08-02 | 2023-06-19
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4042903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116936578 | Completed | 18360 | 18360 | 2022-09-13 | 2023-09-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4064254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115733598 | Completed | 18360 | 17782 | 2022-07-26 | 2023-07-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4075358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119857068 | Completed | 18360 | 17969 | 2022-07-17 | 2023-07-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4188206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114052209 | Completed | 18360 | 17782 | 2022-07-17 | 2023-07-14
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4193283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115324410 | Completed | 18360 | 17748 | 2022-07-26 | 2023-04-20
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4326938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106490958 | Completed | 18360 | 18360 | 2022-08-26 | 2022-11-04
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4327343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115891388 | Completed | 18360 | 18224 | 2022-09-02 | 2023-12-22
KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4337539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106476926 | Completed | 18360 | 18360 | 2022-09-13 | 2023-06-19
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4396469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106945779 | Completed | 19890 | 18564 | 2023-07-13 | 2023-08-19
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4397198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115885379 | Completed | 19890 | 15552 | 2023-09-14 | 2025-02-20
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4397205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115893406 | Completed | 19890 | 18564 | 2023-07-13 | 2023-09-04
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4398186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116432736 | Completed | 19890 | 19669 | 2023-07-13 | 2023-08-19
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4398333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115109559 | Completed | 19890 | 19448 | 2023-07-13 | 2023-10-14
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4545211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106919457 | Completed | 23490 | 21870 | 2025-02-20 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4546382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106939934 | Completed | 21870 | 21627 | 2025-02-20 | 2025-04-01
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4548276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106721817 | Completed | 21870 | 21870 | 2025-02-24 | 2025-04-01
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4550071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106911721 | Completed | 23490 | 21960 | 2025-02-21 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4551824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113505099 | Completed | 23490 | 21870 | 2025-02-20 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4552484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114058403 | Completed | 23490 | 21888 | 2025-02-25 | 2025-10-14
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4553875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114098278 | Completed | 21870 | 21384 | 2024-11-26 | 2025-03-17
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4555161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114099640 | Completed | 21870 | 21870 | 2024-11-19 | 2025-03-17
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4560483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115097423 | Completed | 23490 | 21888 | 2025-02-24 | 2025-10-06
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4560575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115108510 | Completed | 23490 | 23490 | 2025-09-18 | 2025-10-14
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4567296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115876248 | Completed | 23490 | 21870 | 2025-02-19 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4567317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115877624 | Completed | 23490 | 22014 | 2025-02-19 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4568371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116914325 | Completed | 23490 | 21870 | 2025-02-19 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4574966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117284934 | Completed | 21870 | 20412 | 2024-11-11 | 2025-02-20
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4695787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115883645 | Completed | 23490 | 21870 | 2025-02-21 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4740504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106733708 | Completed | 23490 | 21960 | 2025-02-21 | 2025-10-06
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4741325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106939904 | Completed | 23490 | 21870 | 2025-02-20 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4747294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115715327 | Completed | 23490 | 22050 | 2025-03-11 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4751909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116301863 | Completed | 23490 | 21870 | 2025-02-21 | 2025-10-15
KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/4819220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106933223 | Completed | 23490 | 21870 | 2025-02-21 | 2025-10-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5311715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115380700 | Completed | 23490 | 23490 | 2025-04-15 | 2025-10-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5323822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115713486 | Completed | 23490 | 23490 | 2025-04-15 | 2025-10-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5324013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118286251 | Completed | 23490 | 23490 | 2025-04-15 | 2025-10-14
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5478092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116930838 | Completed | 23490 | 23490 | 2025-08-21 | 2025-10-09
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5479680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115324964 | Completed | 23490 | 22968 | 2025-04-24 | 2025-10-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5711466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115713426 | Completed | 23490 | 23490 | 2025-07-30 | 2025-10-15
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5746762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115116320 | Completed | 23490 | 23490 | 2025-08-20 | 2025-10-23
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5747949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106916629 | Completed | 23490 | 23490 | 2025-08-20 | 2025-10-09
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/5748677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106912689 | Completed | 23490 | 23490 | 2025-08-19 | 2025-10-09
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/92560 — Construction of IAY House -IAY REG. NO. MP-18-001-080-001/23 | Physically Completed | 14310 | 0 | 2016-01-14 | 2024-11-21
KHACHAROD | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001080/IF/IAY/92561 — Construction of IAY House -IAY REG. NO. MP-18-001-080-001/26 | Suspended | 14310 | 0 | 2021-11-06
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718001080/LD/22012034247513 — खेल मेदान | Completed | 200000 | 176516.63 | 2015-12-28 | 2018-06-13
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718001080/LD/22012034315252 — शांति धाम चम्बलपाडलिया | Deleted | 180000 | 0 | 2017-06-08
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001080/LD/22012034580361 — CPT &Land Development kabrishtan bhumi per GP Chambal padlya | Completed | 509922.49 | 385367 | 2022-11-21 | 2024-11-04
KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/20 — मनरेगा+पंच परमेश्‍वर सीसी व नाली निर्माण चम्‍बलपाउ | Completed | 130000 | 123681.32 | 2012-09-06 | 2015-05-20
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034188112 — मनरेगापचपरमेश्‍वर तिसारी किशत प्राथमीक विघालयसे | Completed | 23900 | 25656 | 2013-12-25 | 2016-07-03
KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034188115 — मनरेगा पचपरमेश्‍वर चोथी किशत मा०वि०देवा बागरी के घ | Completed | 83000 | 80456 | 2014-10-26 | 2015-05-20
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034198732 — मनरेगा+पंच परमेश्‍वर दिव्तीय किश्त | Deleted | 0 | 0 | 2013-04-18
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034198735 — मनरेगा+पंच परमेश्‍वर माध्यमिक विधालय से. | Deleted | 0 | 0 | 2013-04-18
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034198741 — मनरेगा पचपरमेश्‍वर दिव्तिय किशत | Completed | 124000 | 115982 | 2014-01-13 | 2016-05-18
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034199002 — मनरेगा+पंच परमेश्‍वर सीसी व नाली निर्माण दिव्‍तीय किशत | Deleted | 124488 | 0 | 2013-04-18
KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034200097 — अतरिकमार्ग मुरमीकरण | Completed | 500000 | 437545.36 | 2014-01-22 | 2015-10-25
KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034227406 — panchparmeswar +manrega deva bagri ke har se runch | Completed | 83000 | 74647 | 2014-10-26 | 2015-07-25
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034265358 — समशान सेट एव समतलिकरण | Completed | 378000 | 377346.9 | 2015-11-27 | 2017-09-05
KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034265359 — सूदूर सदक महादेव मंदीर से महेन्द्रसिह के खेत की ओर | Deleted | 0 | 0 | 2014-10-02
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034287995 — मनरेगा+पंचपरमेश्वर(सिमेंट कान्करिट व नाली निर्माण) | Completed | 96000 | 95958 | 2015-11-06 | 2016-05-11
KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034295590 — मनरेगा+पंचपरमेश्वर(सिमेंट कान्करिट व नाली निर्माण) | Completed | 91358 | 91140 | 2016-01-22 | 2016-05-11
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034302234 — मनरेगा पंचपरमेश्‍वरनरबेसिह के घर से रमेशलाल के घर की ओर | Completed | 123352 | 123281 | 2016-08-18 | 2016-09-29
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034302235 — मनरेगा+परफारमेंस ग्राट सिमेंट कांकीट निर्माण कार्य | Completed | 49000 | 48725 | 2016-09-15 | 2016-11-03
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034328214 — सुदुर सड्क | Completed | 1073000 | 1046781.22 | 2017-02-23 | 2018-07-27
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034335560 — रतनसिंंह के घर से कालु महाराज के घर तक सि सि व नाली निर्माण | Completed | 30975 | 30276 | 2019-02-09 | 2019-12-17
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034343061 — sudur sampark shadak | Completed | 1418000 | 1391070.27 | 2017-06-30 | 2021-03-30
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034348922 — सिमेंट कांक्रीट सुखराम के घर से रतन के घर तक अजा बस्ती | Completed | 66375 | 66220 | 2017-08-14 | 2017-09-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034348924 — सिमेंट कान्क्रीट रणछोड के घर से रतन के घर तक अजा बस्ती | Completed | 12713 | 9288 | 2018-02-13 | 2018-06-28
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034348928 — रमेश के घर से राजेश अजा के घर तक अजा बस्ती | Deleted | 40455 | 0 | 2017-04-20
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034348932 — रमेश के घर से कमल अजा के घर तक अजा बस्ती | Completed | 23895 | 23736 | 2017-09-11 | 2017-09-22
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034348935 — शंकरलाल के घर गंगाराम के घर तक | Completed | 16200 | 16340 | 2017-08-25 | 2017-09-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034350789 — पूनाजी के घर से मदन के घर तक सि सि व नाली निर्माण | Completed | 10440 | 10320 | 2017-08-25 | 2017-09-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034350791 — भंवरलाल के घर से रशमबाई के घर तक सि सि व नाली निर्माण | Completed | 24337 | 24252 | 2017-08-25 | 2017-09-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034350792 — अंबाराम के घर से रुघनाथ के घर तक सि सि व नाली निर्माण | Completed | 28087 | 28036 | 2017-08-25 | 2017-09-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034350793 — रुघनाथसिंह के घर से भादरसिंह के घर तक सि सि व नाली निर्माण | Completed | 34909 | 35088 | 2017-08-25 | 2017-09-22
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034353344 — मेहबुब के घर के पास चोक सि सि व नाली निर्माण | Completed | 74475 | 73960 | 2017-09-21 | 2018-06-28
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034373952 — तीन बत्ती रोड से शुरु होकर जशवंंतसिंंह के घर कि ओर सि सि व नाली निर्माण | Completed | 39825 | 39324 | 2019-02-01 | 2019-04-10
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034383594 — मदन के घर से भेरुलाल के घर तक सिमेंट कांक्रीट रोड नालि निर्मान | Completed | 12443 | 12384 | 2018-02-13 | 2018-06-28
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034383599 — रुगनाथ के घर से गोपालनाथ के घर तक सिमेंट कांक्रीट रोड नालि निर्माण | Completed | 25110 | 20640 | 2018-02-13 | 2018-06-28
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034383602 — भगवानसिंह के घर से रुगनाथ सिह के घर तक सिमेंट कांक्रीट रोड | Completed | 6630 | 6192 | 2018-02-13 | 2018-07-04
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034441628 — Cc road | Deleted | 0 | 0 | 2019-01-26
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034462551 — ईशवरसिंह के घर से मनोहरलाल शर्मा के घर तक सी और नाली निर्माण | Completed | 23512 | 23490 | 2019-03-11 | 2019-12-19
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034462553 — प्रधानमन्त्री सड़क से भंवरलाल के घर तक सी और नाली निर्माण | Completed | 44917 | 44880 | 2019-03-12 | 2019-12-17
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034462554 — रईश के घर से वलीमोहमद के घर तक सी और नली निर्मा | Completed | 8370 | 15840 | 2019-03-10 | 2019-12-17
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034475262 — प्रधानमंत्री रोड से सुरेश के घर तक सी सी व नाली निर्माण | Completed | 34875 | 34848 | 2019-09-19 | 2022-02-01
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034479646 — जगदीश के घर से लालजी चोधरी के घर तक सी सी व नाली निर्माण | Completed | 27900 | 27836 | 2019-10-12 | 2020-06-17
KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034513860 — मरम्मत सी सी रोड | Deleted | 0 | 0 | 2019-01-26
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001080/RC/22012034526382 — sudur gram sampark tin batti fatak railway station se barkheda kakad or nirbhaysingh ki or | Completed | 1489857.3 | 1445511.01 | 2020-07-27 | 2022-11-03
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034530500 — महेंद्रसिंह के घर से बजरंगबली चबूतरे की और सी सी निर्माण | Completed | 42075 | 41990 | 2020-07-18 | 2020-11-03
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034530501 — ईजीएस स्कूल से दिनेश के घर तक सी सी निर्माण | Completed | 43350 | 43320 | 2020-08-12 | 2020-09-17
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034534539 — Ramesh ke ghar se rajesh ke ghar tak c c nirman | Completed | 30600 | 30590 | 2020-08-19 | 2020-09-22
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034554666 — c c road nirman mataji chok ke pass | Completed | 11000 | 10640 | 2021-01-09 | 2021-10-23
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034564882 — C C road or nali nirman javalamukhi mataji ke pass | Completed | 45452 | 44969 | 2021-11-16 | 2022-08-25
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034660287 — c c road nirman radheshyam mangilal ke ghar se suresh mangilal ke ghar ki or chambal padlya | Completed | 56407 | 56134 | 2023-10-04 | 2024-04-12
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034820557 — c c road nirman shuresingh ke ghar se mehbub kha ke ghar tak | Completed | 17826 | 16281 | 2024-11-04 | 2025-01-08
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034820559 — c c road nirman shuresingh ke ghar se mehbub kha ke ghar tak chambalpadlya | Completed | 11899 | 11898 | 2024-10-21 | 2025-01-08
KHACHAROD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034843671 — c c road nirman kamlabai ke ghar se sumersingh ke ghar ki or chambal padlya | Completed | 65968 | 65772 | 2025-06-06 | 2025-12-25
KHACHAROD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001080/RC/22012034843673 — c c road nirman kailash ke ghar se jitendra ke ghar ki or chambal padlya | Completed | 68368 | 67860 | 2025-06-23 | 2025-12-25
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | School Toilet Units / Construction of Multi Unit Toilets for School | Construction of Toilets | 1718001080/RS/22012034307219 — Shochalay Nirman 33 Unit 2200wale Chambal Padlya | Deleted | 323400 | 0 | 2016-11-21
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034309577 — शौचालय निर्माण मोहन गणपत ओर किशन बाबरु 2200 वाले | Completed | 19600 | 16342 | 2016-12-08 | 2017-07-26
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319514 — bhagwan singh / dulesingh toilate | Completed | 9800 | 9671 | 2017-01-22 | 2017-06-15
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319515 — lalsingh/ ramsingh toilate | Completed | 9800 | 9504 | 2017-03-21 | 2017-07-26
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319542 — vilam kunwar / nahar singh toilate | Completed | 9800 | 9671 | 2017-01-22 | 2018-07-01
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319544 — rukhma bai / asharam | Completed | 9800 | 9671 | 2017-01-22 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319546 — radheshyam / hemraj toilate | Completed | 9800 | 9671 | 2017-01-31 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319600 — jagdish / mangilal tolilate | Completed | 9800 | 9671 | 2017-01-22 | 2017-06-30
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319605 — shravan / banesingh toilate | Completed | 9800 | 9671 | 2017-03-12 | 2017-06-15
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319607 — champalal / nanuram toilate | Completed | 9800 | 9671 | 2017-01-31 | 2017-06-15
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319608 — gopaldas / kachru | Completed | 9800 | 9671 | 2017-01-22 | 2017-07-26
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319609 — dhansingh / ramsingh toilate | Completed | 9800 | 9671 | 2017-01-31 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319611 — ambaram / babru toilate | Deleted | 9800 | 0 | 2017-01-22
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319612 — rama / babaru toilate | Completed | 9800 | 9671 | 2017-01-22 | 2017-06-15
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319613 — rama ji / laxman ji toilate | Deleted | 9800 | 0 | 2017-08-04
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034319616 — ramesh / varda ji toilate | Completed | 9800 | 9838 | 2017-01-22 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321760 — dhapubai/mangilal sochalay | Completed | 9800 | 9671 | 2017-03-09 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321763 — sampatbai/baluji sochalay | Completed | 9800 | 9671 | 2017-03-05 | 2018-07-01
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718001080/RS/22012034321767 — Kaniram ji / Motiji toilate | Completed | 9800 | 9736 | 2017-05-18 | 2018-07-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321769 — Lila Bai /jaluji shochalay | Deleted | 9800 | 0 | 2017-01-31
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321771 — jagnath/shankerlal sochalay | Completed | 9800 | 9671 | 2017-03-12 | 2017-06-15
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321772 — Mangilal/hemraj sochalay | Completed | 9800 | 9671 | 2017-03-12 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321774 — lalji/hinduji sochalay | Deleted | 12000 | 0 | 2017-01-30
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321775 — punaji/bhagratji sochalay | Completed | 9800 | 2171 | 2017-01-31 | 2018-06-25
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718001080/RS/22012034321925 — Ratan /shobaram sochalay | Deleted | 9800 | 0 | 2017-08-04
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321926 — nathibai/heralal sochalay | Completed | 9800 | 9671 | 2017-02-04 | 2017-07-26
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321930 — ramesh/shankerlal sochalay | Completed | 9800 | 9671 | 2017-03-14 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034321931 — prahlad/ambaram sochalay | Completed | 9800 | 9671 | 2017-02-01 | 2017-06-09
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034329848 — lalsingh vikramsingh sochalay nirman | Completed | 9800 | 9671 | 2017-03-12 | 2017-07-26
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034329850 — Ramsingh Nandaji Sochalay Nirman | Completed | 9800 | 9671 | 2017-03-12 | 2017-06-15
KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034329853 — Gangaram nanuram Sochalay Nirman | Completed | 9800 | 9671 | 2017-03-12 | 2018-07-01
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034363259 — जीवन पिता गणपत शोचालय | Deleted | 12000 | 0 | 2017-08-04
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034363269 — संगीताबाई सेवाराम शोचालय | Deleted | 12000 | 0 | 2017-08-04
KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001080/RS/22012034363276 — भेरुलाल बगदिराम शोचालय | Deleted | 12000 | 0 | 2017-08-04
KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012034504594 — Nali nirman chambal padlya | Completed | 45000 | 44460 | 2021-01-17 | 2021-10-23
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012034512430 — Nali nirman ramchandra ke ghar se chabutara ki or | Completed | 33877 | 33859 | 2021-12-04 | 2022-04-21
KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718001080/RS/22012034607292 — Samudayik sawchhata parisar nirman chambal padlya | Completed | 88000 | 49765 | 2021-12-04 | 2024-02-09
KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012034632565 — Nali nirman mehbub ke ghar se ganesh chabutare ki or | Completed | 24196 | 24072 | 2022-11-04 | 2022-12-03
KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012034681195 — Nali nirman rajaram ke ghar se hanuman ji ke chabutare ki or | Completed | 27000 | 26928 | 2022-12-27 | 2023-07-15
KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012035114741 — Nali nirman bapu ramchandra ke ghar se nadi ki or chambal padlya | Completed | 59663 | 59449 | 2023-10-04 | 2024-04-12
KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012035128492 — Nali nirman kadar kha ke ghar se ramsingh choudhary ke ghar tak | Completed | 58734 | 58734 | 2024-10-07 | 2025-01-01
KHACHAROD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001080/RS/22012035137815 — Nali nirman kamlabai ke ghar se sumersingh ke ghar ki or chambal padlya | Completed | 42660 | 42543 | 2025-06-12 | 2025-12-25
KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034446993 — नाला ट्रेचिंग व चेक डेम निर्माण रामा हेमा के खेत से पास | Deleted | 876000 | 0 | 2019-01-26
KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034446999 — नाला ट्रेचिंग व चेक डेम निर्माण गोपालसिंह के खेत के पास | Deleted | 876000 | 0 | 2019-01-26
KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034447184 — नाला ट्रेचिंग व चेक डेम निर्माण दशरथ चोधरी के खेत के पास | Deleted | 876000 | 0 | 2019-01-26
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034530463 — नाला ट्रेचिंग व चेक डेम निर्माण गोपालसिंह के खेत के पास | Completed | 581258.95 | 569070 | 2020-04-30 | 2021-05-24
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718001080/WC/22012034581838 — Recharge pond chambal padlya | Completed | 332572.21 | 265620 | 2020-09-30 | 2021-05-24
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034586096 — Nala traching ganpat nagu ke khet ke pass | Deleted | 0 | 0 | 2020-08-15
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034586097 — Nala traching rama ke khet ke pass | Deleted | 0 | 0 | 2020-08-15
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718001080/WC/22012034586098 — Recharge pond mangu bagdiram ke khet ke pass | Completed | 332572.21 | 265620 | 2020-10-28 | 2021-05-24
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034586293 — Check dem or nala traching nirman antersingh ke khet ke pass | Completed | 1172420.39 | 1150400 | 2020-12-08 | 2022-11-03
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034586294 — Check dem or nala traching nirman rama hema ke khet ke pass | Completed | 1338831.28 | 1290376 | 2021-03-12 | 2022-11-03
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034598904 — Nala traching virendrasingh ke khet ke pass gram chambal padlya gram panchayat chambal padlya | Completed | 370669 | 282040 | 2021-02-25 | 2022-08-25
KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034620640 — Check dem or nala traching nirman pratapsingh jujharsingh ke khet ke pass G P chambal padlya | Completed | 1351836.57 | 1289578.5 | 2021-03-10 | 2021-10-23
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001080/WC/22012034678317 — Check dem or nala traching munnalal ke khet ke pass Chambalpadlya G P Chambal padlya | Deleted | 0 | 0 | 2021-04-14
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034678386 — Nala traching munnalal ke khet ke pass chambalpadlya G P Chambal padlya | Completed | 559510.85 | 321096 | 2022-04-19 | 2022-08-10
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034745473 — Sokta gadda gabbaji ke ghar ke pass handpamp chambal padlya G P chambal padlya | Completed | 81942.49 | 53946 | 2021-09-19 | 2022-12-20
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034745478 — Sokta gadda virendrasingh ke ghar ke pass handpamp chambal padlya G P chambal padlya | Completed | 14467.3 | 10422 | 2021-10-23 | 2022-01-28
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034745483 — Sokta gadda sewaram ke ghar ke pass handpamp chambal padlya G P chambal padlya | Completed | 14467.3 | 10422 | 2021-11-23 | 2022-01-19
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034745487 — Sokta gadda p s ke ghar ke pass handpamp chambal padlya G P chambal padlya | Completed | 14467.3 | 10422 | 2021-10-16 | 2022-01-28
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034745489 — Sokta gadda M S ke ghar ke pass handpamp chambal padlya G P chambal padlya | Completed | 14467.3 | 10422 | 2021-10-16 | 2022-01-28
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718001080/WC/22012034745497 — Water harwesting panchayat bhawan chambal padlya G P chambal padlya | Closed | 22229.14 | 0 | 2021-10-06
KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718001080/WC/22012034745502 — Water harwesting p s bhawan chambal padlya G P chambal padlya | Completed | 22229.14 | 11177.88 | 2025-02-12 | 2025-04-10
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718001080/WC/22012034787915 — सोख़्ता गड्डा | Completed | 14467.3 | 10387 | 2023-07-12 | 2023-10-02
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034830235 — CTR Sokta Gadda Gnaesh chabutara ke pass chambal padlya | Completed | 14467.3 | 10422 | 2021-09-25 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034830240 — CTR Sokta Gadda anganwadi bhawan ke pass chambal padlya | Completed | 14467.3 | 10422 | 2021-09-26 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034830243 — CTR Sokta Gadda ratan ke ghar ke pass chambal padlya | Completed | 14467.3 | 10422 | 2021-09-25 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034830252 — CTR Sokta Gadda mahendrasingh ke ghar ke pass chambal padlya | Completed | 14467.3 | 10422 | 2021-09-25 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851095 — CTR Sokta gadda EGS School ke paas | Completed | 14467.3 | 10422 | 2021-10-16 | 2022-01-19
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851099 — CTR Sokta gadda kachru ji ke ghar ke paas | Completed | 14467.3 | 10422 | 2021-10-18 | 2022-01-19
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851106 — CTR Sokta gadda dinesh ke ghar ke paas chambalpadlay | Completed | 14467.3 | 10422 | 2021-10-17 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851121 — CTR Sokta gadda naya kheda lalji choudhry ke ghar ke paas chambalpadlay | Completed | 14467.3 | 10422 | 2021-10-16 | 2022-01-19
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851125 — CTR Sokta gadda prahalad ke ghar ke paas chambalpadlay | Completed | 14467.3 | 10422 | 2021-10-23 | 2022-01-17
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001080/WC/22012034851129 — CTR Sokta gadda gangaram ke ghar ke paas chambalpadlay | Completed | 14467.3 | 10422 | 2021-10-23 | 2022-01-19
KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034902843 — Nala traching Manoharsingh ke khet ke pass Chambal padlya | Closed | 0 | 0 | 2021-10-02
KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012034902848 — Nala traching Rajendrasingh ke khet ke pass Chambal padlya | Completed | 496263.5 | 320405.7 | 2024-07-05 | 2025-05-02
KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001080/WC/22012034924636 — Talab pal marammat karya chambal padlya | Completed | 47000 | 46512 | 2022-06-04 | 2023-02-10
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001080/WC/22012034924639 — Talab pal marammat karya ramesh mangilal ke khet ke pass chambal padlya | Completed | 22000 | 21658 | 2023-06-28 | 2023-07-15
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1718001080/WC/22012035131828 — Nala tranching ganpat nanuram ke khet ke pass chambal padlya | Completed | 268586.26 | 220781 | 2023-10-05 | 2024-07-05
KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001080/WC/22012035225352 — Dug pond mangilal ke khet ke pass chambal padlya | Approved | 0 | 0 | 2024-10-02
KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001080/WC/22012035247900 — Recharge pond nirman ramesh nanda ke khet ke pass chambal padlya | Ongoing | 1344831.58 | 743328 | 2025-12-01
KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034595245 — मनरेगा निजी खेत मे फलौधान श्री गब्बाजी पिता शंकरलाल ग्राम चम्बल पाड्ल्या | Completed | 144170 | 97634.5 | 2020-09-10 | 2026-03-01
KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034595247 — मनरेगा निजी खेत मे फलौधान श्री रमेश पिता मांगीलाल ग्राम चम्बल पाड्ल्या | Completed | 144170 | 65976 | 2020-09-10 | 2025-06-26