## Work List
Exported on: 2026-10-27 03:36:37
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: DHOOMAHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718001092/AV/22012034505384 — shantidham nirman | Ongoing | 192447.09 | 0 | 2020-01-24
KHACHAROD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1718001092/DP/22012034610611 — Poshan vatika dhoomaheda | Ongoing | 898945.24 | 0 | 2023-10-06
KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718001092/IF/22012034656530 — Kup nirman Akbarkha allnurkha Dhoomaheda G P Dhoomaheda | Ongoing | 246126.86 | 0 | 2021-02-19
KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718001092/IF/22012035091802 — Dayaram gopal navin kup niraman gram dhoomaheda | Ongoing | 282417.57 | 2640 | 2024-03-16
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718001092/IF/22012035287387 — Kapil dhara kup nirman saitanbai fattaji dhoomaheda | Ongoing | 312155.12 | 0 | 2025-04-17
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718001092/IF/22012035287389 — Kapil dhara kup nirman kamlabai baluram dhoomaheda | Ongoing | 312155.12 | 0 | 2025-04-17
KHACHAROD | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/3317897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5528834 | Approved | 27000 | 0 | 2021-11-02
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39188 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/17 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39190 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/29 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39191 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/4 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39192 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/54 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39194 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/60 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/39195 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/70 | Approved | 27000 | 0 | 2015-11-20
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/5710947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125310313 | Approved | 27000 | 0 | 2025-05-26
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/5921098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118821921 | Completed | 23490 | 0 | 2026-03-23 | 2026-08-06
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6102868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129569185 | Ongoing | 27000 | 0 | 2026-04-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6102962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126463104 | Physically Completed | 27000 | 18900 | 2026-05-08 | 2026-10-13
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6104519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123574002 | Completed | 27000 | 15600 | 2026-04-20 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6105294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125315706 | Completed | 23490 | 9600 | 2026-04-20 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6106359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117479456 | Ongoing | 27000 | 0 | 2026-04-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6108680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118566730 | Physically Completed | 23490 | 5700 | 2026-04-20 | 2026-07-29
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6108777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118491911 | Completed | 23490 | 8400 | 2026-04-26 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6108778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118492253 | Ongoing | 27000 | 0 | 2026-04-20
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6108779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118492596 | Completed | 23490 | 11400 | 2026-04-20 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6110614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567407 | Completed | 27000 | 19800 | 2026-06-02 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6112793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129569736 | Ongoing | 27000 | 20700 | 2026-05-12
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6112926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124218783 | Completed | 23490 | 0 | 2026-04-20 | 2026-07-21
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6113127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124466972 | Physically Completed | 27000 | 15600 | 2026-05-12 | 2026-09-06
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6113172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118492661 | Completed | 27000 | 21300 | 2026-04-26 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6113173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118492736 | Completed | 27000 | 21864 | 2026-04-26 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6113410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567278 | Ongoing | 27000 | 12000 | 2026-04-20
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6114307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124217696 | Completed | 23490 | 12000 | 2026-04-16 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6114561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567054 | Completed | 27000 | 13500 | 2026-04-20 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6114961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124799013 | Completed | 27000 | 18300 | 2026-05-12 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6114987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124219797 | Completed | 27000 | 16500 | 2026-05-12 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6115044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124128645 | Completed | 27000 | 17400 | 2026-05-12 | 2026-10-07
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6115181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124218243 | Ongoing | 27000 | 6600 | 2026-04-20
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6115526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125311454 | Completed | 23490 | 0 | 2026-04-20 | 2026-07-16
KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6244122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123575027 | Ongoing | 27000 | 18027 | 2026-07-20
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6325099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118491855 | Approved | 27000 | 0 | 2026-01-28
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6325116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130520386 | Approved | 27000 | 0 | 2026-02-24
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6325212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125310718 | Approved | 27000 | 0 | 2026-02-21
KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/6421658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118492000 | Approved | 27000 | 0 | 2026-02-26
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/93559 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/019 | Approved | 27000 | 0 | 2015-09-21
KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718001092/IF/IAY/93560 — Construction of IAY House -IAY REG. NO. MP-18-001-092-001/22 | Approved | 27000 | 0 | 2015-09-21
KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718001092/WC/22012035241068 — Recharge pond nirman saskiya talab ke pass dhoomaheda | Approved | 485996.22 | 0 | 2024-12-05
KHACHAROD | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718001092/WC/VB/YD/22012035337339 — Aangnwadi bhawan Roof Top Rain Water Harvesting Structure for Community dhoomaheda | Approved | 30496.65 | 0 | 2026-10-03