## Work List
Exported on: 2026-10-28 14:41:06
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: BRAHMANKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MAHIDPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1718002001/DP/22012034615745 — NIRMAL NEER NIRMAN NAI AABADI BRAHMANKHEDA | Ongoing | 648891.55 | 42185 | 2024-03-17
MAHIDPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035170061 — KUP NIRMAN SHRAVANLAL RATANLAL | Ongoing | 284323.71 | 0 | 2025-01-16
MAHIDPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035206302 — Kup nirman Padam bai Govind | Physically Completed | 282417.57 | 0 | 2024-03-17 | 2026-08-10
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035240094 — Kup Nirman Shambhulal Lalu ji | Ongoing | 284789.42 | 0 | 2025-04-06
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035417932 — JGSA 2025 Kup Nirman Pirulal Jujhar ji | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035418071 — JGSA 2025 Kup Nirman Dilipsingh Lal Singh | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035418236 — JGSA 2025 Kup Nirman Bhanvar singh Rodsingh | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035418446 — JGSA 2025 Kup Nirman Prem kunvar vagtavarsingh | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718002001/IF/22012035510223 — JGSA 2025 FORM POND gokul ganpat ji | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718002001/IF/22012035525024 — JGSA 2025 Farm Pond Nirman tufan Singh pita Rugnath Singh | Approved | 147621.16 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718002001/IF/22012035540019 — JGSA 2025 KUP NIRMAN BHAGIRATH PUNA JI | Approved | 0 | 0 | 2025-04-14
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718002001/IF/22012035626077 — EK BAGIYA MAA KE NAAM SANGEETA BAI WO TEJ KUMAR BHUMI TEJ KUMAR GABBULAL BRAHMANKHEDA | Approved | 184292.72 | 0 | 2025-08-15
MAHIDPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/2284743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4302345 | Approved | 27000 | 0 | 2019-07-24
MAHIDPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/4408767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145190660 | Ongoing | 27000 | 0 | 2024-02-20
MAHIDPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/4629358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128479121 | Completed | 27000 | 1500 | 2024-10-19 | 2026-09-23
MAHIDPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/4695328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116791863 | Completed | 27000 | 0 | 2024-10-05 | 2026-09-23
MAHIDPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/4705414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122442776 | Completed | 27000 | 7500 | 2025-01-12 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5149137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117508341 | Completed | 27000 | 5200 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5149659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119880806 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5153144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145716639 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5160700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478596 | Ongoing | 27000 | 0 | 2025-05-04
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5165538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923783 | Completed | 27000 | 5200 | 2025-05-02 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5168021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145190857 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5169434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117922620 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5181148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145720270 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5199343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116791996 | Ongoing | 27000 | 2700 | 2025-05-04
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5228010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478878 | Completed | 27000 | 5200 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5235069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923968 | Completed | 27000 | 1500 | 2025-06-20 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5241192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116793619 | Completed | 27000 | 1500 | 2025-04-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5431087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128498204 | Ongoing | 27000 | 5400 | 2025-07-31
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5455061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478421 | Ongoing | 27000 | 0 | 2025-04-22
MAHIDPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5688664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145137321 | Ongoing | 27000 | 8400 | 2026-09-12
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5735575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117330621 | Ongoing | 27000 | 0 | 2026-01-11
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5735976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116791919 | Ongoing | 27000 | 0 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5735978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116793689 | Ongoing | 27000 | 8400 | 2026-02-04
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146892341 | Completed | 27000 | 1500 | 2025-08-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478434 | Ongoing | 27000 | 1500 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478470 | Completed | 27000 | 1500 | 2025-08-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478485 | Completed | 23490 | 0 | 2026-02-26 | 2026-08-20
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478600 | Completed | 23490 | 0 | 2025-09-27 | 2026-07-22
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145716310 | Ongoing | 27000 | 0 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5736829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145741299 | Completed | 27000 | 5200 | 2025-09-27 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5737064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122444723 | Ongoing | 27000 | 5400 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5737233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117922526 | Ongoing | 27000 | 0 | 2026-01-11
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128498625 | Ongoing | 27000 | 5400 | 2025-09-07
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128498657 | Ongoing | 27000 | 0 | 2025-11-01
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478366 | Ongoing | 27000 | 5700 | 2025-08-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122442384 | Completed | 27000 | 0 | 2025-08-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478631 | Ongoing | 27000 | 0 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478826 | Ongoing | 27000 | 0 | 2025-09-07
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145715630 | Ongoing | 27000 | 5700 | 2025-09-07
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5738999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145715659 | Ongoing | 27000 | 5700 | 2025-09-07
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5739514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117923209 | Ongoing | 27000 | 4450 | 2025-08-22
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5739888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118196552 | Ongoing | 27000 | 0 | 2026-02-25
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5740270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117508318 | Completed | 27000 | 1500 | 2025-08-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5740588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117508130 | Ongoing | 27000 | 9400 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5741403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126806743 | Completed | 27000 | 1500 | 2025-08-23 | 2026-09-23
MAHIDPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5741591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117922780 | Ongoing | 27000 | 2700 | 2026-05-02
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5742076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116527960 | Completed | 27000 | 1500 | 2025-08-22 | 2026-09-23
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/5804022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128478526 | Ongoing | 27000 | 0 | 2025-09-27
MAHIDPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718002001/IF/IAY/6299976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116792788 | Approved | 27000 | 0 | 2025-09-10
MAHIDPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1718002001/RC/22012034820367 — SUDUR SAMPARK SADAK NIRMAN BRAHMANKHEDA SE Kanthariya MARG TAK | Approved | 0 | 0 | 2024-06-08
MAHIDPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1718002001/RC/22012034821870 — RCC Nali Nirman Girdhari ke ghar se pratikshala bhavan tak | Approved | 33000 | 0 | 2024-06-08
MAHIDPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1718002001/RS/22012034680401 — SBM SAMUDAIK SWACHATA PARISAR BRAHMANKHEDA | Ongoing | 47000 | 0 | 2023-05-09
MAHIDPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1718002001/WC/22012035082795 — CTR RICHARG POND NIRMAN HANUMAN MANDIR KE PAS | Ongoing | 304586.87 | 0 | 2023-07-15
MAHIDPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718002001/WC/22012035212936 — ctr Richarg pond sita bai ke khet ke pas | Approved | 0 | 0 | 2024-06-08
MAHIDPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718002001/WC/22012035212940 — ctr richarg pond Rakesh ke khet pas | Approved | 0 | 0 | 2024-06-08
MAHIDPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1718002001/WC/22012035212944 — CTR Chek Dhem Nirman kailash ke khet ke pas | Approved | 0 | 0 | 2024-06-08
MAHIDPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1718002001/WC/22012035226647 — Percolation Tank Naran ke khet ke pas | Approved | 0 | 0 | 2024-10-02
MAHIDPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718002001/WC/22012035261655 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN SAMUDAYIK KUP NAI AABADI | Approved | 0 | 0 | 2025-04-07
MAHIDPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718002001/WC/VB/22012035336790 — Roof Top Rain Water Harvesting Samudayik Bhavan me | Approved | 0 | 0 | 2026-10-02