## Work List
Exported on: 2026-10-11 10:29:29
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: LIMBODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TARANA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1718004071/AV/22012034583517 — DINING TABEL P SCHOOL GRAM LIMBODA | Completed | 16093.32 | 2316 | 2021-09-13 | 2022-10-22
TARANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1718004071/AV/22012034649433 — PULIYA NIRMAN (15 VITYA) SHASKIYA KUP KE PAS LIMBODA | Completed | 24000 | 23426 | 2023-10-08 | 2024-03-28
TARANA | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718004071/AV/2723 — Anganwadi Sewa Kendra,TARANA | Deleted | 0 | 0 | 2015-01-26
TARANA | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718004071/AV/2725 — Anganwadi Sewa Kendra,TARANA | Deleted | 0 | 0 | 2015-01-26
TARANA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718004071/AV/3766 — Aanganbadi/Other Rural Infrastructure,TARANA | Completed | 195000 | 193414 | 2015-10-01 | 2018-07-20
TARANA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718004071/AV/3767 — Aanganbadi/Other Rural Infrastructure,TARANA | Completed | 195000 | 194313 | 2015-10-01 | 2018-07-20
TARANA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1000067305 — कपिलधारा कूप निर्माण सजनबाई भवरलाल लिम्बोदा | Completed | 271000 | 231751.2 | 2014-02-06 | 2016-06-21
TARANA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1000067309 — कपिलधारा कूप निर्माण कैलाशबाई मदनसिंह लिम्बोदा | Completed | 271000 | 248409.2 | 2014-01-30 | 2016-06-21
TARANA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1000067312 — कपिलधारा कूप निर्माण गुड्डीबाई प्रकाश लिम्बोदा | Completed | 271000 | 212921.5 | 2014-01-30 | 2016-06-21
TARANA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/164 — नवीन कुप निर्माण रेशमबाइ / भेरुलाल [ लिम्बोदा] | Completed | 257000 | 241219.77 | 2012-06-07 | 2015-05-20
TARANA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/165 — नवीन कुप निर्माण इश्वरसिह / रामसिह [ लिम्बोदा] | Completed | 257000 | 254622.2 | 2012-06-10 | 2014-12-09
TARANA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/166 — नवीन कुप निर्माण जोजनसिह / दुलेसिह [ लिम्बोदा] | Completed | 257000 | 238986.9 | 2012-06-07 | 2015-05-20
TARANA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/167 — नवीन कुप निर्माण कोदुलाल / सिध्दुलाल [ लिम्बोदा] | Completed | 257000 | 233986.9 | 2012-06-07 | 2014-12-09
TARANA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1 कुप निर् — कुप निर्मान मेर्बान S/o देवगीर जी | Completed | 150000 | 53160 | 2009-05-15 | 2009-04-21
TARANA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1 नवीन कुप — नवीन कुप निमार्ण विक्रम प्रहलाद लिम्‍बोदा | Completed | 161400 | 82285 | 2009-05-25 | 2013-12-20
TARANA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/1नवीन कुप — नवीन कुप निर्माण कैलाश / बापु जी { लिम्बोदा } | Completed | 64120 | 132877 | 2008-09-29 | 2008-02-26
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/22012034305006 — CM AAWAS RAJARAM GHEESHA | Completed | 15030 | 14948 | 2016-12-15 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718004071/IF/22012034350433 — वृक्षारोपण आगन वाड़ी भवन व प्रा वी नविन लिम्बोदा | Completed | 335000 | 15436 | 2017-07-06 | 2019-01-09
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718004071/IF/22012034350434 — वृक्षारोपण हनुमान मंदिर लिम्बोदा | Completed | 335000 | 188372 | 2017-07-06 | 2022-11-02
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718004071/IF/22012034350438 — वृक्षारोपण नेनावद लिम्बोदा रोड से यशवंत नगर गाव तक यशवंत नगर | Completed | 335000 | 20488 | 2017-07-13 | 2019-01-09
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1718004071/IF/22012034429146 — खेत की मेड पर वरक्षारोपन लिम्बोदा कैलाश बापू | Completed | 187600 | 119382 | 2018-08-10 | 2022-10-10
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718004071/IF/22012034477478 — khet talab | Deleted | 0 | 0 | 2019-01-26
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718004071/IF/22012034477479 — khet talab | Deleted | 0 | 0 | 2019-01-26
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034477480 — kapildhara kup nirman | Deleted | 0 | 0 | 2019-01-26
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034524141 — कपिलधारा कूप निर्माण सीताराम अमर सिंह लिम्बोदा | Completed | 234458.57 | 232260 | 2020-04-30 | 2021-09-22
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034524142 — कपिलधारा कूप निर्माण गेंदा लाल घीशा लिम्बोदा | Completed | 234458.57 | 232386 | 2020-05-02 | 2021-09-22
TARANA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034534679 — कपिलधारा कूप निर्माण संतोष बाई लक्ष्मण सिंह लिम्बोदा | Completed | 234458.57 | 230972 | 2020-03-15 | 2021-09-22
TARANA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034535057 — कपिलधारा कूप निर्माण रमेश रतनलाल यशवंतनगर | Closed | 234458.57 | 0 | 2020-01-26
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034661007 — KAPILDHARA KUP NIRMAN SUMAN BAI MANGILAL GRAM LIMBODA | Closed | 0 | 0 | 2020-10-02
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034669764 — KAPILDHARA KUP NIRMAN HEMKUWAR BAI ANTAR SINGH GRAM LIMBODA | Closed | 0 | 0 | 2020-10-03
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034682207 — KAPILDHARA KUP NIRMAN DINESH JAYRAM GRAM LIMBODA | Closed | 0 | 0 | 2021-01-26
TARANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012034685295 — KAPILDHARA KUP NIRMAN KRASHAN BAI RAMESH GRAM YASHWTNAGAR | Closed | 0 | 0 | 2020-10-03
TARANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012035106188 — KAPILDHARA KUP NIRMAN RAMSINGH LALUJI YASHWANTNAGAR | Completed | 282417.57 | 279881 | 2023-06-12 | 2024-10-11
TARANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012035106192 — KAPILDHARA KUP NIRMAN GEETABAI LAXMAN GRAM LIMBODA | Completed | 282417.57 | 280943 | 2023-06-12 | 2024-07-30
TARANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/22012035119457 — KAPILDHARA KUP NIRMAN GANARAM SHAVJI LIMBODA | Completed | 282417.57 | 281096 | 2023-06-22 | 2024-10-11
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035330455 — KOOP RECHARGE PIT KAILASH BAPU GRAM LIMBODA TARANA | Completed | 23177.32 | 22093.71 | 2025-04-21 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035330468 — KOOP RECHARGE PIT RAMESH BHERULAL GRAM LIMBODA TARANA | Completed | 23177.32 | 22007.71 | 2025-04-20 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718004071/IF/22012035330476 — KOOP RECHARGE PIT BHARAT KODULAL GRAM LIMBODA TARANA | New | 0 | 0 | 2025-04-01
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035330478 — KOOP RECHARGE PIT BHARAT KODULAL GRAM LIMBODA TARANA | Completed | 23177.32 | 22103.71 | 2025-04-21 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035330488 — KOOP RECHARGE PIT MAKHAN LAKSHMAN GRAM LIMBODA TARANA | Completed | 23177.32 | 22103.71 | 2025-04-21 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035330495 — KOOP RECHARGE PIT PAVITRA BAI MEHARBAN GRAM LIMBODA TARANA | Completed | 23177.32 | 22103.71 | 2025-04-20 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718004071/IF/22012035330500 — KOOP RECHARGE PIT VIKRAM PRAHLAD GRAM LIMBODA TARANA | New | 0 | 0 | 2025-04-01
TARANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718004071/IF/22012035536794 — FARM POND NIRMAN NAGULAL MANUJI GRAM LIMBODA | Physically Completed | 299694.44 | 278400.47 | 2025-05-21 | 2026-03-30
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035543987 — KOOP RECHARGE PIT VIKRAM PRAHLAD GRAM LIMBODA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545769 — KUP RECHARGE PIT BHANWARLAL BHAVSINGH GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545775 — KUP RECHARGE PIT JOJAN DULESINGH GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545782 — KUP RECHARGE PIT ISHWAR RAMSINGH GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545785 — KUP RECHARGE PIT INDARSINGH BHONESINGH GRAM LIMBODA TARANA | Completed | 23177.32 | 21950.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545789 — KUP RECHARGE PIT VIKRAMSINGH BHONESINGH GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545792 — KUP RECHARGE PIT BHAGWANTA LALUJI GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545797 — KUP RECHARGE PIT PRAHLAD SIDDHUJI GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545803 — KUP RECHARGE PIT UMRAV MUNNALAL GRAM LIMBODA TARANA | Completed | 23177.32 | 22078.71 | 2025-05-24 | 2026-03-27
TARANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718004071/IF/22012035545808 — KUP RECHARGE PIT HARJI RUPAJI GRAM YASHWANTNAGAR | Completed | 23177.32 | 22100.71 | 2025-05-25 | 2026-03-27
TARANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718004071/IF/22012035616226 — EK BAGIYA MAA KE NAAM REKHA BAI DINESH GRAM LIMBODA | Closed | 190647.95 | 0 | 2025-09-25
TARANA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/2नवीन कुप — नवीन कुप निमार्ण मेहरवान सिहं | Deleted | 169000 | 10240 | 2009-05-22
TARANA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/2नवीन कूप — नवीन कूप निर्माण भगवंता लालू लिम्‍बोदा | Completed | 162000 | 118213 | 2009-12-09 | 2011-08-29
TARANA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718004071/IF/9993662678 — केटल शेड निर्माण मानसिंघ घिशा | Deleted | 0 | 0 | 2015-01-26
TARANA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718004071/IF/9993662679 — केटल शेड निर्माण नगलल मानुजी | Deleted | 0 | 0 | 2015-01-26
TARANA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/9993662680 — कपिलधारा निर्माण प्रेमनारायण कन्हैया लाल | Deleted | 0 | 0 | 2015-01-26
TARANA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/9993662681 — कपिलधारा निर्माण भेरूलाल कालूराम | Deleted | 0 | 0 | 2015-01-26
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/9993716638 — KAPILDHARA KUP NIRMAN 1 | Deleted | 0 | 0 | 2016-04-14
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718004071/IF/9993716775 — KAETAL SHED NIRMAN 1 | Deleted | 0 | 0 | 2016-04-14
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1002603 — Construction of IAY House -IAY REG. NO. MP2075786 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1003069 — Construction of IAY House -IAY REG. NO. MP2959596 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1006023 — Construction of IAY House -IAY REG. NO. MP1366888 | Completed | 15480 | 15480 | 2017-09-15 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1022252 — Construction of IAY House -IAY REG. NO. MP2033071 | Completed | 15480 | 15480 | 2017-08-10 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1040214 — Construction of IAY House -IAY REG. NO. MP2990681 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1051487 — Construction of IAY House -IAY REG. NO. MP3941392 | Completed | 15480 | 15504 | 2017-10-26 | 2018-04-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1051699 — Construction of IAY House -IAY REG. NO. MP3966855 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1055370 — Construction of IAY House -IAY REG. NO. MP1368092 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1055446 — Construction of IAY House -IAY REG. NO. MP1371521 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1072654 — Construction of IAY House -IAY REG. NO. MP2062432 | Completed | 15480 | 15136 | 2017-08-10 | 2018-02-06
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1072687 — Construction of IAY House -IAY REG. NO. MP2063725 | Completed | 15480 | 15308 | 2017-05-25 | 2018-01-02
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1083871 — Construction of IAY House -IAY REG. NO. MP2605688 | Completed | 15480 | 15564 | 2017-08-10 | 2018-06-12
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1088884 — Construction of IAY House -IAY REG. NO. MP2954463 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1210779 — Construction of IAY House -IAY REG. NO. MP1090097 | Completed | 15480 | 15648 | 2018-03-08 | 2018-07-20
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1210861 — Construction of IAY House -IAY REG. NO. MP1359867 | Completed | 15480 | 15648 | 2018-03-08 | 2018-07-20
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1460730 — Construction of IAY House -IAY REG. NO. MP2055486 | Completed | 15480 | 15660 | 2018-04-12 | 2018-08-19
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1460854 — Construction of IAY House -IAY REG. NO. MP2063746 | Completed | 15480 | 15660 | 2018-04-12 | 2018-07-31
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1634840 — Construction of IAY House -IAY REG. NO. MP2610866 | Completed | 15660 | 15660 | 2018-04-12 | 2018-08-19
TARANA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/1638031 — Construction of IAY House -IAY REG. NO. MP2960907 | Completed | 15660 | 14616 | 2018-04-12 | 2018-07-20
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/207251 — Construction of IAY House -IAY REG. NO. MP1021654 | Completed | 15030 | 21148 | 2017-02-23 | 2018-01-10
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/227973 — Construction of IAY House -IAY REG. NO. MP1272036 | Completed | 15030 | 15240 | 2017-01-26 | 2018-01-02
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/232872 — Construction of IAY House -IAY REG. NO. MP1362697 | Completed | 15030 | 15120 | 2017-01-26 | 2017-10-26
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/233102 — Construction of IAY House -IAY REG. NO. MP1366954 | Completed | 15030 | 15016 | 2017-03-02 | 2018-01-02
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/233768 — Construction of IAY House -IAY REG. NO. MP1379767 | Completed | 15030 | 14896 | 2017-01-26 | 2017-12-13
TARANA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/235499 — Construction of IAY House -IAY REG. NO. MP1412953 | Completed | 15030 | 15480 | 2017-03-09 | 2018-01-02
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/3968382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880345 | Completed | 18360 | 18360 | 2022-06-15 | 2023-01-01
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/3968383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880482 | Completed | 18360 | 18360 | 2022-07-15 | 2023-05-22
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/3973349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114121291 | Completed | 18360 | 18132 | 2022-06-18 | 2023-01-01
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4065292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113914358 | Completed | 18360 | 18132 | 2022-06-11 | 2023-01-01
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4073866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118518996 | Completed | 18360 | 18360 | 2022-07-23 | 2023-05-22
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4242787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113628464 | Completed | 18360 | 18360 | 2022-07-29 | 2023-01-01
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4244699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880219 | Completed | 18360 | 18360 | 2022-07-29 | 2023-01-01
TARANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4376677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880414 | Completed | 18360 | 17952 | 2022-11-05 | 2023-05-22
TARANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4740450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106718570 | Completed | 23490 | 21870 | 2024-12-09 | 2026-02-07
TARANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4751319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116573498 | Completed | 23490 | 21942 | 2024-11-11 | 2025-08-05
TARANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4751325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116578801 | Completed | 23490 | 22158 | 2025-01-29 | 2025-08-05
TARANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/4861523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880289 | Completed | 23490 | 22320 | 2025-01-07 | 2025-08-05
TARANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718004071/IF/IAY/6287873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114776729 | Approved | 27000 | 0 | 2025-07-11
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/894800 — Construction of IAY House -IAY REG. NO. MP2063096 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/92933 — Construction of IAY House -IAY REG. NO. MP-18-004-071-002/22565969 | Deleted | 15480 | 0 | 2015-09-16
TARANA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/92934 — Construction of IAY House -IAY REG. NO. MP-18-004-071-002/22870461 | Deleted | 15480 | 0 | 2015-09-16
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/956911 — Construction of IAY House -IAY REG. NO. MP1433143 | Completed | 15480 | 15480 | 2017-05-25 | 2018-01-10
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/956966 — Construction of IAY House -IAY REG. NO. MP2020771 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/956970 — Construction of IAY House -IAY REG. NO. MP2032943 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/956974 — Construction of IAY House -IAY REG. NO. MP2075437 | Completed | 15480 | 15480 | 2017-09-07 | 2018-01-02
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/956975 — Construction of IAY House -IAY REG. NO. MP2075556 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/957031 — Construction of IAY House -IAY REG. NO. MP2581654 | Completed | 15480 | 15480 | 2017-08-10 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/957036 — Construction of IAY House -IAY REG. NO. MP2615847 | Completed | 15480 | 15136 | 2017-05-25 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/957039 — Construction of IAY House -IAY REG. NO. MP2648799 | Completed | 15480 | 15480 | 2017-08-10 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/957058 — Construction of IAY House -IAY REG. NO. MP2975988 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-26
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/982139 — Construction of IAY House -IAY REG. NO. MP3967010 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/982436 — Construction of IAY House -IAY REG. NO. MP3978329 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718004071/IF/IAY/983221 — Construction of IAY House -IAY REG. NO. MP1089983 | Completed | 15480 | 15480 | 2017-05-25 | 2017-12-13
TARANA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/नवीन कुप निर्माण राजाराम / कांशीराम — नवीन कुप निर्माण राजाराम / कांशीराम [ लिम्बोदा ] | Completed | 161000 | 80502 | 2009-03-14 | 2008-02-26
TARANA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718004071/IF/नवीन कूप न — नवीन कूप निर्माण वल्‍ला भेरूलाल लिम्‍बोदा | Completed | 162000 | 148887 | 2009-12-09 | 2011-08-29
TARANA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718004071/LD/22012034245814 — शांतिधाम समतलीकरण कार्य लिम्बोदा | Completed | 466000 | 459432.69 | 2015-12-24 | 2018-01-23
TARANA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718004071/LD/22012034245818 — शांतिधाम समतलीकरण कार्य यशवन्तनगर | Completed | 735000 | 549272.7 | 2015-12-24 | 2018-01-23
TARANA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718004071/LD/22012034304783 — खेल मैदान लिम्बोदा | Completed | 186600 | 185341.76 | 2017-05-25 | 2018-01-23
TARANA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718004071/LD/22012034304785 — खेल मैदान यशवंत नगर | Completed | 186600 | 185592 | 2017-05-25 | 2018-01-23
TARANA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718004071/RC/1G S B मार — G S B मार्ग निर्माण 2 [ लिम्बोदा ] | Completed | 141000 | 123499 | 2010-05-01 | 2011-08-29
TARANA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034161064 — पंच परमेश्वर सी. सी. व नाली निर्माण देवमहाराज के ओ | Completed | 76000 | 72708 | 2013-01-30 | 2013-12-20
TARANA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034189053 — पंचपरमेश्वर व नाली निर्माण राम मंदिर से पेयजल कुण | Completed | 160000 | 146772 | 2013-10-10 | 2015-04-02
TARANA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034189056 — पंचपरमेश्वर व नाली निर्माण खन्ना सिंह के घर से मा | Completed | 80000 | 79741.9 | 2013-10-10 | 2015-04-02
TARANA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034227547 — पंच परमेशवर सी सी रोड व् नाली निर्माण पानी की टंकी | Completed | 138000 | 138970 | 2014-08-19 | 2016-06-21
TARANA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034264252 — पञ्च परमेश्वर व नाली निर्माण पानी के टंकी से महेरबान के घर तक | Deleted | 0 | 0 | 2015-01-26
TARANA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034293458 — पंचपरमेश्वर व नाली निर्माण बाबूलाल के घर से मानु दा के घर की और | Completed | 103000 | 83586 | 2016-01-07 | 2017-10-26
TARANA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034302010 — सी सी रोड व नाली निर्माण 1 | Deleted | 0 | 0 | 2016-04-14
TARANA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034323718 — panchaparmeshwar see see w nali nirman | Deleted | 0 | 0 | 2017-04-01
TARANA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034332377 — पंचपरमेश्वर (१४ वित्तय) सी सी व नाली निर्माण कार्य शंकरलाल के घर से पी ऍम सड़क | Completed | 75225 | 54008 | 2017-05-04 | 2018-07-07
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034374504 — CC | Deleted | 0 | 0 | 2018-04-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034389307 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण कार्य राम मंदिर से पंचायत भवन की और | Completed | 49995 | 49068 | 2018-05-10 | 2018-08-21
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034438378 — cc | Deleted | 0 | 0 | 2019-04-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441640 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण हैंडपंप से केशर सिंह के घर तक | Completed | 15795 | 13572 | 2019-02-11 | 2020-07-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441645 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण मेहरबान सिंह के घर से दीप सिंह के घर तक | Completed | 11425 | 6612 | 2019-02-11 | 2020-07-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441649 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण पी ऍम सड़क से राधू दास के घर तक | Completed | 8370 | 8352 | 2019-02-11 | 2020-07-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441653 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण पी ऍम सड़क से महेंद्र सिंह के घर तक | Completed | 6637 | 6612 | 2019-02-11 | 2020-07-01
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441658 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण आंगनवाड़ी भवन से श्यामलाल जी के घर तक | Completed | 42338 | 25128 | 2019-03-10 | 2021-02-10
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034441662 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण हरजी लाल के घर से हनुमान मंदिर तक | Completed | 25875 | 9396 | 2019-03-08 | 2021-02-10
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034465786 — cc road | Deleted | 0 | 0 | 2019-01-26
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034465787 — cc road | Deleted | 0 | 0 | 2019-01-26
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034465788 — cc road | Deleted | 0 | 0 | 2019-01-26
TARANA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034465789 — cc road | Deleted | 0 | 0 | 2019-01-26
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034475064 — cc road | Deleted | 0 | 0 | 2019-05-29
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034475388 — पंचपरमेश्वर (१४ वित्य) नाली निर्माण सरकारी कुण्डी से पीएम सड़क | Closed | 4950 | 0 | 2019-05-29
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034479062 — पंचपरमेश्वर (१४ वित्य) सी सी व नाली निर्माण पी ऍम सड़क से गब्बा जी के घर तक | Completed | 81330 | 81312 | 2019-09-28 | 2020-07-01
TARANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034528642 — पंचपरमेश्वर (14 वित्य) सी सी व नाली निर्माण राजाराम के घर से मूलचन्द्र के घर की ओर लिम्बोदा | Completed | 12870 | 6630 | 2020-09-18 | 2021-10-27
TARANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034528644 — पंचपरमेश्वर (14 वित्य) सी सी व नाली निर्माण रामप्रसाद के घर से चंदु के घर की ओर लिम्बोदा | Completed | 52005 | 42492 | 2020-09-18 | 2021-10-27
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034540099 — PANCHAPARMESHWAR (15 VITYA) CC W NALI NIRMAN KODULAL KE GHAR SE AAGANWADI KI OR LIMBODA | Closed | 0 | 0 | 2020-01-26
TARANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034544311 — PANCHAPARMESHWAR (14 VITYA) CC W NALI NIRMAN PANCHAYAT BHAWAN KE SAMNE LIMBODA | Completed | 11700 | 11454 | 2020-11-25 | 2022-04-04
TARANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034544313 — PANCHAPARMESHWAR (14 VITYA) CC W NALI NIRMAN DULICHANDRA KE GHAR SE SHETAN BAI KE GHAR TAK LIMBODA | Completed | 11036 | 9120 | 2020-11-25 | 2021-09-24
TARANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034544315 — PANCHAPARMESHWAR (15 VITYA) CC W NALI NIRMAN KODULAL KE GHAR SE AAGANWADI BHAWAN KI OR LIMBODA | Closed | 48129 | 0 | 2020-01-26
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034578852 — PANCHAPARMESHWAR (15 VITYA) CC W NALI NIRMAN CHANDULAL KE GHAR SE HANUMAN MANDIR KI OR GRAM LIMBODA | Closed | 35550 | 0 | 2021-04-14
TARANA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034610517 — RCC (15 VITYA) NALI NIRMAN KALURAM KE GHAR SE MATA MANDIR KI OR LIMBODA | Completed | 8600 | 8340 | 2022-05-25 | 2022-11-22
TARANA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034610519 — RCC (15 VITYA) NALI NIRMAN BHAGIRATH KE GHAR SE HANDPUMP TAK LIMBODA | Completed | 15635 | 15590 | 2022-05-25 | 2024-03-28
TARANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034620533 — PANCHAPARMESHWAR (15 VITYA) CC NALI NIRMAN TUFAN SINGH KE GHAR SE HARI SINGH KE GHAR KI OR LIMBODA | Completed | 43000 | 41618 | 2023-07-26 | 2024-07-21
TARANA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034636595 — PANCHAPARMESHWAR (15 VITYA) NALI NIRMAN MEN ROAD SE SHYAMLAL KE GHAR KI OR YASHWANTNAGAR | Closed | 19000 | 0 | 2023-01-26
TARANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034661699 — RCC (15 VITYA) NALI NIRMAN DEVNARAYAN KE GHAR SE PULIYA KI OR LIMBODA | Completed | 31800 | 28067 | 2023-10-06 | 2024-03-28
TARANA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034676643 — cc road nali nirman | New | 0 | 0 | 2024-04-01
TARANA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034821714 — PANCHPARMESHWAR (15 VITYA) CC ROAD NIRMAN KUNDI SE LAXMAN SINGH KE GHAR TAK LIMBODA | Completed | 72000 | 70518 | 2024-08-01 | 2025-01-27
TARANA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034838939 — PANCHPARMESHWAR (05 VITYA) CC ROAD NIRMAN DINESH KE GHAR SE PANI KI TANKI KI OR YASHWANTGAD | Completed | 92000 | 91964 | 2025-06-09 | 2026-04-09
TARANA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034845603 — PANCHPARMESHWAR (15 VITYA) CC ROAD NIRMAN GANGA BAI KE GHAR SE DP KI OR GRAM LIMBODA | Completed | 40700 | 40560 | 2025-08-24 | 2026-03-15
TARANA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718004071/RC/22012034845605 — PANCHPARMESHWAR (15 VITYA) CC ROAD NIRMAN DHARMENDRA SINGH KE GHAR SE DEEP SINGH KE GHAR KI OR LIMBO | Approved | 38900 | 0 | 2025-04-14
TARANA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718004071/RC/299 — सी सी रोड व नाली निमाण देवनारायण के घर से बंजारा म | Completed | 111667 | 110836 | 2013-03-12 | 2013-12-20
TARANA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718004071/RC/GSB अर्थवर्क लिम्बोदा से हनुमान मन्द — GSB अर्थवर्क लिम्बोदा से हनुमान मन्दिर [लिम्बोदा] | Completed | 266290 | 217272 | 2008-06-05 | 2008-02-25
TARANA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718004071/RC/G.S.B.मार् — G.S.B.मार्ग निर्माण घाटी से यशवंतनगर [ लिम्बोदा ] | Completed | 500000 | 486470 | 2011-06-13 | 2013-02-27
TARANA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718004071/RS/22012034496184 — SAMUDAIK SWACHHATA PARISAR AJAA MOHALLA GRAM LIMBODA | Completed | 48000 | 43541 | 2020-12-23 | 2023-02-22
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718004071/RS/22012034539735 — NADEP NIRMAN KARY PULIYA KE PAS HANUMAN RASTE PAR GRAM LIMBODA | Closed | 0 | 0 | 2021-04-14
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718004071/RS/22012034539737 — NADEP NIRMAN KARY KANCHANSINGH KE BADE KE PAS GRAM LIMBODA | Closed | 0 | 0 | 2021-04-14
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718004071/RS/22012034542540 — NADEP NIRMAN KARY KANCHAN SINGH KE BADE KE PAS GRAM LIMBODA | Closed | 15158.23 | 0 | 2021-04-14
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718004071/RS/22012034542542 — NADEP NIRMAN KARY HANUMAN MANDIR ROAD PULIYA KE PAS GRAM LIMBODA | Closed | 15158.23 | 0 | 2021-04-14
TARANA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718004071/WC/22012034432715 — CHEK DEM SEETARAM JAT KE KHET KE PAS SASHKIYA NALE PAR BANJARI | Completed | 1123000 | 1113438 | 2019-02-27 | 2020-07-01
TARANA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718004071/WC/22012034516064 — CHEK DEM WITH NALA TRECHING NARAYAN SINGH KE KHET KE PAS LIMBODA | Completed | 1011755.1 | 921575.33 | 2020-05-02 | 2021-12-06
TARANA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718004071/WC/22012034516065 — CHEK DEM WITH NAL TRECING DHARMENDRA NAGU KE KHET KE PAS LIMBODA | Completed | 1003503.48 | 995247.51 | 2020-12-16 | 2022-11-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034677638 — ROOF TOP WH WORK IN P SCHOOL BHAWAN GRAM LIMBODA | Completed | 15037.95 | 2316 | 2021-09-30 | 2022-12-30
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034677643 — ROOF TOP WH WORK IN AAGANWADI BHAWAN GRAM LIMBODA | Completed | 15037.95 | 2316 | 2021-09-30 | 2022-12-30
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034677646 — ROOF TOP WH WORK IN SAMUDAIK SAWCCHTA PARISAR GRAM LIMBODA | Completed | 15037.95 | 2280 | 2021-09-30 | 2022-12-30
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718004071/WC/22012034728801 — CTR NALA TRECHING LAXMICHANDRA KE KHET SE SEETARAM KE KHET TAK GRAM LIMBODA | Completed | 303248.31 | 258501 | 2021-06-20 | 2022-04-04
TARANA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718004071/WC/22012034728805 — CTR NALA TRECHING SAJAN BAI KE KHET SE GABBA JI KE KHET KI OR GRAM LIMBODA | Completed | 300500.59 | 260460 | 2021-06-03 | 2022-04-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034741943 — CTR SOAK PIT HANUMAN MANDIR HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-09-13 | 2021-12-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034741946 — CTR SOAK PIT HANUMAN MANDIR SASHKIYA KUP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-09-13 | 2021-12-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034741950 — CTR SOAK PIT KHEL MEDAN HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-09-13 | 2021-12-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034741955 — CTR SOAK PIT KHARAPANI HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-09-13 | 2022-01-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034741959 — CTR SOAK PIT MEN ROAD HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-09-13 | 2022-01-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034837477 — CTR SOAK PIT NENAWAD ROAD SHASHKIYA KUP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10808 | 2021-10-07 | 2022-01-10
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034837478 — CTR SOAK PIT KHOKHA MATA KI PICHE GRAM LIMBODA | Completed | 14467.3 | 9279 | 2021-10-07 | 2022-01-10
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034837482 — CTR SOAK PIT KHOKHA MATA HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 11580 | 2021-10-07 | 2021-12-28
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034837484 — CTR SOAK PIT KUNDI KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-10-07 | 2022-01-10
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034837486 — CTR SOAK PIT BAG ME HANDPUMP KE PAS GRAM LIMBODA | Completed | 14467.3 | 10422 | 2021-10-28 | 2022-01-10
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873141 — CTR SOAK PIT PS PIYAV KE PAS LIMBODA | Completed | 14467.3 | 10422 | 2021-12-02 | 2022-01-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873144 — CTR SOAK PIT MS PIYAV KE PAS LIMBODA | Completed | 14467.3 | 10422 | 2021-12-02 | 2022-01-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873147 — CTR SOAK PIT MS PIYAV KE PAS 2 LIMBODA | Deleted | 0 | 0 | 2021-08-16
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873150 — CTR SOAK PIT SWCHHTA PARISAR KE PAS LIMBODA | Completed | 14467.3 | 10422 | 2021-12-02 | 2021-12-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873152 — CTR SOAK PIT MS HANDPUMP KE PAS LIMBODA | Completed | 14467.3 | 8878 | 2021-12-02 | 2022-01-04
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718004071/WC/22012034873153 — CTR SOAK PIT PS HANDPUMP KE PAS LIMBODA | Completed | 14467.3 | 10422 | 2021-12-02 | 2022-01-10
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1718004071/WC/22012034897354 — STOPDEM MARMMAT KALUSINGH KE KHET KE PAS LIMBODA | Deleted | 0 | 0 | 2021-10-02
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012034906617 — NALA TRECHING OMPRAKASH KE KHET SE RUKHAMA BAI KHET KI OR LIMBODA | Completed | 108120.03 | 101883 | 2022-02-14 | 2022-05-22
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012034906618 — NALA TRECHING BAPULAL KE KHET SE OMPRAKASH KE KHET KI OR LIMBODA | Completed | 170715.83 | 151032 | 2022-02-14 | 2022-10-25
TARANA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1718004071/WC/22012034921931 — PDW STOP DEM MARMMAT KARY KALU SINGH KE KHET KE PAS LIMBODA | Completed | 11000 | 10974 | 2022-03-13 | 2022-11-04
TARANA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012034977468 — NALA TRECHING GENDMAL KE KHET KE PAS LIMBODA | Completed | 185600.16 | 160898 | 2022-05-27 | 2024-07-27
TARANA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718004071/WC/22012034999153 — CONTOUR TRENCH NIRMAN NAG MANDIR KE PAS YASHWANTNAGAR | Completed | 107584.66 | 93012 | 2022-11-05 | 2023-05-16
TARANA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1718004071/WC/22012034999154 — WIRE CRATE GABION NIRMAN NAG MANDIR KE PAS SHASHKIYA NALE PAR YASHWANTNAGAR | Deleted | 28831.24 | 2520 | 2022-10-29
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718004071/WC/22012035006472 — RICHARJ POND NIRMAN YASHWANTNAGAR | Completed | 337559.7 | 295606 | 2023-08-11 | 2024-07-21
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012035088168 — NALA TRECHING KESHAR SINGH KE KHET KE PAS LIMBODA | Closed | 227962.99 | 0 | 2023-04-14
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012035088169 — NALA TRECHING DEERAP SINGH KE KHET KE PAS LIMBODA | Closed | 242946.41 | 0 | 2023-04-14
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718004071/WC/22012035116509 — RICHARJ POND SHASKIYA BHUMI PAR GRAM YASHWANTNAGAR | Completed | 357975.87 | 298969 | 2023-09-29 | 2024-07-27
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718004071/WC/22012035116663 — CONTOUR TRENCH NIRMAN SHASHKIYA BHUMI PAR YASHWANTNAGAR | Completed | 149888 | 129519 | 2023-09-29 | 2024-07-27
TARANA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718004071/WC/22012035116689 — NALA TRECHING KUNDALI KE PAS LIMBODA | Completed | 341731.54 | 104750 | 2023-09-29 | 2026-04-27
TARANA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718004071/WC/22012035244651 — RICHARJ POND NIRMAN KALU KE KHET KE PAS GRAM YASHWANTNAGAR | Completed | 197876.09 | 99680 | 2025-02-19 | 2026-03-15
TARANA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718004071/WC/22012035244652 — RICHARJ POND NIRMAN MANGILAL KE KHET KE PAS GRAM YASHWANTNAGAR | Completed | 198138.72 | 158400 | 2025-02-19 | 2025-06-22
TARANA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718004071/WC/22012035244654 — CONTOUR TRENCH NAI AABADI KE PAS GRAM YASHWANTNAGAR | Approved | 134615.03 | 0 | 2024-12-04
TARANA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718004071/WC/23पेयजल कु — पेयजल कुप निर्माण [ लिम्बोदा ] | Completed | 98800 | 146354 | 2009-02-18 | 2011-08-29
TARANA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718004071/WC/VB/22012035330858 — SOAK PIT HANDPUMP KE PAS GRAM LIMBODA | Ongoing | 27847.31 | 10499.97 | 2026-08-05
TARANA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718004071/WH/22012034389718 — तालाब बन्ड मरम्मत कार्य गेंदा लाल के खेत के पास लिम्बोदा | Completed | 91000 | 94134 | 2019-01-07 | 2019-06-10