## Work List
Exported on: 2026-10-18 16:17:59
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: MANGROLA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1718005057/AV/22012034660009 — RCC NALI NIRMAN KARY RAJENDRA SINGH KE GHAR SE ASHOK SINGH KE GHAR TAK | Ongoing | 54000 | 0 | 2025-01-10
UJJAIN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1718005057/AV/22012034660010 — RCC NALI NIRMAN KARY NARSINGH MANDIR SE RAMJANAM SINGH KE GHAR TAK | Ongoing | 57000 | 0 | 2025-01-10
UJJAIN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1718005057/IF/22012035324339 — AATMARAM BAPUJI KUP RECHARGE PIT RATNAKHEDI | New | 0 | 0 | 2025-04-01
UJJAIN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718005057/IF/IAY/39041 — Construction of IAY House -IAY REG. NO. MP-18-005-057-001/237 | Approved | 27000 | 0 | 2015-11-21
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005057/IF/IAY/4563449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115796869 | Ongoing | 27000 | 261 | 2024-12-24
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005057/IF/IAY/4565706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115829429 | Ongoing | 27000 | 0 | 2024-12-24
UJJAIN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718005057/RC/22012034673274 — CC ROAD NIRMAAN MUKHYA MARG SE BAHADUR SINGH KE GHAR KI OR MANGROLA | Ongoing | 35000 | 0 | 2024-09-04
UJJAIN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718005057/RC/22012034828854 — CC ROAD NIRMAN AJIT SINGH KE GHAR SE DEVENDRA SINGH KE GHAR TAK MUKHYA MARG MANGROLA | Ongoing | 93000 | 0 | 2025-01-10
UJJAIN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718005057/WC/22012034899584 — NAALA TRENCHING MORGRAM KE PASS MANGROLA | Ongoing | 208604.25 | 0 | 2022-02-04
UJJAIN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718005057/WC/22012034906034 — NAALA TRENCHING BYPASS ROAD PULIYA KE PASS MANGROLA | Ongoing | 204712.66 | 0 | 2022-02-04