## Work List
Exported on: 2026-10-23 22:25:03
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: BHAND BADODIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1718005065/AV/22012034657645 — KAWARD NALI NIRMAN KARY NABBI BAI KE GHAR SE PRAKASH KE GHAR KI OR SAYARKHEDI | New | 0 | 0 | 2024-06-12
UJJAIN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1718005065/DP/22012034577954 — NAVIN SAMUDAYAK KUP NIRMAN DEWANKHEDI | Ongoing | 648891.55 | 0 | 2023-07-14
UJJAIN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1718005065/DP/22012034628888 — PLANTATION KARYA TALAB KE PAS DEWANKHEDI | Approved | 0 | 0 | 2024-12-16
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718005065/IF/22012035256439 — NANDAN FALODYANJIVAN PITA BHAGIRATH GRAM BHAND BADODIYA | Ongoing | 145050.83 | 0 | 2024-12-24
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718005065/IF/22012035256442 — NANDAN FALODYAN SORAM BAI PATI DHARA SINGH GRAM BHAND BADODIYA | Ongoing | 145050.83 | 0 | 2024-12-24
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718005065/IF/22012035288702 — KUP NIRMAN KARYA RAJENDRA SHARMA JI GRAM SAYARKHEDI | Ongoing | 312155.12 | 0 | 2025-01-24
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718005065/IF/22012035288723 — KUP NIRMAN KARYA VIJAY SINGH GRAM DEVANKHEDI | Ongoing | 312155.12 | 2100 | 2025-01-24
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718005065/IF/22012035288734 — KUP NIRMAN KARYA AATMARAM GRAM SAYARKHEDI | Approved | 312155.12 | 0 | 2024-12-05
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718005065/IF/22012035313217 — KUP NIRMAN KARYA DHRU PITA PRAKASH GRAM DEVANKHEDI | Ongoing | 322434.5 | 2674.99 | 2025-04-28
UJJAIN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1718005065/IF/22012035489580 — JGSA2025 KUP RICHARJ PIT PAWAN JAAT SAYARKHEDI GP BHAND BADODIYA | Approved | 25899.46 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035556018 — JGSA2025 KUP RICHARJ PIT BHERU LAL SEN GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035573533 — JGSA2025 KUP RICHARJ PIT RAJARAM PITA ABJI GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035573536 — JGSA2025 KUP RICHARJ PIT MAYRAM SOLANKI GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035573546 — JGSA2025 KUP RICHARJ PIT BHERU LAL AMRAJI GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035573550 — JGSA2025 KUP RICHARJ PIT JAGDHISH PPITA LALJI GP BHAND BADODIYA | Approved | 25899.46 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035573554 — JGSA2025 KUP RICHARJ PIT BABULAL PITA DAYARAMGP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035574080 — JGSA2025 KUP RICHARJ PIT KALURAM PITAA DALLJI GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035574085 — JGSA2025 KUP RICHARJ PIT DHARMENDRA PRAJAPAT GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035574098 — JGSA2025 KUP RICHARJ PIT BHERULAL PRAJAPAT GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035574102 — JGSA2025 KUP RICHARJ PIT SAWAN SINGH CHOUHAN GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1718005065/IF/22012035574113 — JGSA2025 KUP RICHARJ PIT SARE KUNWAR GP BHAND BADODIYA | Approved | 0 | 0 | 2025-04-16
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718005065/IF/22012035609657 — EK BAGIYA MAA KE NAME SHAKUNTALA BAI PATI BALRAM GRAM BHAND BADODIYA | Approved | 0 | 0 | 2025-08-15
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/4683814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100485227 | Physically Completed | 23490 | 0 | 2026-03-06 | 2026-07-05
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/4989500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106498531 | Ongoing | 27000 | 0 | 2025-03-26
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/4991218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106869333 | Completed | 27000 | 0 | 2025-04-11 | 2026-10-14
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/4991546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106705841 | Approved | 27000 | 0 | 2025-02-20
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/4991607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106735023 | Ongoing | 27000 | 0 | 2025-06-01
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/5095120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142023343 | Ongoing | 27000 | 0 | 2025-07-18
UJJAIN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/5166213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106717674 | Ongoing | 27000 | 14616 | 2026-08-07
UJJAIN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/5673727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122087733 | Ongoing | 27000 | 0 | 2025-07-28
UJJAIN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/5674405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106871358 | Approved | 27000 | 0 | 2025-02-23
UJJAIN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718005065/IF/IAY/93845 — Construction of IAY House -IAY REG. NO. MP-18-005-065-003/221 | Approved | 27000 | 0 | 2015-10-14
UJJAIN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1718005065/LD/22012034592138 — SAMUDAYAK VRAKSHA ROPAN KARYA SHAMSHAN PARISAR DEVAN KHEDI | Ongoing | 427106.07 | 0 | 2023-07-15
UJJAIN | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718005065/RC/22012034438610 — C C NALI NIRMAN PRIMARY SCHOOL DEVANKHEDI SE BANJARA BASTI KI OR GRAM DEVANKHEDI, JANPAD NIDHI | Ongoing | 70000 | 0 | 2019-02-12
UJJAIN | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718005065/RC/VB/YD/22012034854458 — CC ROAD NIRMAN SATYANARAYAN MANDIR SE MUKHYA MARG KI AUR BHAND BAD0DIYA | Approved | 0 | 0 | 2026-07-21
UJJAIN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718005065/WC/22012035195814 — NALA TRENCHING BABULAL JI KE KHET SE GOKUL KE KHET KI OR GRAM DEVANLKEDI | New | 0 | 0 | 2024-02-14
UJJAIN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718005065/WC/22012035195816 — NALA TRENCHING BABULAL JI KE KHET SE GOKUL KE KHET KI OR GRAM DEVANLKEDI | New | 0 | 0 | 2024-02-14
UJJAIN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718005065/WC/22012035195824 — NALA TRENCHING KAILASH BAI KE KHET SE GAJRAJ SINGH KE KHET KI OR GRAM DEVANLKEDI | New | 0 | 0 | 2024-02-14
UJJAIN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1718005065/WC/22012035283418 — JGSA 2025 CHECK DAM NIRMAN KARYA NALE PAR GRAM BHAND BADODIYA | Approved | 25899.46 | 0 | 2025-04-15