## Work List
Exported on: 2026-09-28 05:53:17
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: SILODIA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006008/AV/22012034447761 — AGANVADI BHAVAN NIRMAN SILODIYA | Completed | 180000 | 165368 | 2019-04-04 | 2023-03-01
BADNAGAR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1718006008/AV/22012034583904 — Construction of dining table | Closed | 16093.2 | 0 | 2021-04-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006008/AV/22012034624650 — श्मशान घाट मुंगावदी | Closed | 0 | 0 | 2022-10-02
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006008/AV/22012034658357 — नाडी निर्माण कार्य उच्छब लाल के घर से बालकृष्ण दास बैरागी के घर तक सिलोदिया | New | 0 | 0 | 2024-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006008/AV/22012034658412 — नाडी निर्माण कार्य उच्छब लाल के घर से बालकृष्ण दास बैरागी के घर तक सिलोदिया | New | 0 | 0 | 2024-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006008/AV/22012034658773 — N नाली निर्माण कार्य उच्छबल के घर से बालकृष्ण दास बैरागी के घर तक सिलादिया | New | 0 | 0 | 2024-04-14
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006008/DP/22012034242258 — वृछा रोपण शांति धाम सिलोदिया | Deleted | 33500000000 | 0 | 2017-05-19
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/DW/9993654278 — SOKHATA GADDA SILODIYATS-30/12.6.15 UNIT 5 | Completed | 32500 | 30797.85 | 2015-07-01 | 2016-03-30
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006008/IF/22012034344841 — वृक्ष रोपण शांतिधाम सिलोदिया (t.s. 3005/6008) | Completed | 335000 | 21912 | 2017-06-21 | 2020-09-10
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006008/IF/22012034357928 — vriksharopan dehta 2 | Deleted | 335000 | 0 | 2017-08-09
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035026443 — पशुशेड निर्माण अम्रतलाल /आत्माराम नाई सिलोदिया | Deleted | 0 | 0 | 2022-08-15
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035026446 — पशुशेड निर्माण मनोहरसिंह /उदयसिंह मुगावदी | Deleted | 0 | 0 | 2022-08-15
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035247952 — Cattle Shed Nirman Savita bhai pati amratlal | Deleted | 0 | 0 | 2024-04-14
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035252382 — केटल सेट निर्माण पूजा बाई पती अजय सिलोदिया | Deleted | 0 | 0 | 2024-06-06
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035256356 — केटल सेट निर्माण सरिता बाई पति अमृतलाल जी | Deleted | 0 | 0 | 2024-08-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035579622 — CATTE SHED NIRMAN KARYA POOJA BAI W/0 AJAY SILODIYA | New | 0 | 0 | 2025-04-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035641998 — CATTLE SHED POOJA BAI PATI AJAY 5123030 | Approved | 0 | 0 | 2025-10-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035642031 — CATTLE SHED SARITA BAI PATI AMARAT LAL 5123008 | Approved | 0 | 0 | 2025-10-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006008/IF/22012035652671 — PASHU SHED NIRMAAN KARY SANTOSH BAI MANOHAR SINGH MUNGAWADI SHG CODE 170021354754 | Approved | 0 | 0 | 2025-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/9993679472 — IAY(LEELA BAI -RAMSINGH ) | Completed | 14310 | 3816 | 2016-01-08 | 2017-11-25
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/9993699740 — IAY (SITABAI_RATNLAL) | Completed | 14310 | 13644 | 2016-01-08 | 2017-09-04
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1462841 — Construction of IAY House -IAY REG. NO. MP2159488 | Completed | 15480 | 15312 | 2018-04-05 | 2018-08-16
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1863536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4902132 | Completed | 15660 | 15660 | 2018-07-01 | 2018-12-29
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1863549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4943084 | Completed | 15660 | 14268 | 2018-07-01 | 2018-11-14
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1863574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5025260 | Completed | 15660 | 15376 | 2018-09-23 | 2020-05-21
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1863717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5451589 | Deleted | 15660 | 0 | 2018-06-24
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1872595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5707964 | Completed | 15660 | 15312 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/1872897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5448908 | Completed | 17100 | 1215 | 2018-07-01 | 2024-11-22
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/254782 — Construction of IAY House -IAY REG. NO. MP2102931 | Completed | 15030 | 15472 | 2017-01-30 | 2017-12-27
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/262035 — Construction of IAY House -IAY REG. NO. MP1295142 | Completed | 15030 | 15450 | 2017-02-27 | 2017-12-27
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/268646 — Construction of IAY House -IAY REG. NO. MP1283948 | Completed | 15030 | 14328 | 2017-02-04 | 2018-03-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4058836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113647712 | Completed | 18360 | 15980 | 2022-08-31 | 2023-12-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4079171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119592027 | Completed | 18360 | 17952 | 2022-08-18 | 2023-06-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4079185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119596046 | Completed | 18360 | 17340 | 2022-08-18 | 2024-01-30
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/410918 — Construction of IAY House -IAY REG. NO. MP1270404 | Completed | 15030 | 1002 | 2017-02-27 | 2018-05-21
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/410934 — Construction of IAY House -IAY REG. NO. MP1270534 | Completed | 15030 | 16392 | 2017-02-04 | 2018-02-08
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4181850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147160537 | Completed | 18360 | 16626 | 2022-09-14 | 2023-12-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4291745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113685809 | Completed | 18360 | 18239.7 | 2022-12-19 | 2023-04-30
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4292509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123831855 | Completed | 18360 | 12444 | 2022-08-31 | 2024-07-17
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4295205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147158961 | Physically Completed | 18360 | 15552 | 2024-08-25 | 2024-11-21
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4690407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113641411 | Ongoing | 23490 | 23112 | 2025-02-11
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4698336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115110739 | Ongoing | 23490 | 22050 | 2024-10-06
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/4774046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125341433 | Completed | 23490 | 20873 | 2025-02-04 | 2025-12-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5247272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119852681 | Physically Completed | 23490 | 21924 | 2025-11-14 | 2026-02-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5247743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113638062 | Ongoing | 23490 | 23490 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5248493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119846869 | Ongoing | 23490 | 21924 | 2025-08-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5255578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106923078 | Ongoing | 23490 | 16016 | 2025-07-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5255797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115109007 | Ongoing | 23490 | 20097 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5259769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113648969 | Ongoing | 23490 | 20880 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5261459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145690900 | Ongoing | 23490 | 19670 | 2025-08-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5264676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114190744 | Ongoing | 23490 | 21924 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5267532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119605316 | Ongoing | 23490 | 0 | 2026-02-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5275305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113651393 | Physically Completed | 23490 | 20880 | 2025-07-08 | 2026-01-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5279023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106938796 | Ongoing | 23490 | 20880 | 2025-07-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5286496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119607589 | Physically Completed | 23490 | 23490 | 2025-05-12 | 2026-03-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5295307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113680485 | Physically Completed | 23490 | 21924 | 2025-10-28 | 2026-01-17
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5300598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113679083 | Ongoing | 23490 | 0 | 2026-02-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5304447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113676384 | Physically Completed | 23490 | 23229 | 2025-04-26 | 2026-05-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5304474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113683338 | Physically Completed | 23490 | 12528 | 2025-08-06 | 2026-04-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5319598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113642763 | Ongoing | 23490 | 19836 | 2025-07-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5320768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119603728 | Ongoing | 23490 | 23490 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5323108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119601556 | Ongoing | 23490 | 0 | 2026-02-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5333399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119849460 | Physically Completed | 23490 | 20880 | 2025-04-26 | 2026-01-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5336954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119593787 | Physically Completed | 23490 | 10962 | 2026-02-02 | 2026-05-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5435723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106930507 | Ongoing | 23490 | 22707 | 2025-04-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5438066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113689121 | Ongoing | 23490 | 21924 | 2025-12-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5438906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146431130 | Physically Completed | 23490 | 21924 | 2025-05-12 | 2025-12-25
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5625139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146421630 | Ongoing | 23490 | 21924 | 2025-08-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5720148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113645978 | Ongoing | 23490 | 15921 | 2025-09-24
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/578834 — Construction of IAY House -IAY REG. NO. MP2119729 | Completed | 15030 | 15420 | 2017-02-14 | 2017-12-12
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/5970551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119610247 | Ongoing | 23490 | 14616 | 2026-05-19
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/780374 — Construction of IAY House -IAY REG. NO. MP2109798 | Completed | 15030 | 14448 | 2017-06-18 | 2017-12-27
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/780375 — Construction of IAY House -IAY REG. NO. MP2111570 | Completed | 15030 | 15480 | 2017-05-11 | 2017-12-27
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/780376 — Construction of IAY House -IAY REG. NO. MP2111628 | Completed | 15030 | 15480 | 2017-05-11 | 2018-02-08
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/780394 — Construction of IAY House -IAY REG. NO. MP2159271 | Completed | 15030 | 15480 | 2017-05-11 | 2017-11-25
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/899831 — Construction of IAY House -IAY REG. NO. MP2134973 | Completed | 15480 | 15480 | 2017-06-18 | 2017-12-29
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/961996 — Construction of IAY House -IAY REG. NO. MP3342346 | Completed | 15480 | 15480 | 2017-12-09 | 2018-03-01
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006008/IF/IAY/962184 — Construction of IAY House -IAY REG. NO. MP3346383 | Completed | 15480 | 15480 | 2017-12-09 | 2018-02-07
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006008/LD/22012034247082 — SHANTIDHAM me shed+samtlikran cpt(ts-236/5.11.15) | Completed | 532881 | 481633.8 | 2016-01-04 | 2016-10-20
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006008/LD/22012034294393 — SHANTIDHAM me shed+samtlikran cpt MUNGAVADI t/s 138/11-11-16 | Completed | 797000 | 520567.4 | 2016-12-05 | 2017-08-10
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718006008/PG/9425887743 — PLAY GROUND SILODIYA | Completed | 737400 | 648386.2 | 2016-01-05 | 2016-10-20
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034188626 — cc road+nali savai singh se hiralal(ts-176/13.9.13 | Completed | 203000 | 176527 | 2013-10-07 | 2014-02-28
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034199085 — cc+nali rajya+m mungawdi(ts-143/6.6.13) | Completed | 66750 | 60045 | 2014-01-15 | 2014-03-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034203996 — cc+nali pp+m shree devnarayan mandir(ts-335/23.1.1 | Completed | 197000 | 174026 | 2014-02-12 | 2014-11-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006008/RC/22012034210987 — gravel road silodiya kharspd(ts 519/28/01/2014) | Completed | 1387000 | 1340242.16 | 2014-03-04 | 2016-06-20
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034226631 — cc road pp+m sajjansingh(Ts 114/27/05/2014) | Completed | 69000 | 60781 | 2014-08-05 | 2015-06-05
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034226637 — cc road siddhuji k ghar(TS 113/27/05/2014) | Completed | 86000 | 81690 | 2014-08-02 | 2015-06-05
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034263985 — cc road +nali pp+m narayan se karan mungawdi ts-143/24.9.15 | Completed | 71000 | 38048 | 2015-10-09 | 2016-10-20
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034264509 — cc+nali nirman mn+pp2 gram abadi silodiya | Closed | 0 | 0 | 2014-10-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034323125 — CC ROAD AND NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034327243 — cc rod nali nirman jivan ke ghar se pradhan mantri sadak tak (ts7418/24.12.16) | Completed | 70000 | 135426 | 2017-03-09 | 2018-03-31
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034338605 — सी सी रोड +नाली निर्माण नाहरजी के घर से प्रधानमंत्री रोड तक | Deleted | 325000 | 0 | 2017-05-20
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034338709 — सी सी रोड +नाली निर्माण राम किशन के घर से मुख्य मार्ग तक (t.s.580/04/03/2017) | Deleted | 6500000000 | 0 | 2017-05-21
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006008/RC/22012034339776 — सुदूर ग्राम सम्पर्क सडक सिलोदिया से मुख्यमंत्रीसड़क लसुडिया तक(T.S.NO.570/22/02/2017) | Completed | 2336000 | 2018581.85 | 2017-05-31 | 2019-11-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034365063 — सी सी रोड् + नालीनिर्माण रामकिशन के घर से मुख्य मार्ग तक | Completed | 65000 | 61920 | 2017-10-28 | 2018-01-10
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034371137 — सीसी रोड +नाली | Closed | 0 | 0 | 2018-04-01
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034440174 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006008/RC/22012034549398 — Greval sadak Rajaram ke ghar se jivan lal yadav ke khet tak | Completed | 1257178.11 | 1349139.68 | 2020-12-05 | 2021-04-27
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/22012034823320 — Nali nirman karya uchchav lalji ke ghar se balkrishna das bairagi ke ghar tak | Approved | 114000 | 0 | 2024-06-06
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006008/RC/28मुरमीकरण — मुरमीकरण कार्य सलवा से सिलोदिया (468/10.6.11) | Completed | 497000 | 474105.75 | 2011-06-13 | 2012-06-29
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006008/RC/29अर्थवर्क — अर्थवर्क स‍िलोदा से लसुड‍िया मार्ग (365/24.5.11) | Completed | 497000 | 405745 | 2012-04-02 | 2012-11-15
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/32सी सी रो — सी सी रोङ एवं नाली fनमाण ‍िसलो‍दीया,शान्‍ि‍तलाल के घरसे गंगाराम के घरतकPP+M (374/16.02.2012) | Completed | 284200 | 118492 | 2012-03-26 | 2013-03-23
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006008/RC/35आन्‍तर‍ि — आन्‍तर‍िक मार्ग (जी.एस.बी ) मूरमीकरण कार्य केलाश के घर से गोवधन के घर (T/S 61/22.05.12) | Completed | 499000 | 406612 | 2012-06-04 | 2013-03-23
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/35सी सी रो — सी सी रोङ व नाली V+ M.‍ (T/S 74 /20.01.2011) | Completed | 200000 | 200050 | 2012-01-16 | 2013-03-23
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006008/RC/36सी सी रो — सी सी रोङ नाली स‍हीत PP+M Pashu dhel से Udaypal tak SILODIYA(459/6.10.2012) | Completed | 120700 | 109786 | 2013-02-07 | 2013-11-07
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006008/RC/3 सिलोदिया — सिलोदिया अर्थवर्क सिलोदिया से चिरोला तक | Completed | 763000 | 14105 | 2009-02-28 | 2012-02-21
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006008/RC/6 अर्थवर्क — अर्थवर्क सिलोदिया से खरसौदकंला मार्ग भाग 1 | Completed | 497000 | 480750 | 2010-05-10 | 2010-12-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006008/RS/22012034311905 — NADEP PRAKASH/DAYARAMJI( T.S.295/30/11/2016) | Completed | 12200 | 180 | 2016-12-29 | 2017-10-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006008/RS/22012034313455 — NADEP SOBHARAMs/oAMBARAM JI(T.S.295/30/11/2016) | Completed | 12200 | 2004 | 2016-12-29 | 2017-10-25
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006008/RS/22012035129772 — Nali nirman karya uchchav lal ke ghar se balkrishana das beragi ke ghar | Completed | 100000 | 99872.61 | 2024-07-27 | 2026-03-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006008/RS/32082 — NIRMAL BHARAT MANUBAI MANGILAL SILODIA (AS- 100/14 | Deleted | 4312 | 0 | 2013-06-12
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034429176 — चेक डेम एवं नाला ट्रेचिंग कार्य मुगावदी | Completed | 828000 | 505140 | 2018-12-21 | 2020-05-10
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034430188 — Check dam nala traincjingh mugavdi k raste par ts 100/27.12.18 | Completed | 1485000 | 866337.63 | 2019-01-03 | 2019-11-26
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034430201 — mwc check dam nala trainching mugavdi k raste par ts 101/27.12.18 | Completed | 1500000 | 863429.3 | 2019-01-07 | 2019-12-05
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034438451 — chek deam Nirman | Closed | 0 | 0 | 2018-04-14
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034443446 — Check dam nirman gram mugavdi k nale par ts 178/22.2.19 | Completed | 1348000 | 1312702.5 | 2019-03-10 | 2021-02-27
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034444542 — check dam nala trainching gram mugavdi k nale par ts 214/28.2.19 | Completed | 1253000 | 1203390 | 2019-03-10 | 2020-05-10
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034482032 — रिचार्ज पीठ हेडपंप हैंड पंप गोदाम के पास silodiya | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034482052 — रिचार्ज पीठ हैंड पंप DPके पास silodiya | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034502981 — CHECK DAM NIRMAND KHARSODKALA KMRASTE PAR JIVAN YADAV K KHET K PAS G.P SILODIYA | Completed | 1126293.08 | 1131102 | 2020-01-04 | 2021-02-27
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1718006008/WC/22012034502985 — WEST WEIR NIRMAND TALAB K PASS SILODIYA | Suspended | 1499625.82 | 0 | 2020-03-17
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006008/WC/22012034556945 — परकुलेशन टैंक | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1718006008/WC/22012034566615 — वेस्टवेयर का निर्माण सिलोदिया | Closed | 0 | 0 | 2020-05-18
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718006008/WC/22012034580906 — Nala trenching work mungawadi raste | Closed | 0 | 0 | 2020-08-26
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718006008/WC/22012034580907 — Nala trenching work silodiya puliya se | Closed | 0 | 0 | 2020-08-26
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1718006008/WC/22012034715497 — Nala treching silodiya | Completed | 391238.4 | 387702 | 2021-06-10 | 2024-07-29
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034744218 — shokta gadda anganwadi ke paas hand pump pe CTR | Closed | 5717.19 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718006008/WC/22012034744481 — CTR RAIN WATER HARVESTING ANGANWADI BHAWAN PER | Closed | 16140.25 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778114 — CTR shokta gadda 11 | Completed | 14467.3 | 9264 | 2021-10-05 | 2022-01-17
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778117 — CTR shokta gadda 12 | Completed | 14467.3 | 9264 | 2021-10-05 | 2022-01-17
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778120 — CTR shokta gadda 13 | Closed | 14467.3 | 0 | 2021-06-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778130 — CTR shokta gadda 14 | Closed | 14467.3 | 0 | 2021-06-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778134 — CTR shokta gadda 15 | Closed | 14467.3 | 0 | 2021-06-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778141 — CTR rain watter harvesting 16 | Closed | 22229.14 | 0 | 2021-06-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034778144 — CTR rain watter harvesting 17 | Closed | 22229.14 | 0 | 2021-06-14
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718006008/WC/22012034800691 — NALA TRENCHING AND CULVERT AT SILODIYA | Completed | 1267028.95 | 1226192 | 2021-08-30 | 2023-01-25
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034837157 — CTR RAIN WATER HARVESTING SILODIYA AANGANWADI BHAWAN PER | Closed | 22229.14 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034837160 — CTR RAIN WATER HARVESTING SILODIYA SCHOOL 1 BHAWAN PER | Closed | 22229.14 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034837161 — CTR RAIN WATER HARVESTING SILODIYA SCHOOL 2 BHAWAN PER | Closed | 22229.14 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848844 — CTR SHOKHTA GADDA 7 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848846 — CTR SHOKHTA GADDA 8 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848848 — CTR SHOKHTA GADDA 9 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848851 — CTR SHOKHTA GADDA 10 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848853 — CTR SHOKHTA GADDA 11 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848856 — CTR SHOKHTA GADDA 12 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848859 — CTR SHOKHTA GADDA 13 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848863 — CTR SHOKHTA GADDA 14 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848869 — CTR SHOKHTA GADDA 15 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848872 — CTR SHOKHTA GADDA 16 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848876 — CTR SHOKHTA GADDA 17 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848879 — CTR SHOKHTA GADDA 18 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848880 — CTR SHOKHTA GADDA 19 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848883 — CTR SHOKHTA GADDA 20 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848885 — CTR SHOKHTA GADDA 21 SILODIYA | Deleted | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848888 — CTR SHOKHTA GADDA 22 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848890 — CTR SHOKHTA GADDA 23 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848897 — CTR SHOKHTA GADDA 24 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848902 — CTR SHOKHTA GADDA 25 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848903 — CTR SHOKHTA GADDA 26 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006008/WC/22012034848905 — CTR SHOKHTA GADDA 27 SILODIYA | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006008/WC/22012034924910 — PDW तालाब जीर्णोद्धार कार्य, खरसौदकलां रास्ते पर, सिलोदिया | Completed | 49000 | 44553 | 2022-03-14 | 2022-11-21
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012034998369 — NALA TRACHING KARYA SILODIYA | Closed | 0 | 0 | 2022-08-15
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1718006008/WC/22012035027897 — संकीर्ण पोंड सिलोदिया खरसोदकला रोड पर | Closed | 0 | 0 | 2022-11-01
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1718006008/WC/22012035027898 — संकीर्ण पोंड सिलोदिया खरसोदकला रोड पर | Completed | 397456.84 | 368012.2 | 2023-06-10 | 2024-03-12
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006008/WC/22012035125435 — Recharge trench silodiya mungawadi ki or | Completed | 320487.81 | 66243 | 2023-10-05 | 2025-06-13
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006008/WC/22012035125449 — sakrin pond silodiya school ki or | Deleted | 493088.52 | 500 | 2023-10-05
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006008/WC/22012035130461 — Recharge trench udsinga 2 | Closed | 0 | 0 | 2023-08-15
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006008/WC/22012035130468 — Recharge trench silodiya 2 | Completed | 313585.9 | 201314 | 2023-10-05 | 2025-05-24
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/22012035179254 — Check dam nirman kanhiyalal gujar ji ke khet ke paas silodiya | Completed | 1139278.64 | 1093611.56 | 2024-03-07 | 2026-03-26
BADNAGAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/7परकोलेशन — परकोलेशन टैंक सिलोदिया (467/10.6.11) | Completed | 218000 | 190764 | 2012-03-12 | 2012-11-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006008/WC/9993663137 — PERCOLATION TANK SILODIYA(TS-235/5.11.15) | Completed | 386000 | 352381 | 2016-01-04 | 2016-10-20
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/22012034151436 — ग्रेवल रोड निर्माण नागदा रोड सिलोदिया से मुंगावदी | Completed | 2352000 | 2618530.81 | 2010-12-30 | 2016-06-22