## Work List
Exported on: 2026-09-02 10:05:38
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: MADHOPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718006013/AV/22012034549166 — SHANTIDHAM ME SHED NIRMAN MADHOPURA | Closed | 0 | 0 | 2020-10-02
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718006013/AV/22012034549203 — KABRISTAN ME SHED NIRMAN MADHOPURA | Completed | 270405.68 | 228540.05 | 2021-02-02 | 2021-12-14
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006013/AV/3682 — Anganwadi/Other Rural Infrastructure,BADNAGAR | Completed | 195000 | 190858 | 2015-09-29 | 2018-07-07
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006013/AV/3684 — Anganwadi/Other Rural Infrastructure,BADNAGAR | Completed | 195000 | 191496 | 2015-09-29 | 2018-07-07
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006013/AV/3685 — Aanganbadi/Other Rural Infrastructure,MADHOPURA | Deleted | 0 | 0 | 2015-04-14
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718006013/DP/22012034614009 — CNG work talab ke pas Madhopura | Closed | 1142221.29 | 0 | 2024-01-26
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1718006013/DP/22012034624662 — सामुदायिक वृक्षा रोपण कार्य शांतिधाम माधोपुरा | Approved | 0 | 0 | 2024-06-14
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006013/DP/22012034625140 — वृक्षा रोपण कार्य शांतिधाम माधोपुरा | Ongoing | 453563.17 | 98518.3 | 2024-11-06
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006013/IF/22012034342739 — VRAKCHAROPAN (KABRISTAN) | Completed | 335000 | 262798 | 2017-06-01 | 2022-11-24
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006013/IF/22012034357508 — VARCHHA ROPAN madhopura2 | Deleted | 335000 | 0 | 2017-08-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035239164 — Nandan Falodhyan Karya Bherulal Kishan ji ke khet par Madhopura | Ongoing | 173308.58 | 60991.56 | 2024-07-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006013/IF/22012035509021 — JGSA 2025 Bherulal pita Gopal ji GP Madhopura | Physically Completed | 55865.38 | 51057 | 2025-05-15 | 2026-03-28
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006013/IF/22012035522195 — JGSA 2025 Sarjubai w/0 Kishore nagar GP Madhopura | Physically Completed | 450885.64 | 399417.71 | 2025-05-17 | 2026-03-28
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006013/IF/22012035541091 — JGSA khet talab nirman karya Rajendra s/0 Pannalal ji Madhopura | Physically Completed | 147621.16 | 127201.05 | 2025-05-25 | 2026-03-28
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035636011 — EK BAGIYA MAA KE NAAM SUGAN BAI UMASHANKAR MADHOPURA SHG CODE 170028588459 | Ongoing | 263511.37 | 54639.62 | 2025-11-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035636014 — EK BAGIYA MAA KE NAAM TARA BAI RAJENDRA MADHOPURA SHG CODE 170028588459 | Ongoing | 263511.37 | 139628.96 | 2025-11-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035636018 — EK BAGIYA MAA KE NAAM RUKHMA BAI RAJENDRA MADHOPURA SHG CODE 170028588459 | Ongoing | 263511.37 | 134357.96 | 2025-11-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006013/IF/22012035648081 — EK BAGIYA MAA KE NAAM SEEMA RAKESH NAGAR MADHOPURA SHG CODE 17005421753 | Deleted | 0 | 0 | 2025-10-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035648082 — EK BAGIYA MAA KE NAAM SEEMA RAKESH NAGAR MADHOPURA SHG CODE 17005421753 | Ongoing | 196660.93 | 67745 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006013/IF/22012035648083 — EK BAGIYA MAA KE NAAM TULSA BAI PANNALAL MADHOPURA SHG CODE 17005421753 | Ongoing | 197235.13 | 92801 | 2025-12-11
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/9993679022 — INDRA AWAS (NANDA BAI W\O BABULAL) | Completed | 14310 | 11832 | 2015-12-20 | 2017-09-19
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/9993679035 — INDRA AWAS (FATA BEE W\O BABU KHA) | Completed | 14310 | 13502 | 2015-12-20 | 2017-09-19
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/9993697668 — INDRA AWAS(RUPA BAI w/o VED PRAKASH | Completed | 14310 | 12024 | 2016-08-02 | 2017-09-19
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/9993752312 — INDRA AWAS (TARA BAI W/O KARULAL) | Completed | 14310 | 13026 | 2016-08-02 | 2017-09-19
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006013/IF/9993752313 — INDRA AWAS (TARA BAI W/O KARULAL) | Deleted | 14310 | 0 | 2015-08-15
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/1848978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5474402 | Completed | 15660 | 15660 | 2018-07-02 | 2018-11-04
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/3695904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106671391 | Completed | 18360 | 18190 | 2022-11-12 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/3874644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145479815 | Completed | 18360 | 17136 | 2022-07-03 | 2022-11-24
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4175183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106678592 | Completed | 18360 | 18360 | 2022-08-24 | 2022-11-24
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4549880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113696428 | Completed | 23490 | 21978 | 2024-10-24 | 2025-12-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4556964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114780899 | Completed | 21870 | 21870 | 2024-11-09 | 2025-03-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4557060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114792485 | Completed | 21870 | 13608 | 2024-10-16 | 2025-02-07
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4559144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114841422 | Completed | 23490 | 22482 | 2024-11-19 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4562525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115673159 | Completed | 21870 | 21627 | 2024-10-17 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4563348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115934167 | Completed | 21870 | 21870 | 2024-11-15 | 2025-03-23
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4563390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115937149 | Completed | 21870 | 21870 | 2024-11-15 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4742420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113701451 | Completed | 21870 | 21870 | 2024-11-15 | 2025-03-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4743885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114831775 | Completed | 23490 | 22986 | 2024-11-18 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4748324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114789060 | Completed | 21870 | 21870 | 2024-12-18 | 2025-02-07
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4793396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145490281 | Completed | 23490 | 22221 | 2024-11-15 | 2025-12-04
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4847837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115947437 | Completed | 21870 | 21870 | 2024-11-15 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4873690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127971873 | Completed | 23490 | 22248 | 2025-01-17 | 2026-02-24
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/4881508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145497475 | Completed | 23490 | 22986 | 2025-01-09 | 2026-02-24
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/92957 — Construction of IAY House -IAY REG. NO. MP-18-006-013-001/33 | Approved | 27000 | 0 | 2015-07-15
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006013/IF/IAY/93704 — Construction of IAY House -IAY REG. NO. MP-18-006-013-001/31 | Approved | 27000 | 0 | 2015-10-01
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034169280 — CC ROAD NALI NIRMAN HAJI MOHALLA(T/S 1094 27/02/20 | Completed | 197830 | 189714 | 2013-05-28 | 2016-07-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034204690 — cc road pp+m pradhanmantri sadak vijay(t/s237/28/1 | Completed | 197000 | 186484 | 2014-02-14 | 2016-06-17
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006013/RC/22012034217795 — khetsadak gendalal pirkha khet(ts 563/29/01/2014) | Completed | 1391400 | 923703.5 | 2014-05-09 | 2017-02-23
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034219428 — विजय नगर से PWD रोड की ओर (ts 11/19/05/2014) | Completed | 200000 | 127245 | 2014-05-30 | 2016-06-17
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034263998 — cc road+nali nirman pp+m chitu kha se pipali chouk tak | Deleted | 167000 | 0 | 2016-01-01
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1718006013/RC/22012034264518 — Nali nirman (CC) रतलाम बडनगर रोड से गाव की ओर | Completed | 489333 | 155426 | 2016-01-15 | 2017-10-06
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034295370 — CC +NALI CHITU KHA KE GHAR SE PIPLI(TS-162/13.10.15) | Completed | 167000 | 116700 | 2016-01-06 | 2017-10-06
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034295385 — CC ROAD+nali nirman prathmik sala se premnarayan ke ghar tak | Completed | 272000 | 240427.4 | 2016-01-15 | 2018-06-01
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034295388 — cc road+nali nirman ismail haji ke ghar se motilal ke ghar tak t/s 981/26.12.15 sv+m | Completed | 221000 | 197549 | 2016-01-15 | 2017-10-06
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034298530 — CC ROAD+NALI PP+M JAMAT KHANE SE MANDIR KI OR | Completed | 193000 | 56703 | 2016-02-15 | 2018-03-07
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034302150 — CC ROAD+NALI YUNUS KE GHAR SE DHARMSALA KI OR | Completed | 75000 | 53484 | 2017-03-20 | 2018-06-27
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034323211 — cc road+nali nirman | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034349418 — CC ROAD+NALI CHAMPA KE GHAR SE LIYAKAT KE GHAR TAK | Completed | 42000 | 17888 | 2017-08-16 | 2018-07-17
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034349424 — CC+NALI BHARAT SINGH KE GHAR SE SHOKAT KE GHAR TAK | Completed | 16000 | 12212 | 2017-08-16 | 2018-07-07
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034349427 — CC ROAD+NALI BABU NETA KE GHAR SE SATTAR SULEMAN KE GHAR KI OR | Completed | 29000 | 22532 | 2017-08-16 | 2018-07-07
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034353436 — CC ROAD+NALI NIRMAN HAJI KHAJU KE GHAR SE HASAN JI KE GHAR TAK | Completed | 9000 | 5504 | 2017-09-14 | 2017-10-30
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034361450 — CC+nali nirman madrase se fata bee ki or | Completed | 36000 | 34916 | 2017-09-27 | 2018-02-09
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034366987 — CC+NALI NIRMAN ANSAR KE GHAR SE USMAN KE GHAR TAK | Completed | 27000 | 24768 | 2017-11-16 | 2018-02-09
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034371103 — सीसी रोड +नाली | Deleted | 0 | 0 | 2018-04-01
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034385066 — CC+NALI NIRMAN BHANJI KE GHAR SE PWD ROAD TAK | Completed | 23000 | 3132 | 2018-06-15 | 2018-06-27
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034387920 — CC+NALI NIRMAN BHERU KE GHAR SE BHURALAL KE GHAR TAK | Completed | 27000 | 3132 | 2018-06-15 | 2018-06-30
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034395212 — CC+NALI NIRMAN PREMNARAYAN KE GHAR SE HUSEN KE GHAR KI OR | Completed | 98000 | 96570 | 2018-10-02 | 2019-02-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034395239 — CC+NALI NIRMAN PANCHAYAT BHAWAN SE SHOKAT SULEMAN KE GHAR KI OR | Completed | 133000 | 130674 | 2018-10-02 | 2019-02-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034433697 — cc road nirman शासकीय मा.वि.माधोपुरा | Completed | 24300 | 22968 | 2019-01-06 | 2019-02-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034433701 — cc road nirman शासकीय प्रा.वि.माधोपुरा | Completed | 80000 | 78300 | 2019-01-06 | 2019-03-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034434628 — सीसी रोड निर्माण रहमत अली के घर से भेरुलाल किशनलाल के घर तक | Completed | 115000 | 111708 | 2019-01-09 | 2019-03-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034437486 — CC ROAD NIRMAN PWD ROAD SE ALLANUR KE GHAR KI OR | Completed | 115000 | 113100 | 2019-01-29 | 2019-03-26
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034440176 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034445822 — C.C. रोड निर्माण भेरू के घर से मोहन के घर कि ओर | Physically Completed | 115000 | 20854 | 2019-03-01 | 2021-09-20
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034482846 — सीसी रोड नाली निर्माण शा.मा. विद्यालय नविन शाला भवन के सामने | Physically Completed | 160000 | 34848 | 2019-10-19 | 2019-12-10
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034551365 — C C ROAD NIRMAN PURANI FATAK SE SAMSHAN TAK | Completed | 164000 | 79794 | 2020-12-04 | 2023-04-22
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034551376 — C C ROAD NIRMAN MEN ROAD SE KABRISTAN TAK | Completed | 102000 | 99204 | 2020-12-04 | 2022-01-01
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034552004 — CC ROAD NALI NIRMAN SIKANDER KE GHAR SE RAM RATAN KE GHAR TAK | Completed | 116000 | 58429 | 2020-12-07 | 2022-01-17
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034628675 — CC + NALI NIRMAN RAVI KE GHAR SE VISHNU KE GHAR KI OUR | Completed | 36000 | 35866 | 2023-05-10 | 2024-05-15
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034628676 — CC + NALI NIRMAN MURLI KE GHAR SE RAVI KE GHAR KI OUR | Completed | 55000 | 54992 | 2023-05-03 | 2024-05-15
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034637547 — CC ROAD NALI NIRMAN KARYA BHERULAL KE GHAR SE ARJUN NAGAR KE GHAR TAK | Completed | 24000 | 23647 | 2023-09-27 | 2024-06-09
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034637550 — CC ROAD NALI NIRMAN ASHOK KE GHAR SE DASHRATH KE GHAR KI OR | Completed | 61000 | 60763 | 2023-07-05 | 2024-06-09
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034663691 — C C ROAD + NALI NIRMAN किशोर के घर से लाखन के घर तक | Completed | 67000 | 65195 | 2023-10-06 | 2024-07-18
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034663718 — C C ROAD + NALI NIRMAN विष्णु के घर से पंकज के घर की ओर | Completed | 49000 | 46631 | 2023-10-06 | 2024-07-18
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034829902 — cc road nali nirmand ambaram k ghar se gopal k ghar madhopura (5 va vitt) | Completed | 80000 | 79288.42 | 2025-01-02 | 2026-02-25
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034829906 — cc road nali nirmand kailash k ghar se dashrath k ghar madhopura | Completed | 94000 | 93814.74 | 2025-03-07 | 2026-02-25
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034831374 — cement concret ki nali nirmand masjid se lagakr yunush k ghar ki or madhopura | Approved | 84000 | 0 | 2024-10-02
BADNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/22012034843556 — cement concret road nali nirmand tejajaji mandir se revashankar k har ko or madhopura | Completed | 126000 | 124756.9 | 2025-07-25 | 2026-02-25
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006013/RC/27माधोपुरा — माधोपुरा शांतिधाम (64/16.4.11) | Completed | 173000 | 117436 | 2011-05-03 | 2013-03-27
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/34C.C. Roa — C.C. Road Naali Nirman PP+M Piple choke se Shalabhawan(T/S171/27.01.2012) | Deleted | 0 | 0 | 2012-01-26
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/35C.C. Roa — C.C. Road Naali Nirman PP+M MADHAVPURA Shala tak (T/S171/27.01.2012) | Completed | 507500 | 178146 | 2012-04-12 | 2013-03-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006013/RC/35सी सी रो — सी सी रोङ एवं नाली fनमाण Madhopura से Runija marg PP+M (T/s 633/10.10.2012) | Completed | 197830 | 106000 | 2012-12-12 | 2015-04-02
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | School Toilet Units / Construction of Multi Unit Toilets for School | Construction of Toilets | 1718006013/RS/22012034293603 — SAMUDAYAK SHOCHALAY MADHPURA(TS-984/26.12.15) | Deleted | 191000 | 0 | 2015-12-21
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012034438329 — NALI NIRMAN VAKIL KE GHAR SE NAHAR KHA KE GHAR TAK | Completed | 14000 | 13008 | 2019-02-26 | 2021-08-12
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012034438330 — NALI NIRMAN NIYAJ KE GHAR SE DILAVAR KHA KE GHAR KI OR | Completed | 2550 | 1044 | 2019-02-26 | 2019-11-30
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006013/RS/22012034681196 — सामुदायिक स्वछता परिसर निर्माण माधोपुरा | Completed | 47000 | 45630 | 2022-12-27 | 2024-05-15
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035131040 — nali nirmand nurhusan k ghar se fidahusan k ghar madhopura | Approved | 88000 | 0 | 2024-06-08
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035131041 — nali nirmand laxman k ghar se isarail k ghar ki or madhopura | Deleted | 0 | 0 | 2024-06-08
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035131042 — nali nirmand laxman k ghar se isarail k ghar ki or madhopura | Deleted | 0 | 0 | 2024-06-08
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035131043 — nali nirmand laxman k ghar se isarail k ghar ki or madhopura | Approved | 88000 | 0 | 2024-06-08
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035134374 — nali nirmand vakil k ghar se kudarat k ghar ki or madhopura | Completed | 84000 | 83821.65 | 2025-01-24 | 2026-02-20
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006013/RS/22012035134376 — nali nirmand masjid se lagakr yunush k ghar ki or madhopura | Completed | 84000 | 83957.04 | 2025-01-30 | 2026-02-20
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034481072 — Recharge pit hand pump missile school ke samne | Completed | 10857.75 | 9206 | 2019-08-18 | 2021-12-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034481076 — Recharge pit hand pump aangan wadi ke samne | Completed | 10857.75 | 9196 | 2019-08-18 | 2022-02-10
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034481081 — Recharge pit hand pump kbristan ke samne | Completed | 10857.75 | 9196 | 2019-08-18 | 2022-11-28
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034481084 — Recharge pit hand pump ibrahim be ke ghar ke samne | Completed | 10857.75 | 9196 | 2019-08-18 | 2022-11-24
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034481086 — Recharge pit hand pump miru ke ghar ke samne | Completed | 10857.75 | 9196 | 2019-08-18 | 2022-11-28
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1718006013/WC/22012034579884 — nala trenching work ishak ke khet se talab tak | Completed | 239443.14 | 199092 | 2021-02-18 | 2023-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718006013/WC/22012034833338 — sokhta gadda madhopura kabristan 1 | Completed | 5718.26 | 386 | 2021-10-04 | 2022-02-20
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718006013/WC/22012034833344 — sokhta gadda madhopura kabristan 2 | Completed | 5718.26 | 193 | 2021-10-05 | 2022-01-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718006013/WC/22012034833357 — ROOF WATER HARWESTING MADHOPURA AANGANWADI 1 | Completed | 16878.31 | 10741 | 2021-10-01 | 2022-09-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718006013/WC/22012034833363 — ROOF WATER HARWESTING MADHOPURA AANGANWADI 2 | Completed | 16878.31 | 9985 | 2021-10-01 | 2022-09-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844797 — सोखता गड्ढा निर्माण टंकी के सामने माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844807 — सोखता गड्ढा निर्माण मिडिल स्कूल के पीछे माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844820 — सोखता गड्ढा पंचायत भवन के सामने माधोपुरा | Completed | 14467.3 | 10422 | 2022-02-18 | 2022-03-31
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844834 — सोखता गड्ढा निर्माण एसाद छीतू माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844841 — सोखता गड्ढा निर्माण शाहरुख फकरुद्दीन माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844850 — सोखता गड्ढा निर्माण राशिद रईस माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844862 — सोखता गड्ढा निर्माण सत्तार कासम माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006013/WC/22012034844884 — सोखता गड्ढा निर्माण अमजद शाह मोहब्बत माधोपुरा | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1718006013/WC/22012034908622 — Nala trenching ajabnur patel ke khet se talab ki or | Completed | 169413.12 | 142253 | 2022-02-21 | 2023-04-14
BADNAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1718006013/WC/22012034910977 — sankirn pond salim ke khet ke samne | Deleted | 0 | 0 | 2022-01-27
BADNAGAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1718006013/WC/22012034910980 — sankirn pond salim ke khet ke samne | Completed | 235296 | 197392 | 2022-02-21 | 2024-07-31
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006013/WC/22012034923986 — PDW तालाब जीर्णोद्धार कार्य, हुण्डीवाला तालाब माधोपुरा | Completed | 28000 | 27645 | 2022-03-12 | 2023-07-07
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006013/WC/22012034943917 — अमृत सरोवर योजना अंतर्गत संकीर्ण पोंड माधोपुरा | Completed | 1250537.28 | 500412 | 2022-05-07 | 2024-06-09
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1718006013/WC/22012034957308 — Talab jirnoddhar bheruji | Deleted | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006013/WC/22012034968740 — TALAB JIRNOUDDAR KARY ,BHERU JI VALA TALAB | Deleted | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006013/WC/22012034968741 — TALAB JIRNOUDDAR KARY ,BHERU JI VALA TALAB | Completed | 47000 | 46716 | 2022-05-20 | 2022-11-24
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006013/WC/22012035125188 — sakrin pond madhopura adawa 1 | Completed | 389481.4 | 338080 | 2023-10-06 | 2025-05-02
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006013/WC/22012035125197 — sakrin pond madhopura adawa 2 | Physically Completed | 389481.4 | 212839 | 2023-12-02 | 2026-04-01
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006013/WC/22012035210218 — NALA TRANCHING GORDHAN SINGH KE KHET SE KHACHROD CHOURAHA KI OR | Approved | 0 | 0 | 2024-04-14
BADNAGAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006013/WC/7परकोलेशन — परकोलेशन टैंक माधोपुरा (425/25.5.11) | Completed | 354000 | 345062 | 2011-06-08 | 2013-03-27
BADNAGAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006013/WC/9993652487 — पर्कुलेशन टेंक {भेरू जी } | Completed | 383049 | 270825 | 2014-05-30 | 2015-06-04