## Work List
Exported on: 2026-09-10 03:12:30
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: SUNDRABAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1718006015/AV/22012034584753 — DINING HALL WORK MIDDLE SCHOOL SUNDRABAD | Closed | 0 | 0 | 2021-06-05
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1718006015/AV/22012034584757 — DINING HALL WORK MIDDLE SCHOOL SUNDRABAD | Closed | 16093.2 | 0 | 2021-06-05
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034598013 — DINING HALL WORK PRIMERY SCHOOL SUNDRABAD | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617618 — पंचायत भवन सुंदराबाद | Completed | 1000000 | 984450.33 | 2022-11-15 | 2026-03-05
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617619 — पंचायत भवन | Deleted | 0 | 0 | 2022-04-01
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617620 — पंचायत भवन | Deleted | 0 | 0 | 2022-04-01
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617621 — पंचायत भवन | Deleted | 0 | 0 | 2022-04-01
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617622 — पंचायत भवन | Deleted | 0 | 0 | 2022-04-01
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006015/AV/22012034617623 — पंचायत भवन | Deleted | 0 | 0 | 2022-04-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718006015/DP/22012034445093 — पेय जल कूप निर्माण निर्मल नीर सुंदराबाद | Deleted | 535000 | 4176 | 2019-03-11
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1718006015/DP/22012034533523 — वृक्षारोपण सामुदिक पानी की टंकी के पास | Closed | 117912.51 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006015/DP/22012034546281 — NUTRATION GUARDEN aaganwadi ke paas suneda | Closed | 0 | 0 | 2022-01-26
BADNAGAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006015/DP/2सुन्‍दराब — सुन्‍दराबाद व़क्षारोपण शा गोया के पश्चिम में | Completed | 492000 | 23742 | 2009-06-07 | 2011-05-12
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006015/DP/जेटरोपा रोपण गांव के पश्चिम में सुन् — जेटरोपा रोपण गांव के पश्चिम में सुन्‍दराबाद | Completed | 351400 | 33184 | 2008-07-22 | 2011-05-12
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006015/DP/मेड्बन्धान कार्य सुन्दराबाद — मेड्बन्धान कार्य सुन्दराबाद | Completed | 2440 | 5470 | 2008-10-10 | 2011-05-12
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654013 — Sokta gaddhasundrabad TS58/12.6.15/1 | Deleted | 6500 | 0 | 2015-06-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654014 — Sokta gaddha sundrabad TS 58/12.6.15 /2 | Deleted | 6500 | 0 | 2015-06-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654015 — Sokta gaddha sundrabad TS 58/12.6.15/3 | Deleted | 6500 | 0 | 2015-06-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654016 — Sokta gaddhasundrabad TS 58/12.6.15/4 | Deleted | 6500 | 0 | 2015-06-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654017 — Sokta gaddha sundrabad TS58/12.6.15/5 | Deleted | 0 | 0 | 2015-06-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/DW/9993654135 — SOKHTA GADDA SUNDRABAD TS58/12/06/2015/UNIT 5 | Completed | 32500 | 30639.55 | 2015-07-03 | 2016-05-28
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718006015/FP/22012034641505 — cici rod puliyavali ghathi | Approved | 0 | 0 | 2024-08-16
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718006015/FP/22012034641506 — naali nirman gram aabadi | Approved | 0 | 0 | 2024-08-16
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718006015/FP/22012034641508 — naali nirman gram aabadi | New | 0 | 0 | 2024-08-16
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718006015/FP/22012034641509 — naali nirman gram aabadi | Approved | 0 | 0 | 2024-08-16
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1718006015/FR/22012034323844 — community pond sundrabad | Completed | 447235.49 | 371723.69 | 2025-02-25 | 2025-05-30
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1718006015/IF/1000066363 — murgi aasray bharata(ts260) | Deleted | 19845 | 0 | 2014-02-07
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1718006015/IF/1000066694 — murgi ashray rama ji (ts-261/30/12/2013) | Deleted | 19845 | 0 | 2014-02-07
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1718006015/IF/1000066712 — murgi ashray ramchandra (ts-262/30/12/2013 | Deleted | 19845 | 0 | 2014-02-07
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1718006015/IF/1000066718 — murgi ashray pirulal (ts-263/30/12/2013 | Deleted | 19845 | 0 | 2014-02-07
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1718006015/IF/1000066772 — murgi ashray vasudev (ts-264/30/12/2013 | Deleted | 19845 | 0 | 2014-02-07
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1718006015/IF/22012034308416 — nadep sundrabad | Deleted | 0 | 0 | 2016-10-02
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006015/IF/22012034332748 — IAY RAJUBAI RAJARAM | Completed | 15030 | 15136 | 2017-04-11 | 2017-08-31
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006015/IF/22012034342075 — wraksha ropan samudayik (shantidham,pani ki tanke ke pass) sundrabad | Completed | 335000 | 6477 | 2017-05-23 | 2020-09-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/9993678816 — IAY PATWATI BAI INDERLAL | Completed | 14310 | 13884 | 2015-10-19 | 2016-09-01
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/9993679510 — IAY SAMPATBAI BABULAL | Completed | 14310 | 14051 | 2015-10-19 | 2016-09-01
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006015/IF/9993692449 — PASHU SHED NIRMAN DILIPSINGH-RANCHODSINGH | Completed | 100000 | 75061.3 | 2015-12-06 | 2016-10-23
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006015/IF/9993692986 — PASHU SHED+NADEP madansingh-kalusingh | Completed | 100000 | 79522.46 | 2016-01-09 | 2016-10-23
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006015/IF/9993692990 — PASHU SHED+NADEP mahesh-gopal | Completed | 100000 | 79955.8 | 2016-01-09 | 2016-10-23
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/273852 — Construction of IAY House -IAY REG. NO. MP3109698 | Completed | 15030 | 14696 | 2017-01-23 | 2017-08-31
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3672599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106955472 | Completed | 18360 | 18156 | 2022-09-11 | 2023-09-04
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3672639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106957604 | Completed | 18360 | 18262 | 2022-12-07 | 2023-09-04
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3688183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113760754 | Completed | 18360 | 18241 | 2022-09-11 | 2023-09-15
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3688221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763393 | Completed | 18360 | 18284 | 2022-09-13 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3696635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114740055 | Completed | 18360 | 18156 | 2022-09-11 | 2023-04-15
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3738454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125360710 | Completed | 18360 | 18360 | 2022-10-13 | 2023-04-11
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3742207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118156320 | Completed | 18360 | 18088 | 2023-01-10 | 2023-10-10
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3742235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118160237 | Completed | 18360 | 18274 | 2022-09-10 | 2023-09-15
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3742251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118163223 | Completed | 18360 | 18241 | 2022-12-07 | 2023-09-15
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/3822905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117409637 | Completed | 18360 | 19227 | 2023-02-25 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4175870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055734 | Completed | 18360 | 17476 | 2022-10-13 | 2024-01-30
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4248145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117907738 | Completed | 18360 | 18212 | 2022-12-07 | 2023-09-15
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4696862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117410172 | Completed | 23490 | 22014 | 2024-11-14 | 2026-03-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4696885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117418479 | Completed | 23490 | 21996 | 2024-11-14 | 2026-03-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4697165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115031835 | Completed | 21870 | 20169 | 2024-11-14 | 2026-07-30
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4697169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115033823 | Completed | 23490 | 20412 | 2024-11-14 | 2026-07-30
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4697173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115038760 | Completed | 23490 | 21843 | 2024-12-18 | 2026-03-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4708431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125082620 | Completed | 23490 | 20538 | 2024-12-18 | 2026-07-30
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4742955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113757380 | Completed | 23490 | 22230 | 2024-12-18 | 2026-03-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4753297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118151904 | Completed | 23490 | 21996 | 2024-11-14 | 2026-03-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4755347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118037128 | Completed | 23490 | 20538 | 2024-12-18 | 2026-07-30
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/4755394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118050695 | Completed | 23490 | 20538 | 2024-12-18 | 2026-07-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5245697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120839268 | Completed | 23490 | 23490 | 2025-08-26 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5248070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125531238 | Completed | 23490 | 23490 | 2025-06-27 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5251246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117415743 | Completed | 23490 | 23490 | 2025-06-27 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5251249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118044104 | Completed | 23490 | 23490 | 2025-07-11 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5252799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117417530 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5259020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117410836 | Ongoing | 27000 | 19575 | 2026-02-12
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5261556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117414514 | Physically Completed | 23490 | 21924 | 2026-05-01 | 2026-06-28
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5263466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114757389 | Approved | 27000 | 0 | 2025-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5263933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118152351 | Physically Completed | 23490 | 12528 | 2026-02-11 | 2026-03-22
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5265358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422710 | Physically Completed | 23490 | 14616 | 2026-05-24 | 2026-08-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5271000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117429615 | Physically Completed | 23490 | 23490 | 2026-02-02 | 2026-04-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5276773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118176643 | Completed | 23490 | 23490 | 2025-07-11 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5277838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113753214 | Ongoing | 27000 | 14616 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5281662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117421794 | Completed | 23490 | 23229 | 2025-07-11 | 2026-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5288762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117416707 | Completed | 23490 | 23490 | 2025-06-26 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5293840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114747719 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-04
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5293926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119564328 | Approved | 27000 | 0 | 2025-02-25
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5297415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117902974 | Approved | 27000 | 0 | 2025-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5299579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114099548 | Completed | 23490 | 23490 | 2025-06-25 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5300284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114098291 | Physically Completed | 23490 | 15660 | 2026-02-11 | 2026-08-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5300413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118035134 | Completed | 23490 | 23490 | 2025-07-09 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5303128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117429265 | Physically Completed | 23490 | 23229 | 2026-02-02 | 2026-05-03
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5307007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118031418 | Ongoing | 27000 | 4200 | 2025-02-25
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5309213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115035473 | Completed | 23490 | 21924 | 2025-07-11 | 2026-07-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5309501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117905640 | Completed | 23490 | 23490 | 2025-05-03 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5309862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118052392 | Completed | 23490 | 23490 | 2025-05-28 | 2026-02-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5315110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117407438 | Approved | 27000 | 0 | 2025-02-25
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5315529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117408947 | Physically Completed | 23490 | 23229 | 2025-06-26 | 2026-01-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5315775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121357528 | Completed | 23490 | 21924 | 2025-05-28 | 2026-07-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5316614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117420684 | Completed | 23490 | 23490 | 2025-05-03 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5321878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877751 | Completed | 23490 | 22968 | 2025-05-03 | 2026-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5323752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118166707 | Completed | 23490 | 23490 | 2025-06-26 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5326887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114096023 | Completed | 23490 | 23490 | 2025-05-03 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5327850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120896865 | Completed | 23490 | 23490 | 2026-01-01 | 2026-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5327910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118038472 | Completed | 23490 | 23490 | 2025-07-11 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5329623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114733001 | Completed | 23490 | 23490 | 2025-05-22 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5332692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115036836 | Completed | 23490 | 23490 | 2025-05-03 | 2026-02-04
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5333212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114742942 | Ongoing | 27000 | 4800 | 2025-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5337003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120900935 | Completed | 23490 | 23490 | 2025-06-13 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5342551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118032632 | Completed | 23490 | 23490 | 2025-07-11 | 2026-02-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5490464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118177201 | Completed | 23490 | 23490 | 2025-06-26 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5493138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118151651 | Physically Completed | 23490 | 21141 | 2026-03-06 | 2026-06-28
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5495172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117900090 | Completed | 23490 | 22446 | 2025-05-22 | 2026-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5576939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125081106 | Completed | 23490 | 23490 | 2025-11-14 | 2026-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5576967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127934679 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5577868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117910984 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5615601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117428086 | Completed | 23490 | 23490 | 2025-08-26 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5667912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115041058 | Physically Completed | 23490 | 23490 | 2026-02-11 | 2026-05-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5668036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117408393 | Physically Completed | 23490 | 23490 | 2025-11-13 | 2026-01-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5668644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125315513 | Physically Completed | 23490 | 21924 | 2025-09-26 | 2026-05-17
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5702099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106963723 | Approved | 27000 | 0 | 2025-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5702818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120846216 | Physically Completed | 23490 | 23490 | 2026-02-06 | 2026-06-07
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5769897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117423530 | Physically Completed | 23490 | 23229 | 2025-11-13 | 2026-05-17
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5881783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115102607 | Physically Completed | 23490 | 23490 | 2026-02-12 | 2026-03-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006015/IF/IAY/5882044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106960197 | Physically Completed | 23490 | 12006 | 2026-02-11 | 2026-03-15
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006015/LD/11ग्रामीण — ग्रामीण क्रिडागन समतलीकरण एवं CPT (T/S299/19.05.2011) | Completed | 164000 | 163645 | 2012-05-22 | 2013-10-05
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034186420 — CC ROAD+NALI NAYI AABADI NAT MOHALLA(TS-80/18.7.13 | Completed | 175000 | 92044 | 2013-09-29 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006015/RC/22012034214072 — GRAVEL ROAD kachhi vadoda marg(ts-403/24.01.2014) | Completed | 1387000 | 1281667.3 | 2014-03-13 | 2016-11-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034264219 — cc road +nali nirman | Deleted | 2000 | 0 | 2017-03-17
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034264623 — cc rod+nali nirman mn+pp2 gram abadi sundrabad | Closed | 0 | 0 | 2014-10-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034301833 — cc rod | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034301834 — cc rod | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034322584 — CC ROAD AND NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034324940 — CC ROAD+NALI NIRMAN BHATT JI KE GHAR SE PRADHANMANTRI SADAK TAK | Deleted | 0 | 0 | 2016-11-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034324941 — CC ROAD+NALI NIRMAN BHATT JI KE GHAR SE PM SADAK TAK | Completed | 48000 | 20160 | 2017-02-04 | 2018-07-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034327946 — CC ROAD + NALI NIRMAN GAJENDRA KE GHAR SE PM ROAD TAK | Completed | 24000 | 27049.2 | 2017-02-22 | 2018-01-04
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034331107 — cc rod+nali nirman subhash ji ke ghar se pradhanmantri rod tak | Completed | 6000 | 4736 | 2017-03-15 | 2018-07-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034331109 — cc rod+nali nirman basanti lal ke ghar se hendpamp tak | Completed | 8000 | 6800 | 2017-03-15 | 2017-10-30
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034331112 — cc rod+nali nirman mukesh ji ke ghar se pradhanmantri rod tak | Completed | 14000 | 13694 | 2017-03-15 | 2018-01-04
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034332195 — cc rod+nali nirman pawan ji ke ghar se pankaj ji ke ghar tak | Completed | 29500 | 28056 | 2017-03-21 | 2017-10-30
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034371139 — सीसी रोड +नाली | Closed | 0 | 0 | 2018-04-01
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034396480 — सीसीरोड +नालीनिर्माण भारत परमार के घर से रामदेव जी के मंदिर तक तक | Completed | 18000 | 18984 | 2019-03-11 | 2021-09-23
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034396481 — सीसीरोड +नालीनिर्माण भोम सिह के घर से नाले तक | Completed | 7000 | 6288 | 2019-03-11 | 2021-09-23
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034440178 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034463242 — ccrode+naliniman (menrode se puliya tak ) | Completed | 39000 | 37968 | 2019-03-11 | 2021-09-01
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034550360 — ccrode+nalinirman(men rod se yaswant singh ji ke ghar tak) | Closed | 41000 | 0 | 2020-04-01
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006015/RC/22012034637279 — Sudur sadak main road se amrit sarowar tak gp sundrabad | Completed | 2499775.01 | 2486093.81 | 2023-07-01 | 2026-08-30
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034830503 — CC ROAD NIRMAN SCHOOL VALI GHATI | Approved | 29000 | 0 | 2024-10-02
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034835602 — CC ROAD RAMDEVJI VALI GALI SUNDRABAD | Completed | 39000 | 38998.44 | 2025-02-25 | 2026-03-13
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034835677 — nali nirman bairagi mohlla | Completed | 29000 | 27998.28 | 2025-02-26 | 2026-03-13
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034835681 — nali nirman mehrban ke ghar se sanjay ke ghar tak | Ongoing | 19000 | 18499.39 | 2025-02-28
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/22012034835977 — cici rode nirman midil school ke pass | Ongoing | 29000 | 28399.8 | 2025-02-28
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/28 — सीमेन्‍ट कांक्रीट (08/20.1.11) | Completed | 200000 | 198662 | 2011-05-20 | 2012-06-29
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006015/RC/28शांतिधाम — शांतिधाम समतलीकरण एवं टैंच खुदाई (298/19.5.11) | Completed | 164000 | 158311 | 2011-06-01 | 2012-06-29
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/33सी सी रो — सी सी रोङ व नाली P.P+ M.‍िनमाण मेन रोङ से पंशा भवन सुन्‍दराबाद(529/14.03.2012) | Completed | 284000 | 172144 | 2012-05-21 | 2013-10-05
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/35सी सी रो — सी सी रोङ नाली स‍हीत ‍िव+म SUNDRABAD RAMESHWER WALI GALI (492/05.03.2012) | Completed | 175000 | 75408 | 2013-01-05 | 2013-03-26
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006015/RC/36सी सी रो — 1718006015/RC/36सी सी रो | Completed | 197830 | 197084 | 2013-02-28 | 2013-11-07
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006015/RC/अर्थवर्क सुन्‍दराबाद से पिटलावदिया स — अर्थवर्क सुन्‍दराबाद से पिटलावदिया सुन्‍दराबाद | Completed | 509920 | 508830 | 2008-09-18 | 2010-09-28
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006015/RS/22012034308575 — swachh bharat abhiyan sundrabad unit8 | Completed | 86400 | 82379 | 2016-12-01 | 2018-04-24
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006015/RS/22012034312813 — Nadep compost pit nirman work unit 02 | Completed | 24400 | 1989.9 | 2016-12-24 | 2018-04-24
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006015/RS/22012034333851 — NADEEP WARMI CAMOST SAMUDAYIK SUNDRABAD | Completed | 73200 | 7642 | 2017-03-21 | 2018-07-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006015/RS/22012034334685 — swah bharat abhiyan sochalay unit5 sundrabad | Completed | 54000 | 52520 | 2017-03-23 | 2018-04-24
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006015/RS/22012034687156 — नाली निर्माण ग्राम पंचायत सुंदराबाद | Closed | 0 | 0 | 2022-11-16
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1718006015/RS/22012034687416 — समुदायक शोचालय निर्माण | Closed | 47000 | 0 | 2023-01-22
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006015/RS/22012034698527 — सामुदायिक स्वच्छता परिसर सुंदराबाद | Completed | 47000 | 46480 | 2023-07-17 | 2024-06-14
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006015/RS/22012034700514 — Nali nirman gav aabadi me sundrabad | Ongoing | 20000 | 19476 | 2024-03-13
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006015/RS/22012035124999 — नाली निर्माण गाव आबादी ( प्राथमिक शाला से गाव आबादी तक ) | Ongoing | 23000 | 22984 | 2024-03-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006015/RS/29408 — NIRMAL BHARAT BHARAT JAGANNATH(A/S 101 14/04/2013) | Completed | 4312 | 1752 | 2013-06-06 | 2014-05-28
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034427055 — MWC चेक डेम एवं नाला ट्रेचिंग कार्य (गोया में ) | Completed | 803000 | 760008.9 | 2018-12-22 | 2019-08-16
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034438446 — Cehk D.0am Nirman | Closed | 0 | 0 | 2018-04-14
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034438740 — CHECK DEM AND NALA TRENCHING KARYA SUNDRABAAD | Completed | 747900 | 731829 | 2019-02-22 | 2021-12-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480239 — रिचार्ज पिठ handpump ps ( शा.मा.वि.के पास ) | Completed | 10857.75 | 1204 | 2019-08-18 | 2022-01-11
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480241 — रिचार्ज पिठ handpump ps (शा.प्रा.वि.के पास ) | Completed | 10857.75 | 1204 | 2019-08-18 | 2022-01-01
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480243 — रिचार्ज पिठ handpump ps (शा.प्रा.वि.के पास ) | Closed | 10857.75 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480244 — रिचार्ज पिठ handpump ps (रामचंद्र शिकारी के घर के पास ) | Completed | 10857.75 | 1204 | 2019-08-18 | 2022-01-01
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480245 — रिचार्ज पिठ handpump ps (यशवंत जी के घर के पास ) | Completed | 10857.75 | 1204 | 2019-08-18 | 2022-01-01
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034480248 — रिचार्ज पिठ handpump ps (भेरुनाथ के घर के पास ) | Completed | 10857.75 | 1204 | 2019-08-18 | 2022-01-01
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1718006015/WC/22012034516417 — chekdem nala tranching hanuman mandir se aage nale par sundarabad | Deleted | 0 | 0 | 2019-10-02
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1718006015/WC/22012034521974 — NALA TRANCHING MAIN ROAD SE KRASHNA JI KHET TAK | Deleted | 292974.66 | 0 | 2019-10-02
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1718006015/WC/22012034526830 — MWC NALA TRANCHING BALWANT KE KHET SE RAM LAL KE KHET TAK | Closed | 0 | 0 | 2020-01-26
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1718006015/WC/22012034551571 — naalatraching (balwant ke khet ke pass) | Completed | 751054.68 | 743699 | 2020-05-24 | 2021-12-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034551575 — chekden nala treching (basantilal ke khet ke pass) | Completed | 1117262.28 | 1086903 | 2020-11-18 | 2021-08-11
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034579720 — chekdem aur nalatreching(badi pul ke pass) | Completed | 1496332.68 | 1465787.15 | 2021-03-03 | 2023-04-22
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1718006015/WC/22012034580989 — nala trenching work near vijay bahadur khet | Completed | 224534.72 | 215625 | 2020-12-31 | 2022-09-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1718006015/WC/22012034602082 — chekdem aur nalatreching(badi pul ke pass) | Closed | 0 | 0 | 2020-04-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006015/WC/22012034739184 — संकीर्णपौण निर्माण (मदन सिंह जी के खेत के पास ) | Completed | 1465510.08 | 1298058 | 2021-10-18 | 2024-03-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744142 — sokhta gaddha primery school ke paas | Closed | 5718.26 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744151 — CTR sokhta gaddha primery school ke paassarpanch sahab ke ghar ke paas sundrabad | Closed | 5718.26 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744176 — CTR sokhta gaddha PEERALAL KE GHAR KE PAAS sundrabad | Closed | 5718.26 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744180 — CTR sokhta gaddha AMARNATH KE GHAR KE PAAS sundrabad | Closed | 5214.62 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744186 — CTR SOKHTA GADDHA MORI KUI SUNDRABAAD | Closed | 5718.26 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034744196 — CTR ROOF HARVESTING MANGLIK BHAWAN SUNDRABAD | Closed | 16878.31 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718006015/WC/22012034744200 — CTR ROOF HARVESTING ANGANWADI BHAWAN 1 SUNDRABAD | Closed | 16878.31 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845587 — सोख्ता गड्डा(प्रदीप जी के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845622 — सोख्ता गड्डा(श्याम के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845710 — सोख्ता गड्डा(इन्दर के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845743 — सोख्ता गड्डा(भेरू प्रजापत के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845765 — सोख्ता गड्डा(निर्भय सिंह के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845781 — सोख्ता गड्डा(रामचन्द्र प्रजापत के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845799 — सोख्ता गड्डा(राम लाल चौधरी के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845826 — सोख्ता गड्डा(खुशाल सिंह के घर के पास ) | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845830 — सोख्ता गड्डा(खुशाल सिंह के घर के पास ) | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845841 — सोख्ता गड्डा(आगनवाडीभवन के पास ) | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034845859 — सोख्ता गड्डा(शा .मा.वि . के पास ) | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855987 — सोख्ता गड्डा(रमेश परमार के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855988 — सोख्ता गड्डा(कृष्णा परमार के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855990 — सोख्ता गड्डा(मुकेश परमार के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855995 — सोख्ता गड्डा(राधेश्याम परमार के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855998 — सोख्ता गड्डा(रामचंद्र चौहान के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034855999 — सोख्ता गड्डा(रामचंद्र चौहान के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034856001 — सोख्ता गड्डा(मीरा बाई के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034856002 — सोख्ता गड्डा(भेरू नाथ के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034856003 — सोख्ता गड्डा(अमर नाथ के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034856005 — सोख्ता गड्डा(वकील नाथ के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006015/WC/22012034856009 — सोख्ता गड्डा(दयाराम नाथ के घर के पास ) | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006015/WC/22012034922935 — PDW TALAB JIRNODDHAR MARAMMAT KARYA SUNDRABAD | Completed | 39000 | 38068 | 2022-03-25 | 2024-07-04
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006015/WC/22012034961690 — अमृत सरोवर तालाब निर्माण (भेरू जी के रास्ते पर ) | Completed | 1312560.78 | 522611 | 2022-05-04 | 2024-07-10
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1718006015/WC/22012034980462 — नाला ट्रेचिंग गोया में | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1718006015/WC/22012034980532 — नाला ट्रेचिंग गोया सुमेर के खेत पास | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034980535 — नाला ट्रेचिंग गोया सुमेर के खेत पास | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006015/WC/22012034980536 — नाला ट्रेचिंग गोया सुमेर के खेत पास | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006015/WC/22012035125673 — sakrin pond sundrabad kamal malviya ke khet ke pas | Completed | 472845.25 | 390068 | 2024-06-21 | 2025-05-04
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006015/WC/22012035125682 — NALA TRENCHING AT dinesh sen ke khet pas | Completed | 296525.1 | 253680 | 2024-06-06 | 2025-03-23
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006015/WH/19961113 — तालाब नवीन कार्य सुन्दराबाद | Completed | 932000 | 729924.98 | 2017-05-24 | 2021-12-14
BADNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006/IF/22012034600491 — MG MNREGA NIJI PHALOUDHYAN SANTOSH/BADRILAL GRAM-SUNDRABAD | Physically Completed | 164208 | 60490 | 2020-09-25 | 2026-06-29