## Work List
Exported on: 2026-09-05 00:34:46
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: AJDAWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1718006018/AV/22012034664941 — Pachayat Bhavan Nirmand karya Gram Panchayat Ajdawada 15 vitt jila star and mgnregs | Ongoing | 1000000 | 748736.2 | 2025-03-22
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5493505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106132527 | Completed | 23490 | 0 | 2026-01-25 | 2026-08-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5766686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118035527 | Completed | 23490 | 0 | 2025-09-04 | 2026-08-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5950461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142240520 | Physically Completed | 23490 | 0 | 2026-04-10 | 2026-07-29
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5950462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142241216 | Physically Completed | 27000 | 0 | 2026-04-10 | 2026-08-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5950463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142242119 | Ongoing | 27000 | 0 | 2026-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5950620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117915517 | Approved | 27000 | 0 | 2026-02-11
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5951012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123827146 | Completed | 27000 | 4200 | 2026-04-10 | 2026-08-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5951580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103437104 | Approved | 27000 | 0 | 2026-01-23
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5951723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106344068 | Completed | 27000 | 4200 | 2026-04-10 | 2026-08-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5952596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106132836 | Physically Completed | 23490 | 0 | 2026-04-10 | 2026-07-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5954400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115735670 | Approved | 27000 | 0 | 2026-02-11
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5954403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115735759 | Completed | 27000 | 4200 | 2026-04-10 | 2026-08-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5955402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102628719 | Approved | 27000 | 0 | 2026-01-23
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5955908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106306561 | Physically Completed | 27000 | 0 | 2026-04-10 | 2026-08-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5957109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106180902 | Approved | 27000 | 0 | 2026-02-16
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5957663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102629024 | Ongoing | 27000 | 0 | 2026-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5958137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387988 | Approved | 27000 | 0 | 2026-02-11
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5958145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102628932 | Ongoing | 27000 | 4200 | 2026-04-24
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5958445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106174933 | Ongoing | 27000 | 0 | 2026-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5958446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106176788 | Approved | 27000 | 0 | 2026-01-23
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5960459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116093424 | Completed | 23490 | 0 | 2026-04-10 | 2026-08-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5960693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116095345 | Approved | 27000 | 0 | 2026-02-16
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5962362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116338806 | Ongoing | 27000 | 8400 | 2026-06-06
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5962511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106133048 | Ongoing | 27000 | 0 | 2026-06-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5963243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102627244 | Approved | 27000 | 0 | 2026-01-23
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5964531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191441 | Ongoing | 27000 | 0 | 2026-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5964654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118521706 | Approved | 27000 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5966109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118724029 | Approved | 27000 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5966222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106839568 | Approved | 27000 | 0 | 2026-02-11
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5966329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113950956 | Physically Completed | 27000 | 0 | 2026-04-10 | 2026-08-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5966689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102909230 | Physically Completed | 27000 | 0 | 2026-04-10 | 2026-08-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006018/IF/IAY/5966694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114728244 | Ongoing | 27000 | 0 | 2026-04-10
BADNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006018/RC/22012034852397 — Cc road nali nirmand dilip singh k ghar se rajendra Singh k ghar ki or Ajdavda | Ongoing | 158000 | 0 | 2026-01-23
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006018/RS/22012035133101 — nali nirmand ashok patidar k ghar se bharat singh k ghar ki or ajdavda | Ongoing | 96000 | 0 | 2025-02-04
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006018/RS/22012035133669 — nali nirmand vikram singh k ghar se savai singh k ghar ajdavada | Ongoing | 70000 | 0 | 2025-02-05