## Work List
Exported on: 2026-10-17 15:14:47
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: SANAWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006005/RC/36Antrik m — Antrik marg(G.S.B)Muramikaran Radhakrishn Mandir s | Deleted | 140000 | 0 | 2012-06-02
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006029/AV/22012034373717 — Aganvadi bhavan And boundarywall Norman gram itava | Completed | 312000 | 264519 | 2018-06-09 | 2023-01-12
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006029/AV/22012034401033 — AGANVADI BHAVAN NIRMAN SANAVDA | Completed | 180000 | 178240 | 2019-03-08 | 2023-04-26
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718006029/AV/22012034601900 — shantidham shed nirman itawa | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006029/DP/22012034432962 — वृक्षारोपण कार्य प्राथमिक स्कूल के पास सनावदा | Completed | 342000 | 108116 | 2018-07-31 | 2021-04-01
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1718006029/DP/22012034620240 — samudaik plantation at devnarayan rundi sanawda | Physically Completed | 443563.17 | 195870.06 | 2024-07-10 | 2026-04-02
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/DW/9993654121 — SOKHTA GADDHA SANAWADA TS-68/12.6.15 UNIT 5 | Completed | 65000 | 61693.6 | 2015-06-27 | 2016-07-03
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1718006029/FP/22012034627862 — nala trenching ramchandra chodhary ke ghar se nadi ki our | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006029/IF/22012034353499 — वृक्षा रोपण खेल मैदान इटवा | Completed | 335000 | 14116 | 2017-06-21 | 2018-07-08
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006029/IF/22012034357991 — vriksharopan SANAWDA 2 | Completed | 335000 | 211264 | 2017-08-09 | 2021-04-01
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006029/IF/22012034357992 — vriksharopan pachlanabill | Deleted | 335000 | 0 | 2017-08-09
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1718006029/IF/22012034606323 — NANDAN FALODHYAN MANGILAL NANDA | Completed | 142545 | 93060 | 2020-09-05 | 2022-12-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1718006029/IF/22012034606329 — NANDAN FALODHYAN PREM KUWAR CHATAR SINGH | Completed | 164208 | 121374 | 2020-09-05 | 2023-03-30
BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1718006029/IF/22012035130684 — NANDAN FALODHYAN DAYARAM AMARJI | Physically Completed | 180824 | 18080 | 2023-07-26 | 2026-04-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006029/IF/22012035320407 — khet talab niraman jagdish pita ratanlal gp sanawda | Physically Completed | 147621.16 | 138907.35 | 2025-04-22 | 2026-02-22
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006029/IF/22012035537292 — JGSA Jsodabai pati babula khet talab gp sanawda | Closed | 147621.16 | 0 | 2025-04-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006029/IF/22012035602098 — EK BAGIYA MAA KE NAAM SEEMA KUNWAR JITENDRA SINGH SANAWADA SHG CODE 170055417189 | Ongoing | 263510.03 | 70376 | 2025-09-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006029/IF/22012035635629 — EK BAGIYA MAA KE NAAM SANGITA SEWARAM SANAWADA 170022929447 | Ongoing | 263511.37 | 238869.6 | 2025-10-31
BADNAGAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006029/IF/2KAPILDHAR — KAPILDHARA KUP NIRMAN RADHESHYAM SITARAM(37/16.04. | Completed | 258000 | 243142 | 2012-04-24 | 2013-10-01
BADNAGAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006029/IF/3KAPILDHAR — KAPILDHARA KUP NIRMAN BHERULAL SHANKARLAL(36/16.04.12) | Completed | 258000 | 238537 | 2012-04-24 | 2013-09-09
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728589 — khet samtalikaran kailash rameshware(ts 784/28/02/ | Completed | 104000 | 90586 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728590 — khetsamtalikaran gendalal haraji(ts 785/28/02/2014 | Completed | 104000 | 95697 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728591 — khetsamtalikaran indersingh gangaram(ts 786/28/02/ | Completed | 104000 | 94354 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728592 — khetsamtalikaran Gopal gangaram(ts 787/28/02/2014) | Completed | 104000 | 92809.9 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9926728593 — khetsamtalikaran Ganpat puna(ts 788/28/02/2014) | Completed | 104000 | 97041 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728595 — khetsamtalikaran Bherulal Gangaram(ts 789/28/02/20 | Completed | 104000 | 100125.2 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728597 — khetsamtalikaran Nagji Bhuwan(ts 790/28/02/2014) | Completed | 104000 | 84937 | 2014-05-11 | 2014-06-12
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926728598 — khetsamtalikaran Ramlal Kanha(ts 791/28/02/2014) | Completed | 104000 | 98314 | 2014-05-11 | 2014-07-01
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926738951 — KEHT SAMTALIKARAD RESAMBAI-SANKARLAL T/S792 28/02/ | Completed | 105000 | 93752.9 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926738962 — Khet samtalikaran Ishwar Prakash(Ts 793/28/02/2014 | Completed | 105000 | 94320.9 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006029/IF/9926738968 — Khetsamtalikaran Hemraj Dhulji (Ts 69/27/05/2014) | Completed | 105000 | 89610.9 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9926738970 — khet samtalikaran Ramchandra Shankerlal(Ts 68/27/0 | Completed | 105000 | 91868.9 | 2014-06-19 | 2014-11-27
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/9993679494 — IAY/VISHNUBAI-KELASH/AS/1310 | Deleted | 14310 | 0 | 2015-08-15
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/9993679497 — IAY/SUGANBAI-TEJARAM/AS/1309/19/09/2015 | Completed | 14310 | 11832 | 2015-10-10 | 2016-08-05
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993692898 — PASHU SHED+NADEP DHANSINGH-TEJSINGH | Completed | 100000 | 95865.2 | 2016-01-10 | 2016-08-05
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993693412 — pashu shed nadep(kamalsingh-balram singh)ts-272 | Completed | 100000 | 97313.8 | 2016-01-08 | 2016-08-06
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993693416 — pashu shed nadep(resham bai-shankarlal)ts-362 | Deleted | 0 | 0 | 2015-11-18
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993693424 — pashu shed resham bai | Completed | 100000 | 88277 | 2016-01-26 | 2017-10-16
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993693868 — pashu shed (balram shankarlal) | Completed | 100000 | 92144.36 | 2016-01-10 | 2017-10-16
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993698003 — Pashu shed Nadep (Bherulal s/o Shankarlal) TS. No.363 D. 30/11/2015 | Deleted | 100000 | 0 | 2015-12-19
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006029/IF/9993705343 — Catal Shed+nadep Rambhabai Atmaram Ts 488 /13/01/2016 | Completed | 100000 | 98882 | 2016-01-22 | 2016-10-14
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/262761 — Construction of IAY House -IAY REG. NO. MP2832812 | Completed | 15030 | 15060 | 2017-02-03 | 2017-10-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/3668980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115687779 | Completed | 18360 | 18360 | 2022-07-03 | 2023-05-20
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/3711017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117864589 | Completed | 18360 | 18360 | 2022-07-03 | 2023-05-20
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/3813779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865016 | Completed | 18360 | 18156 | 2022-07-03 | 2023-03-30
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4175770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865121 | Completed | 18360 | 18360 | 2022-07-03 | 2023-05-20
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4555781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114762143 | Completed | 23490 | 20412 | 2024-11-29 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4557446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114137068 | Completed | 23490 | 20898 | 2025-03-03 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4560804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114864776 | Ongoing | 27000 | 13122 | 2024-11-29
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4567033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116623253 | Completed | 21870 | 21627 | 2024-11-29 | 2025-03-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4993419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114136975 | Physically Completed | 23490 | 21663 | 2025-07-30 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4993421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114137094 | Completed | 23490 | 21924 | 2025-07-30 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4994591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114864857 | Physically Completed | 23490 | 12789 | 2025-09-25 | 2026-08-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4994592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114864944 | Approved | 27000 | 0 | 2025-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4994612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114875521 | Ongoing | 27000 | 14616 | 2025-06-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4994614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114875695 | Physically Completed | 23490 | 19314 | 2025-05-22 | 2026-03-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4994615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114875792 | Physically Completed | 27000 | 0 | 2025-05-21 | 2026-09-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/4996351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114748766 | Completed | 23490 | 22446 | 2025-05-22 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/4997496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115687591 | Ongoing | 27000 | 13572 | 2025-08-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5082343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115122583 | Completed | 23490 | 21924 | 2025-05-22 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5082344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115122747 | Completed | 23490 | 23229 | 2025-07-30 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006029/IF/IAY/5386631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115370054 | Physically Completed | 27000 | 11484 | 2025-07-30 | 2026-10-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5390391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116240800 | Completed | 23490 | 21924 | 2025-07-30 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5501724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114864547 | Completed | 23490 | 20358 | 2025-07-30 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5828974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114748587 | Physically Completed | 23490 | 20880 | 2025-10-06 | 2026-03-15
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5969919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116241180 | Physically Completed | 23490 | 23217 | 2026-04-19 | 2026-05-31
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/5970249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115369400 | Physically Completed | 23490 | 3654 | 2026-05-07 | 2026-06-14
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/92658 — Construction of IAY House -IAY REG. NO. MP-18-006-029-003/53 | Deleted | 15480 | 0 | 2018-05-25
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006029/IF/IAY/93943 — Construction of IAY House -IAY REG. NO. MP-18-006-029-002/012 | Completed | 14310 | 10020 | 2016-06-24 | 2016-07-23
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006029/LD/22012034242434 — khelmaidan itawa 365/30.11.15 | Completed | 737400 | 398816 | 2015-12-09 | 2017-10-30
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006029/LD/22012034300192 — shanti dham shed sanawda ts/7258-09/12/2016 | Completed | 180000 | 182796.5 | 2017-01-31 | 2018-05-31
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006029/LD/22012034300213 — shanti dham itava 7258/09/12/2016 | Completed | 180000 | 179626 | 2017-01-31 | 2018-05-29
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006029/LD/22012034300225 — shanti dham shed (itawa t/s 7258-09/12/2016) | Completed | 180018 | 1134 | 2017-01-31 | 2017-10-07
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/10 — स् डक निरमाण् | Deleted | 0 | 0 | 2010-04-01
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/15सनावदा ग — सनावदा ग्रामीण क्रीडांगन प्रा वि सनावदा | Completed | 398000 | 379006.06 | 2011-02-18 | 2012-09-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034169676 — CC ROAD NALI NIRMAN ITAVA HAKAM K GHAR S HANUMAN M | Completed | 197830 | 192622 | 2013-06-05 | 2013-11-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034185039 — CC road +nalinirman sanawada gaytrimata mohan(T/S | Completed | 67000 | 19272 | 2013-09-25 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034185042 — cc road + nali mandir se mangu itawa(ts-467/2.6.13 | Completed | 67000 | 60587.88 | 2013-09-25 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034186437 — CC ROAD+NALI HAKAM SE HANUMAN MANDIR(TS-117/23.7.1 | Completed | 133500 | 118532.2 | 2013-10-03 | 2014-06-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/22012034191712 — ANTRIKMARG GSB SANAWDA SE DANTARWA(TS-126/2.8.13) | Completed | 290000 | 264396.8 | 2013-11-12 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006029/RC/22012034205858 — khat sadak shanker balram (ts 443/27/01/2014) | Completed | 1387000 | 1294625.32 | 2014-02-21 | 2016-06-24
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034211617 — ccroad nali pp+m sukhram (ts 708/22/02/2014) | Completed | 98000 | 86517.21 | 2014-03-05 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034211631 — ccroad nali pp+m tejaji(ts 709/22/02/2014) | Completed | 98000 | 65756 | 2014-03-05 | 2014-05-31
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034214722 — ccroad pp+m shalabhawan karan(ts 933/03/03/2014 | Completed | 250000 | 223756.93 | 2014-03-19 | 2014-09-29
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/22012034214738 — anrikmarag gsb itawa(ts 934/03/03/2014) | Completed | 200000 | 181732.8 | 2014-03-19 | 2014-06-17
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034264227 — cc road +nali nirman pp+m sanawada ts-125/20.8.15 | Completed | 200000 | 175598 | 2015-09-16 | 2015-12-18
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034264731 — cc+nali nirman mn+pp2 gram abadi sanavda | Closed | 0 | 0 | 2014-10-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034301922 — cc road+nali | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034301923 — cc road+nali | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034323139 — CC ROAD AND NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034333252 — नाली निर्माण कचरू के घर से बालाराम के घर तक | Completed | 2300 | 2064 | 2017-04-04 | 2018-07-08
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034333257 — नाली निर्माण जगदीश के घर से विश्राम के घर तक | Completed | 4500 | 4128 | 2017-04-04 | 2018-07-07
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034333262 — NALI NIRMAN HANUMAN MANDIR SE NALE TAK | Deleted | 8700 | 0 | 2017-03-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034333263 — NALI NIRMAN PM ROAD SE HEND PUMP TAK | Deleted | 1200 | 0 | 2016-12-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034333267 — CCROAD+NALI NIRMAN PM ROAD TO RAMSINGH KE GAR TAK | Completed | 6000 | 5160 | 2017-04-04 | 2018-07-07
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034338971 — CC ROAD+NALI NIRMAN MUKESH SE BANESINGH KE GHAR KI OR | Completed | 12000 | 8256 | 2017-05-24 | 2018-04-08
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006029/RC/22012034339233 — sudur sampark road p.m.sadak se palwa marg | Completed | 2000000 | 1828731.58 | 2017-05-26 | 2021-04-15
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034368308 — cc road radha krishna mandir se ramprasad ke ghar tak | Completed | 12000 | 11388 | 2017-12-30 | 2018-07-11
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034368386 — cc road pm sadak se bapusingh ke ghar tak 14 | Physically Completed | 36000 | 1126 | 2022-01-13 | 2026-03-31
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034368522 — cc road pm road se pani ki tanki16 | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034368527 — cc road pm road se pani ki tanki16 | Completed | 14000 | 13512 | 2018-01-06 | 2018-07-07
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034368549 — cc+nali pm road se karansingh ke ghar tak17 | Closed | 25000 | 0 | 2017-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034371133 — सीसी रोड +नाली | Closed | 0 | 0 | 2018-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034374388 — सीसी रोड +नाली शीतला माता चोक | Physically Completed | 12000 | 11388 | 2018-01-25 | 2019-12-10
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034374393 — सीसी रोड +नाली मोतीलाल के घर से हीरा लाल के घर तक | Completed | 3000 | 2064 | 2018-01-25 | 2019-08-19
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034379175 — cc+nali pm road se ramchandra ke ghar tak | Completed | 14900 | 1200 | 2022-09-20 | 2023-12-08
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034379180 — cc+nali pm sadak se mangilal ke ghar tak | Physically Completed | 23700 | 21684 | 2018-01-26 | 2019-05-05
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034386398 — cc road nali nirman badrilal chokidar ke ghar se kachru bhagga ke ghar tek itawa | Closed | 21000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034386593 — CC ROAD NALI NIRMAN JUJHAR BHERA KE GHAR SE DILIP KE GHAR TAK | Closed | 4000000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034386600 — CC ROAD NALI NIRMAN KHRNSINGH KE GHAR SE JAGDISHCNDAR KE GHAR TAK | Closed | 0 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034386601 — CC ROAD NALI NIRMAN KHRNSINGH KE GHAR SE JAGDISHCNDAR KE GHAR TAK | Closed | 27000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034386886 — CC ROAD NALI NIRMAN P.M.ROAD SE SUKHARAM KE GHAR TAK | Closed | 7000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387021 — CC ROAD NALI NIRMAN P.M. ROAD SE SUKHRAM KE GHAR TAK | Closed | 0 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387022 — CC ROAD NALI NIRMAN MUKESH SHARMA KE GHAR SE BNESINGH KE GHAR TAK | Closed | 6000000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387024 — CC ROAD NALI NIRMAN MOTILAL KE GHAR SE P.M. TAK | Closed | 36000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387025 — CC ROAD NALI NIRMAN DINESH KE GHAR SE PATEL KE GHAR TAK ETAWA | Closed | 7800000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387026 — CC ROAD NALI NIRMAN BNESINGH KE GHAR SE DHANSINGH KE GHAR OR ETAWA | Closed | 40000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034387027 — CC ROAD NALI NIRMAN SREE RAM MANDIR SE BHADAR SINGH KE GHAR TAK ETAWA | Closed | 6600000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034387132 — NALI NIRMAN SHTIMATA OTLA SE P.M. ROAD TAK ETAWA | Closed | 1000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034387133 — NALI NIRMAN BADRILAL KE GHAR SE HNUMAN JI CHOK TAK ETAWA | Closed | 1000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034387170 — NALI NIRMAN DHULSINGH KE GHAR SE P.M. ROAD TAK ETAWA | Closed | 10000 | 0 | 2017-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1718006029/RC/22012034387171 — NALI NIRMAN P.M. ROAD SE KHEL MEDAN TAK ETAWA | Closed | 7000 | 0 | 2017-10-02
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034440183 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034462880 — CC ROAD NIRMAND PM SADK SE RATAN SINGH K GHAR | Completed | 115000 | 106994 | 2019-03-15 | 2021-03-25
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006029/RC/22012034535181 — gravel road pm road se palwa marg tak | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034538609 — cc road pm sadak se vikram singh ka ghar shivmandir chok v amarsingh ke ghar tak | Completed | 42000 | 42314 | 2020-10-07 | 2021-04-15
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034641652 — Cc road nai abadi se govt. Prathmik EGS School k samne gram itava | Completed | 56000 | 55251 | 2023-06-18 | 2024-04-25
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/22012034663845 — Cc road nirmand pm sadk s lekr panchayt k samne hokr mukesh choudhari k ghar ki or sanavda | Completed | 60000 | 29222 | 2023-10-06 | 2024-07-16
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/27मुरमीकरण — मुरमीकरण ईटावा मुख्‍य मार्ग से पलवा रोड (164/18.4.11) | Completed | 484000 | 470731 | 2011-05-02 | 2012-09-25
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/29अर्थवर्क — अर्थवर्क सनावदा से दातरवा काकड भाग 1 (396/25.5.11) | Completed | 497000 | 474148 | 2011-05-28 | 2013-09-09
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/29मुरमीकरण — मुरमीकरण माता मंद‍िर से सनावदा रोड तक (488/16.6.2011) | Completed | 100000 | 98106 | 2011-06-21 | 2011-06-28
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/30भाग 2 — पलवा से ईटावा भाग 2 (163/18.4.11) | Completed | 497000 | 477785.97 | 2011-04-21 | 2012-09-25
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006029/RC/33सी सी रो — सी सी रोङ व नाली P.P+ M.‍िनमाण मदन सीह से हनुमान मंदीर इटावा(523/14.03.2012) | Completed | 284000 | 121300 | 2012-05-01 | 2013-09-09
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/35Antrik m — Antrik marg(G.S.B)Muramikaran Radhakrishn Mandir s Tejaji Choke( T/S 132/04.06.2012) | Completed | 140000 | 120555 | 2012-06-08 | 2013-09-09
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/37Antrik m — Antrik marg Muramikaran hakam singh k ghar se badri chokidar(T/S131/04/06/2012) | Completed | 139300 | 120377 | 2012-06-10 | 2013-09-09
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/6 अर्थवर्क — अर्थवर्क पलवा रोड से इटावा भाग 1 | Completed | 496000 | 470955 | 2010-06-03 | 2010-12-29
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006029/RC/6सनावदा अर — सनावदा अर्थवर्क सनावदा से दांतरवा काकड | Completed | 500000 | 471815.32 | 2010-04-08 | 2010-11-08
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218909 — निर्मल भारत बन्ना लाल -बग्दीराम(AS 45-04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218918 — निर्मल भारत दयाराम -अमराजी (AS-47-04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218923 — निर्मल भारत मोहन लाल -पीरूलाल (AS-49/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218924 — निर्मल भारत सूरज बाई -मूलचंद (AS-51/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218926 — निर्मल भारत हेमराज -दुलाजी (AS-53/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218928 — निर्मल भारत हेमराज -भग्गाजी (AS-55/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218929 — निर्मल भारत गिरवर -धन्नालाल (AS-57/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218933 — निर्मल भारत मोतीलाल -भेराजी (AS-59/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218936 — निर्मल भारत गोर्वधन -माधवसिंह (AS-63/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218972 — निर्मल भारत जगदीश -रतन लाल (as-65/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218976 — निर्मल भारत भगवान लाल -शंकर लाल (AS-67/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218981 — निर्मल भारत शांताबाई -तेजलाल (AS-04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218987 — निर्मल भारत मोहनलाल -मांगूजी (AS-71/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218991 — निर्मल भारत बहादुर -मांगीलाल (AS-73/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218994 — निर्मल भारतकैलाश -रामेश्वर (AS-75/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218997 — निर्मल भारत इन्दर सिंह -गंगाराम(as77-04/03/2014) | Completed | 4400 | 2628 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034218999 — निर्मल भारत धन्नलाल -केसूराम (AS-79/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034219002 — निर्मल भारत गणपत -पुनाजी (AS-81/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034219004 — निर्मल भारत मोहनलाल -केशुराम (AS83/04/03/2014) | Completed | 4400 | 4388 | 2014-03-22 | 2014-06-07
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242383 — nirmal bharat dhan sing(As 09/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242402 — nirmal bharat tolaram(as-11/30/05/2014 | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242412 — nirmal bharat mangilal Nanda(As 13/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242421 — nirmal bharat ramsing ganpat(as-15/30/05/2014 | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242425 — nirmal bharat ambaram mangilal(as-17/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242433 — nirmal bharat sukhram nanuram(as-19/30/05/2014) | Completed | 5111 | 4866 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242624 — nirmal bharatmadanlal pirulal(21/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242630 — nirmal bharat arjun bhagirath(23/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242633 — nirmal bharat champabai basantilal(25/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034242638 — nirmal bharat bherulal gangaram(27/30/05/2014) | Completed | 5111 | 5023 | 2014-06-19 | 2014-11-27
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006029/RS/22012034373496 — SHOCHALY NIRMAN VISHRAMS-O GANPAT JI | Completed | 12000 | 11264 | 2017-09-20 | 2017-11-06
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Stabilization Pond / Construction of Stabilization Pond for Community | Solid and Liquid Waste Management | 1718006029/RS/22012034403122 — nali nirman shtimata otla se p.m road tak | Closed | 0 | 0 | 2017-10-02
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006029/RS/22012034647094 — NALI NIRMAN KARYA NAI AABADI PANCHAYAT BHAWAN SE BHARATLAL KE GHAR SANAWADA | Completed | 82000 | 102773 | 2022-04-01 | 2022-09-21
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006029/RS/22012034697688 — Nali nirmand girdhari lal k ghar se panchyat tk sanavda | Completed | 13000 | 9870 | 2023-09-03 | 2024-05-07
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006029/RS/22012034698080 — samudayik shohchalay itawa | Completed | 47000 | 43351 | 2023-07-23 | 2023-12-07
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006029/RS/22012035116704 — Nali nirmand aganvadi k samne s badrilal k ghar hote huye hanuman ji mandir k piche wale nale itava | Completed | 18000 | 14270 | 2023-10-06 | 2024-08-25
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006029/RS/22012035133350 — Nali Nirman Shantidham marg itawa | Physically Completed | 99000 | 64638 | 2024-12-05 | 2026-04-13
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034429304 — mwc check dam and nala trenching itawa palwa marg | Physically Completed | 569600 | 361458 | 2018-12-25 | 2021-04-15
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034438656 — Chekdem Nirman | Closed | 0 | 0 | 2018-04-14
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034445675 — CHECK DAM NALA TRAINCHING MANISH KAILASH ORA K KHET PASS GRAM ITAVA T/S 224/28.2.2019 | Completed | 762476 | 483466 | 2019-03-08 | 2021-04-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034480271 — RICHARGE PITH PANCAYAT BHAVAN KE SAMNE SANAWDA | Completed | 10857.75 | 9680 | 2021-11-08 | 2025-05-04
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034480274 — RICHARGE PITH HARIJAN MOHALA HEAD PAMP KE PAS ITAWA | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006029/WC/22012034577772 — NALA TRANCHING SANAWADA ITAWA MARG PR | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006029/WC/22012034577773 — NALA GTRANCHING KANCHAN SINGH KE KHET KE PAAS | Completed | 187763.67 | 190746 | 2021-01-07 | 2021-09-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006029/WC/22012034615003 — NALA NIRMAAN PM SADAK SE HANUMAN JI MANDIR KE PAAS ITAWA | Completed | 64000 | 19412 | 2021-11-08 | 2023-09-12
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034627406 — CHECK DEM AND NALA TREENCHING BANE SINGH KE KHET KE PAAS SANAWADA | Closed | 0 | 0 | 2021-01-06
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034627408 — CHECK DEM AND NALA TREENCHING BANE SINGH KE KHET KE PAAS SANAWADA | Closed | 0 | 0 | 2021-01-06
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034627420 — CHECK DEM AND NALA TREENCHING BANE SINGH KE KHET KE PAAS SANAWADA | Closed | 0 | 0 | 2021-01-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012034659828 — Chack dam & Nala Tranching banesingh ke khet ke pass | Physically Completed | 993148.99 | 959349 | 2021-05-05 | 2022-01-11
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744377 — CTR Sock Pit Nirman PV hundpump | Completed | 5781.86 | 6948 | 2021-10-24 | 2022-04-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744385 — CTR Sock Pit Nirman PV EGS | Completed | 5781.86 | 4632 | 2021-10-24 | 2022-01-11
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744393 — CTR Sock Pit Nirman panchayat bhavan ke pass hundpump ke samne | Completed | 5781.86 | 11106 | 2021-09-30 | 2022-04-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744403 — CTR Rain Water Harvesting Aaganwadi Bhavan | Completed | 16867.31 | 16628 | 2021-09-30 | 2022-04-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744406 — CTR Rain Water Harvesting PV bhavan | Completed | 16867.31 | 9264 | 2021-09-30 | 2022-03-30
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744420 — CTR Rain Water Harvesting Aaganwadi Bhavan itawa | Completed | 16867.31 | 6948 | 2021-09-30 | 2022-02-21
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034744426 — CTR Rain Water Harvesting PV bhavan itawa | Completed | 16867.31 | 11580 | 2021-09-30 | 2022-03-30
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034838102 — CTR Sock Pit Nirman 1 | Completed | 14467.3 | 12352 | 2021-10-10 | 2022-04-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034838106 — CTR Sock Pit Nirman 2 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034843769 — CTR Sock Pit Nirman devnarayan mandir ke samne handpamp | Completed | 14467.3 | 11996 | 2021-11-08 | 2022-04-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844186 — ctr sokhta pit badrilal amar ji ki dukan ke samne itawa | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844204 — ctr sokta pit ramesh mistri ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844215 — vikram singh ji ke get ke pas | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844233 — ctr sokhta pit raju tejaram ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844242 — ctr sokta pit ramchandra chodhri ke ghar ke samne | Completed | 14467.3 | 5790 | 2021-12-07 | 2022-02-21
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844247 — ctr sokta pit genda lal haraji ke ghar ke samne | Completed | 14467.3 | 8522 | 2021-11-22 | 2022-08-20
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844254 — ctr sokta pit basanti lal chodhary ke ghar ke samne | Completed | 14467.3 | 11996 | 2021-11-22 | 2022-08-20
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844264 — ctr sokta pit sayar bai ramlal ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844270 — ctr sokta pit omprakash rupa ji ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034844276 — ctr sokta pit munnalal sharma ke ghar ke samne | Completed | 14467.3 | 10838 | 2021-11-22 | 2025-05-04
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847014 — ctr sokta pit reshambai shankarlal ke ghar ke samne | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847021 — ctr sokta pit prakash siddhnath ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847026 — ctr sokta pit samand bai siddhanath ke ghar ke samne | Completed | 14467.3 | 4632 | 2022-01-03 | 2022-03-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847033 — ctr sokta pit gendalal punaji ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847039 — ctr sokta pit rajesh anandilal ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847047 — ctr sokta pit shantilal bhagwan jike ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847049 — ctr sokta pit amrat lal manohar lalke ghar ke samne | Completed | 14467.3 | 4632 | 2021-12-07 | 2022-02-21
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847056 — ctr water harvesting manoharlal lakha ke ghar ke samne | Completed | 14467.3 | 6948 | 2021-11-30 | 2022-02-21
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847076 — ctr water harvesting ramchandra shankar lalke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012034847081 — ctr sokta pit shantilal shivlal ke ghar ke samne | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006029/WC/22012034900011 — Nala Tranching PV ke samne Nala | Completed | 264708.01 | 195053 | 2022-02-03 | 2022-11-26
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012035018155 — Nala Tranching Nirman sanavada Itawa marg se hakam singh ke khet ki aur | Completed | 248939.53 | 151933 | 2023-06-03 | 2024-07-30
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006029/WC/22012035018158 — Nala Tranching Nirman PM raod se sitaram ke khet ki aur | Completed | 213662.45 | 150366 | 2022-12-15 | 2024-07-09
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006029/WC/22012035137527 — Recharge Tranch shivji runda se nadi ki aur | Completed | 292448.63 | 151038 | 2023-10-06 | 2025-01-16
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012035167945 — Check Dam Nirman Dharmendra singh ke khet ke pass | Completed | 1079720.09 | 1029866.9 | 2024-05-15 | 2025-01-16
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006029/WC/22012035167952 — Check Dam Nirman Satyanarayan ke khet ke pass | Closed | 0 | 0 | 2023-10-02
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1718006029/WC/22012035224941 — Dug Pond Nirman Sanawada | Completed | 542695.65 | 192088.4 | 2024-11-22 | 2025-06-23
BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718006029/WC/VB/YD/22012035336275 — Roof top rain wat. har. str. in gov/Anganwadi bhawan | Approved | 29550.01 | 0 | 2026-08-15