## Work List
Exported on: 2026-10-01 04:35:17
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: JHALARIA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006030/AV/3581 — Aanganbadi/Other Rural Infrastructure,JHALARIA | Completed | 195000 | 95124 | 2015-09-12 | 2018-02-24
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006030/AV/3630 — Aanganbadi/Other Rural Infrastructure,BADNAGAR | Completed | 195000 | 94223 | 2015-09-26 | 2018-07-21
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006030/AV/3631 — Aanganbadi/Other Rural Infrastructure,JHALARIA | Completed | 195000 | 147702 | 2015-09-18 | 2018-08-03
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006030/DP/22012034432744 — vraksharopan railvay patri ke pass kheda madhav | Closed | 342540 | 0 | 2018-08-15
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation in Government Premises / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1718006030/DP/46Kalu kah — नंदन फलोद्यान कालू खा s/o घिसे खा T/S(321/24/07/20 | Completed | 410000 | 243981.99 | 2012-09-22 | 2016-11-25
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/DW/9993653970 — SOKHATA GADDA JHALARIYA TS-100/12-6-2015 UNIT-5 | Deleted | 0 | 0 | 2015-05-15
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/DW/9993653971 — SOKHATA GADDA JHALARIYA TS-101/12-6-2015 UNIT-5 | Completed | 32500 | 31705.73 | 2015-07-02 | 2016-06-24
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Food Grain | Food Grain / Repair and Maintenance of Food grain Storage Building for Community | Constr of Food Grain storage | 1718006030/FG/9425884309 — Anajgodam jha(939/03/03/2014 | Deleted | 896000 | 0 | 2014-07-05
BADNAGAR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006030/IF/1 — कपीलधारा (अय्युबखा-शरीफखा)430/14.12.11 | Completed | 256000 | 206648.4 | 2011-02-18 | 2013-11-07
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006030/IF/22012034344745 — vraksaropan vidylay parisar jhalariya | Completed | 335000 | 7224 | 2017-05-30 | 2017-10-10
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006030/IF/22012034357375 — vriksharopan jhalariya 2 | Deleted | 335000 | 0 | 2017-08-09
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718006030/IF/22012034881017 — CTR soak pit nirman sadik kha | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881022 — CTR soak pit mohanlal | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881029 — CTR soak pit abid kha | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881044 — CTR soak pit kaniram | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881047 — CTR soak pit omprakash | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881048 — CTR soak pit rajesh | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881051 — CTR soak pit rakesh | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881055 — CTR soak pit muktiyar | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881060 — CTR soak pit ramchandra | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881067 — CTR soak pit jani bai | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881070 — CTR soak pit bharulal | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881071 — CTR soak pit salim kha | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718006030/IF/22012034881082 — CTR soak pit ashok | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718006030/IF/22012035327990 — Dug well recharge structure shakil kha s/o sultan kha kup gp jhalariya | Completed | 25177.32 | 22977 | 2025-04-23 | 2026-01-21
BADNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718006030/IF/22012035440463 — Dug well recharge structure ajad kha / sabir kha kup gp jhalariya | Completed | 25899.46 | 23238 | 2025-05-08 | 2026-01-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006030/IF/22012035539726 — JGSA Nahru pita iqbal khet talab gp jhalariya | Closed | 147621.16 | 0 | 2025-04-02
BADNAGAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006030/IF/2कपीलधारा — कपीलधारा उसमान खां सद्‍दु खां(156/18.04.2011) | Completed | 256000 | 200138 | 2011-05-11 | 2013-11-07
BADNAGAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006030/IF/2कुप निर्म — कुप निर्माण Ajad S/O sabbir kha (T/S 68/24.05.12 | Completed | 258190 | 252989 | 2012-05-27 | 2015-06-03
BADNAGAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006030/IF/5कुप निर्म — कुप निर्माण Shakil S/O sultan kha (T/S 69/24.05. | Completed | 258190 | 246322 | 2012-05-27 | 2015-06-03
BADNAGAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006030/IF/9926700872 — KUP NIRMAN YUNUSKHA JALIL(TS-604/30.1.14) | Completed | 272309 | 253086.56 | 2014-02-12 | 2016-06-17
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006030/IF/9926735293 — pasushad kallukha(384/24/1/2014) | Deleted | 0 | 0 | 2014-04-08
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006030/IF/9926735303 — pasushad Rajesh(383/24/01/2014) | Completed | 70700 | 64087.98 | 2014-06-08 | 2016-10-23
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006030/IF/9926735567 — pasusadkallu(384/24/01/2014) | Completed | 70700 | 64666 | 2014-06-09 | 2016-11-25
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/9993697399 — IAYjcard119(mohanlal-ratanlal)\436/08/09/15 | Completed | 14310 | 13644 | 2015-12-19 | 2016-11-29
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006030/IF/9993700961 — IAYjobcard(sajadbai ide kha)\436/08/09/15 | Closed | 14310 | 0 | 2015-12-01
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006030/IF/9993702482 — IAYjobcard145(sabirkha sarifkha)\436/08/09/15 | Closed | 14310 | 0 | 2016-01-06
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006030/IF/9993702486 — IAYjobcard116(akramkha sakurkha)\436/08/09/15 | Closed | 14310 | 0 | 2015-08-15
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006030/IF/9993703714 — pasushed nirman(jahirkha-rasidkha)/431/15/12/2015 | Completed | 100000 | 74812 | 2016-01-11 | 2017-10-25
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006030/IF/9993718189 — cattle shed | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/1274073 — Construction of IAY House -IAY REG. NO. MP2174278 | Completed | 15480 | 14616 | 2018-04-04 | 2018-07-08
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/1849315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4339677 | Completed | 15660 | 15660 | 2018-07-08 | 2018-10-25
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3726314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119691511 | Completed | 18360 | 18360 | 2022-07-08 | 2022-11-13
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3726354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119698889 | Completed | 18360 | 18354 | 2022-10-29 | 2023-05-11
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3731706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119833875 | Completed | 18360 | 18360 | 2022-06-13 | 2023-01-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3734575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123405727 | Completed | 18360 | 18360 | 2022-11-21 | 2023-05-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3745842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120001508 | Completed | 18360 | 18241 | 2023-02-07 | 2023-06-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3745875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120005001 | Completed | 18360 | 18360 | 2022-12-14 | 2023-05-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3869223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145129347 | Completed | 18360 | 18156 | 2022-07-08 | 2022-11-20
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3872271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145264833 | Completed | 18360 | 18122 | 2022-07-08 | 2023-05-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3872272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145266216 | Completed | 18360 | 17748 | 2022-06-30 | 2022-12-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/3872287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145270196 | Completed | 18360 | 18360 | 2022-08-18 | 2022-12-24
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/41154 — Construction of IAY House -IAY REG. NO. MP-18-006-030-002/52 | Approved | 23490 | 0 | 2015-11-25
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/41155 — Construction of IAY House -IAY REG. NO. MP-18-006-030-002/60 | Approved | 23490 | 0 | 2015-11-25
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4175414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118541733 | Completed | 18360 | 18360 | 2022-07-08 | 2023-01-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4584629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120010015 | Completed | 21870 | 21870 | 2024-12-17 | 2025-02-24
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4584676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120020262 | Completed | 21870 | 21870 | 2024-10-16 | 2025-03-16
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4800008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150268626 | Completed | 21870 | 21870 | 2024-11-22 | 2025-03-22
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4800010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150270632 | Completed | 21870 | 21870 | 2024-11-22 | 2025-03-22
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4805091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145263021 | Approved | 23490 | 0 | 2024-10-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4807881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145268188 | Completed | 21870 | 21870 | 2024-11-22 | 2025-03-16
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4909321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119694217 | Completed | 23490 | 22455 | 2025-03-03 | 2025-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/4909835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123448046 | Completed | 23490 | 22860 | 2025-03-03 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5147555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118814155 | Ongoing | 23490 | 21924 | 2026-02-22
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5152719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145209364 | Approved | 23490 | 0 | 2025-02-19
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5166654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119717929 | Approved | 23490 | 0 | 2025-03-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5169973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150279117 | Physically Completed | 23490 | 19314 | 2025-08-20 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5179396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119834450 | Completed | 23490 | 23490 | 2025-08-23 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5199319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119691610 | Completed | 23490 | 23490 | 2025-07-19 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5205810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119835581 | Completed | 23490 | 23490 | 2025-05-01 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5236159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120015528 | Ongoing | 23490 | 7308 | 2026-02-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5237174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148635655 | Physically Completed | 23490 | 17748 | 2026-02-19 | 2026-05-03
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5240277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120611942 | Approved | 23490 | 0 | 2025-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5419400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145211879 | Approved | 23490 | 0 | 2025-04-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5419637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148641722 | Approved | 23490 | 0 | 2025-04-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5421168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145255997 | Completed | 23490 | 23490 | 2025-08-05 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5421720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148626178 | Ongoing | 23490 | 19836 | 2025-10-07
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5422946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119988618 | Approved | 23490 | 0 | 2025-04-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5670730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145249854 | Ongoing | 23490 | 7308 | 2026-03-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5670983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120013092 | Completed | 23490 | 23490 | 2025-10-07 | 2026-03-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5814436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146204323 | Physically Completed | 23490 | 23490 | 2026-02-24 | 2026-04-23
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5853397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123425472 | Completed | 23490 | 23490 | 2025-11-11 | 2026-01-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5880191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146111412 | Approved | 23490 | 0 | 2025-09-04
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5949112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145200723 | Ongoing | 23490 | 14616 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5950901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147853407 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5950923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119840394 | Ongoing | 23490 | 14616 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5951093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146215265 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5951094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146220261 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5951097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147863553 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5951877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145254446 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5952299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145205022 | Approved | 23490 | 0 | 2026-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5952462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145261665 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5952497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120614079 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5952777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120609830 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5953160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145248296 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5953333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146072497 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5954394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118796633 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5954803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150257466 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5955851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145225135 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5955852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145230041 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5956491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123419490 | Ongoing | 23490 | 14616 | 2026-05-12
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5957592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119978310 | Ongoing | 23490 | 21924 | 2026-04-15
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5957755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119986369 | Ongoing | 23490 | 7308 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5957882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118803975 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5958742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150282932 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5959363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145652341 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5960787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146197288 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5960850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118802346 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5961209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119981489 | Ongoing | 23490 | 14616 | 2026-04-24
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5961918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148671476 | Ongoing | 23490 | 21924 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5962217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148626143 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5962784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146098401 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5962785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146115015 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5962956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146194010 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5962985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118550877 | Ongoing | 23490 | 14616 | 2026-04-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5963467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118776461 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5964057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145258365 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5964192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145207231 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146112789 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146068604 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119838675 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119838685 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120613529 | Approved | 23490 | 0 | 2026-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/5966692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118546446 | Approved | 23490 | 0 | 2026-02-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6111957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120625366 | Approved | 23490 | 0 | 2026-02-23
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6112266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146209410 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6112691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148631193 | Approved | 23490 | 0 | 2026-02-23
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6112777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146177349 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6113763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146226645 | Approved | 23490 | 0 | 2026-03-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6113960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146081634 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6114125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120620338 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6114127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148678417 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6114200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118805760 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6114402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145252408 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6114432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146088652 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146084134 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146086481 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120611021 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120696994 | Approved | 23490 | 0 | 2026-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118780822 | Approved | 23490 | 0 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6115966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118810824 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148167497 | Ongoing | 23490 | 14616 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147863574 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147870059 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147836768 | Approved | 23490 | 0 | 2026-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145197331 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118785593 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146103525 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6116963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118776484 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146074327 | Approved | 23490 | 0 | 2026-03-10
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123416053 | Ongoing | 23490 | 14616 | 2026-05-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123420731 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146093994 | Approved | 23490 | 0 | 2026-02-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147787484 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145231917 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148647196 | Approved | 23490 | 0 | 2026-02-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6117531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146091866 | Approved | 23490 | 0 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6139980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147848153 | Approved | 23490 | 0 | 2026-03-17
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6166354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147166716 | Approved | 23490 | 0 | 2026-03-17
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/6168337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146109697 | Approved | 23490 | 0 | 2026-03-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/93655 — Construction of IAY House -IAY REG. NO. MP-18-006-030-002/41 | Approved | 23490 | 0 | 2015-09-25
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006030/IF/IAY/93656 — Construction of IAY House -IAY REG. NO. MP-18-006-030-002/74 | Approved | 23490 | 0 | 2015-09-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006030/LD/22012034306577 — santidham nirman jhalariya | Completed | 180000 | 155356.3 | 2017-03-20 | 2018-02-24
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/14 — अर्थवर्क ग्राम से कब्रस्तान पहुच मार्ग | Deleted | 0 | 0 | 2010-12-27
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/15झलारिया — झलारिया ग्रामीण क्रीडांगन समतलीकरण एवं टेंच खुदाई | Completed | 375000 | 287202.56 | 2011-01-22 | 2015-03-23
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/22012034186100 — GRAMIN SADAK JHALARIYA S PALDUNA (T/S 28/30/05/201 | Deleted | 2231000 | 0 | 2012-04-14
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034191510 — samudayik cc road kabrastan marg(ts-173/12.6.13) | Completed | 45000 | 44970 | 2013-11-03 | 2016-06-24
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/22012034203994 — SUDUR KHET SADAK JHABRI SE ARIF(TS-541/28.1.14) | Completed | 1391400 | 1180534.95 | 2014-02-12 | 2017-02-23
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034224691 — ccroad+nala khajupatel chok(104/18/07/2013) | Completed | 66750 | 63250 | 2014-07-22 | 2015-03-31
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034264238 — cc road +nali nirman pp+m hanuman mandir jhalariya(ts-122/6.8.15) | Completed | 200000 | 114639 | 2015-09-11 | 2017-01-28
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034264740 — cc+nali nirman mn+pp2 gram abadi jhalariya | Closed | 0 | 0 | 2014-10-02
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034292568 — cc road+nali nirman pp+m jamil kheda madhava(ts-406/3.12.15) | Completed | 193000 | 181455 | 2015-12-23 | 2018-02-24
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034295772 — ccroad+nali nirman middie school se salam shah k ghar k or ss+m jhalariya(t/s442/14/09/2015) | Completed | 265000 | 187734 | 2016-01-21 | 2016-11-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034301882 — CC Road | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034301884 — CC Road | Closed | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034323197 — CC ROAD AND NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006030/RC/22012034325815 — sudur gram sampark sadak jhalariya se kheda madhav(173/25-01-2017) | Completed | 1476000 | 1018984.58 | 2017-02-07 | 2019-07-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034332805 — cc road nali nirman edu kha ke ghar ki or jhalariya | Completed | 13300 | 12744 | 2017-03-23 | 2018-03-31
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034359968 — cc road nali nirman hakim kha ke ghar se yasin shah ke ghar tak | Completed | 114200 | 94944 | 2017-09-15 | 2018-07-08
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034362439 — cc road nali nirman chogalal ke ghar se syra bai ke ghar tak | Completed | 91200 | 61920 | 2017-10-04 | 2018-06-27
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034371040 — सीसी रोड + नाली | Closed | 0 | 0 | 2018-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034378366 — cc road hasan khake ghar se rafik kha ke ghar tak | Completed | 41500 | 38700 | 2018-01-02 | 2018-06-27
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034378665 — cc road radhakreshna mandir se babu kha ke ghar tak | Completed | 14000 | 12212 | 2018-01-17 | 2018-06-27
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034378667 — cc road hakim kha ke ghar se kaniram kha ke ghar tak | Completed | 54000 | 48198 | 2018-06-20 | 2019-02-18
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034394900 — सीसी रोड निर्माण इदु खा के घर से रफीक खा के घर कि और झलारिया | Completed | 35400 | 29826 | 2018-10-06 | 2019-05-15
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034394910 — सीसी रोड निर्माण पंचायत भवन के सामने से पीएम सड़क सादिक के घर तक | Completed | 60200 | 59742 | 2018-10-06 | 2019-01-20
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034435916 — cc road nirman sabdar kha ke ghar se mubarik kha ke ghar tak khedamadhav | Completed | 75000 | 74124 | 2019-01-19 | 2019-03-05
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034437034 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034440594 — cc road nirman khaju kha ke ghar se gaffar kha ke ghar tak kheda madhav | Completed | 73000 | 73080 | 2019-02-14 | 2019-04-20
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034448827 — cc road nali nirman sattar kha ke ghar se hamid kha (sanju) ke ghar ki or | Completed | 36000 | 36540 | 2019-03-16 | 2019-04-04
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034448831 — cc road nali nirman shakil kha ke ghar se ayyub kha ke ghar tak | Closed | 14000 | 0 | 2019-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034448833 — cc road nirman kallu kha ke ghar se akbar kha ke ghar tak | Completed | 15000 | 14616 | 2019-03-16 | 2019-04-04
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034448835 — cc road nali nirman shakur kha ke ghar se rasid kha ke ghar tak | Completed | 58000 | 50688 | 2019-09-04 | 2020-04-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034475854 — cc road nali nirman sadik kha ke ghar se Aarif kha ke ghar tak | Completed | 52000 | 45408 | 2019-11-17 | 2020-05-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034480772 — cc road nali nirman vahid kha ke ghar se raup kha ke ghar tak | Completed | 50000 | 40128 | 2019-12-01 | 2020-03-06
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034482228 — cc road nali nirman babu kha ke ghar se jalil kha ke ghar tak kheda madhav | Completed | 54000 | 48936 | 2019-10-31 | 2021-09-15
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034531969 — cc road nirman aslam kha ke ghar se pm sadak tak | Completed | 80000 | 65314 | 2020-08-22 | 2021-09-15
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006030/RC/22012034536619 — Sudur sampark sadak jhalariya pm sadak se moulana pahunch marg | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034560255 — CC road sadik kha ke ghar se akram kha ke ghar tak jhalariya | Completed | 40000 | 36480 | 2021-02-23 | 2022-01-01
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034621348 — cc road nirman pm sadak se govt prathmik sala bhavan jhalariya | Closed | 72000 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034621349 — cc road nirman pm sadak se govt prathmik sala bhavan jhalariya | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034825701 — cc road nali nirman sarfaraj ke ghar ke samne jhalariya | Approved | 21000 | 0 | 2024-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/22012034825706 — cc road nali nirman masjid or akram kha ke ghar ke samne jhalariya | Completed | 24000 | 22113.07 | 2024-10-01 | 2026-02-28
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/2झलारिया — अर्थवर्क खेडामाधव से बिरगोदा मार्ग खेडा्माधव झलारिया | Completed | 500000 | 483395 | 2009-02-18 | 2009-10-15
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/3 — अर्थवर्क ग्राम से कब्रस्तान पहुच मार्ग(406/27.1.11) | Completed | 402000 | 357529.06 | 2011-01-29 | 2013-03-27
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/32सी सी रो — सी सी रोङ नाली स‍हीत ‍िव+म झलारीया (106/22.02.2011) | Completed | 300000 | 122598 | 2011-06-08 | 2013-03-27
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/33अर्थ वर् — अर्थ वर्क रोड खेङामाधव रोड से कराङीया हनुमान(49/13 | Completed | 497000 | 426385.91 | 2011-06-01 | 2015-03-23
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/33सी सी रो — सी सी रोङ व नाली P.P+ M.‍ बरबरा मोहल्‍ला खेङामाधव(556/15.03.2012) | Completed | 423000 | 90484 | 2012-04-08 | 2013-03-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/35Antrik m — आन्तरिक मार्ग (G.S.B) मुरमीकरण shah mohall(ts212-) | Completed | 100000 | 86389.38 | 2012-09-24 | 2015-06-03
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/35U Aakar — U Aakar ki नाली Nirman P.P+ M. Shah Mohalla Jhalariya(505/06.10.2012) | Deleted | 204167 | 0 | 2012-09-06
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006030/RC/35सी सी रो — सी सी रोङ व नाली P.P+ M.‍िनमाण Khedamadhav barbara | Completed | 209666 | 204620 | 2013-06-29 | 2016-06-17
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/3झलारिया अ — झलारिया अर्थवर्क खेडामाधव रेल्‍वे पटरी से कराडिया की ओर | Completed | 500000 | 489371.66 | 2009-10-27 | 2010-04-06
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006030/RC/5झलारिया अ — झलारिया अर्थवर्क ग्राम झलारिया से जेल के पिछे तक | Completed | 500000 | 499649.1 | 2010-04-07 | 2010-10-21
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006030/RS/22012034283361 — swach bharat mission jhalariya unit 3 | Closed | 6000 | 0 | 2015-09-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006030/RS/22012034657086 — nali nirman middle school se kabristan marg ki or jhalariya | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006030/RS/22012034657087 — nali nirman middle school se kabristan marg ki or jhalariya | Completed | 60000 | 58752 | 2022-05-26 | 2022-11-13
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006030/WC/22012034428796 — check dam nala traching jhalariya | Completed | 569604 | 253058 | 2018-12-21 | 2021-09-25
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006030/WC/22012034438724 — check dam | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034550968 — Recharge Pond nirman jhalariya | Completed | 197284.3 | 191422 | 2020-05-31 | 2022-04-13
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034551183 — Nala trenching runda marg jhalariya | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776803 — CTR Sock Pit Nirman school ke pass | Completed | 14467.3 | 9264 | 2021-09-23 | 2022-12-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776806 — CTR Sock Pit Nirmanpalduna marg ke pass | Closed | 0 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776809 — CTR Sock Pit Nirman middle school ke pass | Closed | 14467.3 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776813 — CTR Sock Pit Nirman middle school ke pass | Closed | 0 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776816 — CTR Sock Pit Nirman khel madan handpump ke pass | Completed | 14467.3 | 9462 | 2021-09-23 | 2022-12-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776819 — CTR Sock Pit Nirman palduna marg | Closed | 14467.3 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776825 — CTR Rain Water Harvesting middle school | Closed | 16878.31 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034776831 — CTR Rain Water Harvesting panchayat bhavan | Closed | 22229.14 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034838056 — CTR Sock Pit Nirman 1 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034844651 — CTR sock pit nirman shantidham handpump | Completed | 14467.3 | 9071 | 2022-02-03 | 2022-04-25
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034844661 — CTR sock pit nirman shantidham east | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034844663 — CTR sock pit nirman shantidham west | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034844667 — CTR sock pit nirman shantidham north | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034844670 — CTR sock pit nirman shantidham south | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006030/WC/22012034900019 — Nala Tranching asraf ke khet ke pass nala | Completed | 229413.61 | 224364 | 2022-02-11 | 2022-08-20
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006030/WC/22012034900021 — Nala Tranching asraf ke khet ke pass nala | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012034906082 — Nala Tranching Rajak kha ke ket ke pass | Completed | 264708.01 | 262528 | 2022-02-06 | 2022-07-30
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006030/WC/22012034970779 — Nala Tranching Talib kha ke khet ke pass | Completed | 170564.64 | 99595 | 2022-05-26 | 2024-12-05
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006030/WC/22012035014854 — sankirn pond nirman utwas marg jhalariya | Completed | 635958.51 | 548601 | 2023-05-28 | 2024-07-12
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006030/WC/22012035075867 — Parcolation tank nirman akram kha ke khet ke pass jhalariya | Completed | 357162.05 | 283296 | 2023-06-20 | 2024-07-21
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006030/WC/22012035207141 — Nala Tranching Nirman Rashid kha ke Pass karadiya | Deleted | 0 | 0 | 2024-06-07
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006030/WC/22012035207159 — Nala Tranching Nirman Rashid kha ke Pass karadiya | Completed | 394200.2 | 330391 | 2024-06-26 | 2025-01-29
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006030/WC/22012035224956 — Dug Pond Nirman Jhalariya | Approved | 0 | 0 | 2024-10-02
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006030/WC/22012035225441 — Dug Pond Nirman Palduna Marg pr | Physically Completed | 402263.24 | 329546 | 2024-12-17 | 2026-04-02
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006030/WH/22012034331886 — तालाब जीर्णोद्धार एवम मरम्मत कार्य | Closed | 0 | 0 | 2018-04-14