## Work List
Exported on: 2026-09-28 17:08:43
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: KHARSODKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006041/AV/22012034550782 — AANGANVADI BHAVAN KENDRA KRAMANK 1 KHARSOD KHURD | Completed | 180000 | 178033 | 2021-04-20 | 2024-08-12
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006041/AV/22012034550783 — AANGANVADI BHAVAN KENDRA KRAMANK 5 NAT MOHLLA KHARSOD KHURD | Closed | 0 | 0 | 2020-10-02
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006041/AV/22012034550784 — AANGANVADI BHAVAN KENDRA KRAMANK 5 NAT MOHLLA KHARSOD KHURD KHARSOD KHURD | Completed | 180000 | 174511 | 2021-04-28 | 2026-02-19
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006041/AV/22012034551915 — AANGANVADI BHAVAN KENDRA KRAMANK 6 TEJAJI CHOK KHARSOD KHURD | Closed | 180000 | 0 | 2020-10-02
BADNAGAR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1718006041/AV/22012034574195 — SEGARIGATION SHED KHARSODKHURD | Closed | 588610.25 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1718006041/AV/22012034575407 — Dinning Hall Kharsodkhurd | Closed | 16093.2 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006041/AV/22012034575708 — Samudayik Naadep Nirman Kharsodkhurd | Closed | 60154.51 | 0 | 2021-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006041/AV/22012034659975 — Aanganwadi bhavan 6 kharsodkhurd | Physically Completed | 180000 | 106462 | 2024-09-24 | 2026-03-09
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006041/DP/22012034535502 — block plantation shamshan ghat ke pas mataji tekari par kharsodkhurd | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006041/DP/22012034535673 — samudayi vriksharopan karya kharsodkhurd shamshanghat kramank 1 | Closed | 685575.78 | 11772 | 2021-09-18
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006041/DP/22012034535675 — samudayi vriksharopan karya kharsodkhurd shamshanghat kramank 2 | Closed | 685575.78 | 5946 | 2021-10-18
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006041/DP/22012034535676 — samudayi vriksharopan karya kharsodkhurd shamshanghat kramank 3 | Closed | 685575.78 | 11688 | 2021-09-18
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006041/DP/22012034535677 — samudayi vriksharopan karya kharsodkhurd shamshanghat kramank 4 | Closed | 685575.78 | 20844 | 2021-10-18
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1718006041/DP/22012034535678 — samudayi vriksharopan karya kharsodkhurd shamshanghat kramank 5 | Closed | 685575.78 | 0 | 2021-08-15
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006041/DP/नंदन फलोद्यान रतनलाल थावरजी खरसौदखुर — नंदन फलोद्यान रतनलाल थावरजी खरसौदखुर्द | Completed | 48200 | 1307 | 2008-08-26 | 2011-04-02
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006041/DP/नंदन फलोद्यान विष्‍णुदास सीतारामदास — नंदन फलोद्यान विष्‍णुदास सीतारामदास खरसौदखुर्द | Completed | 48200 | 5114 | 2008-08-18 | 2012-02-21
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006041/IF/22012034354634 — VRAKSHA ROPAN school parisar (HI+MI)(TS2908/25.04.2017) | Completed | 335000 | 32550 | 2017-07-12 | 2020-08-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/22012035042077 — rekha bai pati vikram pm avas | Completed | 18360 | 18350 | 2023-01-13 | 2024-01-30
BADNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718006041/IF/22012035440584 — Dug well recharge structure mahesh / hiralal gp kharsodkhurd | Completed | 25899.46 | 15689.21 | 2025-05-04 | 2026-04-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006041/IF/22012035521935 — JGSA badrilal pita bherulal khet talab gp kharsodkhurd | Physically Completed | 55865.38 | 39343.41 | 2025-05-18 | 2026-02-22
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006041/IF/22012035532759 — JGSA vikram pita ambalal ji khet talab gp kharsodkhurd | Physically Completed | 450885.64 | 280422 | 2025-05-25 | 2026-02-22
BADNAGAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006041/IF/2जितेन्‍द् — खरसौदखुर्द कुप निर्माण जितेन्‍द्र सुरेश तोलाराम (471/15.3.11) | Completed | 256000 | 207662 | 2011-04-01 | 2012-11-14
BADNAGAR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006041/IF/2महेश — खरसौदखुर्द कुप निर्माण महेश हिरालाल (470/15.3.11) | Completed | 256000 | 249797 | 2011-04-01 | 2012-11-14
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718006041/IF/9926732145 — KPIK DARA KUP DHANALAL-TULSIRAM-(TS-269/30/12/2013 | Completed | 272309 | 215267.6 | 2014-05-29 | 2017-09-08
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/9993744574 — IAY(JIVAN-MOHANLAL TS-436/08-09-2015)) | Completed | 14310 | 13026 | 2016-06-09 | 2017-12-06
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/9993744583 — IAY(PREMLATA-LALSINGH TS-436/08-09-2015) | Completed | 14310 | 13026 | 2016-06-09 | 2017-12-06
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006041/IF/9993750666 — IAY NASIMBANO -IDASHA (TS436/08-09-2015) | Deleted | 14310 | 0 | 2016-07-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/4264533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121618177 | Completed | 18360 | 18112 | 2022-11-08 | 2023-06-06
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/46763 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/493 | Completed | 14310 | 13193 | 2016-09-02 | 2017-10-16
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/46764 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/64 | Completed | 14310 | 12204 | 2017-03-10 | 2017-10-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/4999272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115831777 | Physically Completed | 23490 | 16182 | 2025-04-20 | 2026-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/4999529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116242275 | Completed | 23490 | 23490 | 2025-04-20 | 2026-04-04
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/5497668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116260925 | Ongoing | 23490 | 20880 | 2025-05-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/5497942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115831631 | Completed | 23490 | 22446 | 2025-05-16 | 2026-01-28
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/5498434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116004080 | Physically Completed | 23490 | 4959 | 2025-05-16 | 2026-03-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/5625583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117769149 | Completed | 23490 | 23490 | 2025-07-14 | 2025-11-15
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/92992 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/176 | Completed | 14310 | 13026 | 2016-12-06 | 2023-08-02
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/92993 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/339 | Completed | 14310 | 13206 | 2016-12-06 | 2017-10-16
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/92994 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/49 | Completed | 14310 | 13026 | 2016-12-06 | 2017-10-16
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/93711 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/246 | Approved | 23490 | 0 | 2015-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/93712 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/12 | Approved | 23490 | 0 | 2015-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/93713 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/299 | Approved | 23490 | 0 | 2015-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006041/IF/IAY/93797 — Construction of IAY House -IAY REG. NO. MP-18-006-041-001/248 | Approved | 23490 | 0 | 2015-10-03
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006041/LD/14 — 1718006041/LD/14 | Completed | 320000 | 201678.9 | 2013-02-25 | 2015-03-31
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034171632 — CC ROAD+NALI BADRILAL SE BABULAL (TS-488/06/10/201 | Completed | 197830 | 177407 | 2013-06-17 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034175342 — cc road hemraj se anganwadi(ts-1099/04.03.2013) | Completed | 209500 | 203602.25 | 2013-07-18 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034175344 — cc road shitlamata se ishwar chacha(ts-483/06.10.2 | Completed | 197830 | 179379.8 | 2013-07-18 | 2015-04-02
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034189775 — cc road nali harijan basti mangupuri N+ san | Completed | 209500 | 175908 | 2013-10-11 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/22012034191513 — ANTRIK MARG TEJAJI CHOCK SE KABIR(TS-144/5.9.13) | Completed | 356000 | 326505.6 | 2013-11-08 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034213229 — cc road+nali+pm road se banshi maharaj ki (551/31/ | Completed | 103000 | 137214 | 2014-03-15 | 2015-06-04
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/22012034216736 — AANTRIK MANRG DHANNABHAGT SE KABIR AASRAM 144-5.9.14 | Completed | 358262 | 295647.8 | 2014-04-25 | 2015-06-04
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006041/RC/22012034219258 — KHETSADK SHAN KAR SE ASHOK MAKVANA KE KUYETAK(TS-4 | Completed | 1387000 | 1307816.3 | 2014-05-29 | 2016-11-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006041/RC/22012034221141 — KHET SADAK BADNAGAR VALA RASTA( TS-46/26-5-2014 AS | Completed | 1455000 | 815693.6 | 2014-06-13 | 2016-11-26
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034231720 — PP+MN+CC TEJAJI CHOK SE BHARATLAL(TS-268/30/12/12AS-176/06/01/2014) | Deleted | 160700 | 0 | 2013-10-02
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034264228 — DPRcc road +nali nirman PARVATA BAI KE GHAR SE PRAHLAD KE GHAR TAK | Closed | 5000 | 0 | 2014-10-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034264732 — DPR cc+nali nirman GOPAL KE GHAR SE MADANLAL JI SARPANCH KE GHAR TAK | Completed | 34000 | 16856 | 2017-10-07 | 2018-07-23
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034301924 — DPR CC Road+ NALI NIRMAN TEJAJI CHOK SE SURESH KE GHAR TAK | Completed | 85000 | 54012 | 2017-10-12 | 2018-08-17
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034302209 — DPR cc road +nali nirman SHIVNARAYAN KE GHAR SE ASHOK KE GHAR TAK | Closed | 5000 | 0 | 2016-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034323214 — CC ROAD AND NALI NIRMAN PM ROAD SE DILIP KE GHAR TAK (AS-101/26-01-2017) | Completed | 36000 | 36006 | 2017-06-28 | 2020-07-15
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034345235 — DPR CC ROAD AND NALI NIRMAN SCHOOL PULIYA SE BANSHILAL KE GHARTAK (AS-103/26-01-2017) | Completed | 49000 | 48816 | 2017-07-24 | 2018-07-07
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034371095 — सीसी रोड +नाली | Closed | 0 | 0 | 2018-04-01
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034392459 — cc road chmppa lal ke ghar se bhawar lal ke ghar tak | Physically Completed | 20000 | 27288 | 2019-11-14 | 2021-04-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034440168 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034448129 — cc road nalinirman EGS school se kasiram ke gar tak | Completed | 129000 | 133512 | 2019-03-08 | 2020-07-15
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034463539 — cc road nali nirman champalal ke gar se bhanvarlal ke gar tak kharsodkhurd | Closed | 21000 | 0 | 2019-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034463549 — cc road nirman suresh ke gar se kabir asram tak kharsodkhurd | Closed | 145000 | 0 | 2019-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034463563 — cc road niman ajad chouk se bavadi tak kharsodkhurd | Closed | 24000 | 0 | 2018-10-02
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034463567 — cc road nali nirman pratap chodhry ke gar se babulal ke gar tak kharshodkhurd | Closed | 32000 | 0 | 2018-10-02
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034463579 — cc road nirman pm road se prathmik school tak kharsod khurd | Closed | 152000 | 0 | 2018-10-02
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034471864 — सीसी रोड पंचायत भवन के सामने | Physically Completed | 18000 | 360 | 2020-07-16 | 2021-04-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034471865 — बगदीराम के घर से पि.एम्.सड़क तक | Closed | 26000 | 0 | 2019-04-01
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034471866 — सीसी रोड नाली पुलिया से सत्यनारायण राठोर के घर तक | Completed | 145000 | 104344 | 2019-11-27 | 2021-09-25
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034555274 — cc road धर्मशाला से santidham की और | Completed | 107000 | 103740 | 2021-01-08 | 2021-08-15
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034555357 — cc road मोटर पम्प से दुर्गा बाई ke ghar की और | Closed | 56000 | 0 | 2020-12-29
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006041/RC/22012034569056 — Sudur Sampark Nirman Madhyamik vidhiyale bhavan se bhavani mata mandir tak | Physically Completed | 2811504.27 | 2533207.08 | 2021-06-22 | 2026-04-10
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034682870 — cc rod+nali nirman ramchandra dhobi ke ghar se ambaram dhobi ke ghar ki or | Completed | 28000 | 19465 | 2024-03-16 | 2024-06-29
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034682873 — ccrod pm rod se shankar marvada ke ghar ki or | Completed | 24000 | 19465 | 2024-03-16 | 2024-06-29
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/22012034825079 — cc rod+nali nirman prhalad balai ke ghar se ashok bhil ke ghar ki or | Physically Completed | 41000 | 40530.88 | 2024-08-30 | 2026-03-09
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/29अर्थवर्क — अर्थवर्क tejaji chok (489/16.6.11) | Completed | 497000 | 491050 | 2011-06-21 | 2013-11-07
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/29सीमेन्‍ट — सीमेन्‍ट कांक्रीट कार्य नाली स‍हीत ‍िव+म ‍खरसोदखुद (57/26.9.11) | Completed | 300000 | 195498 | 2011-12-01 | 2012-07-05
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/2खरसौदखुर् — खरसौदखुर्द अर्थवर्क खरसौदखुर्द से गावडीलौधा भाग 1 खरसौदखुर्द | Completed | 700000 | 444261 | 2009-01-06 | 2011-07-26
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/35Antrik m — Antrik marg Muramikaran Pradhan mantri sadak ma.vidhyalay ( T/S175 /12.06.2012) | Completed | 208000 | 122236 | 2013-01-18 | 2013-11-07
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/35 नाली ‍ि — नाली ‍िनमाण PP+ M Bagri Mohalla Aja Basti (T/S 32 /04.06.2012) | Completed | 210000 | 199836 | 2012-10-01 | 2013-11-07
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006041/RC/37सी सी रो — 1718006041/RC/37सी सी रो | Completed | 74333 | 67023 | 2013-02-08 | 2015-02-17
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/3खरसोदखुर् — खरसोदखुर्द अर्थवर्क खरसोदखुर्द से गावडीलोधा काकड भाग 2 खरसोदखुर्द | Completed | 500000 | 443630 | 2009-01-23 | 2011-07-26
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006041/RC/3 खरसौद खु — खरसौद खुर्द मुरमीकरण सतवामहल से किलोली की और | Completed | 493000 | 256840 | 2008-09-01 | 2010-09-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034193566 — DINESH-MUNNALAL NIRMAL BHARAT( as/184/06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034193575 — NIRMAL BHART(DASHRATH - HRISINGH AS-183/6-1-2014) | Completed | 4400 | 4388 | 2014-03-08 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034195892 — RATN SINGH NAHR SINGH (AS-174/06/09/2013) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034195900 — NIRMAL BHART RAKESH-KISHANLAL(AS-181-06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197410 — NIRAML BHART BDRILAL-KISHANLAL(AS173/06-09-213) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197417 — NIRMAL BHART RAJESH-KALU SINGH(AS-185/6/1/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197419 — NIRMAL BHART LALSINGH-BHOM SINGH(AS-175/06/09/2013 | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197420 — NIRMAL BHART DYARAM-SHOBHARAM(AS-180/21/1/2013) | Deleted | 0 | 0 | 2012-08-16
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197422 — NIRMAL BHART GITA BAI-GIRDHARILAL(AS-186/06/01/201 | Completed | 5111 | 4429 | 2014-06-04 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197424 — NIRMAL BHART JITENDRA-BANSHILAL(AS-187/06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197426 — NIRMAL BHART BHARTLAL-RAMNARAYN(AS-182/06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197428 — NIRMAL BHART RAMKNYA-BABULAL(AS-179/06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197431 — NIRMAL BHART BHAVARSINGH-LAL SINGH(AS-188/06/01/20 | Deleted | 4400 | 0 | 2012-08-16
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197434 — NIRML BHART BHERUSINGH-RAMSINGH(AS-215/28/1/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034197436 — NIRMAL BHART SHIVNARAYN-BABULAL(AS-194/06/01/2014) | Completed | 4400 | 4388 | 2014-03-07 | 2015-05-12
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034211768 — NIRMAL BHART VIKRAM-BABULAL(AS-177/6/1/2014) | Completed | 4400 | 4429 | 2014-06-04 | 2015-05-15
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034211786 — NIRMAL BHART KELASH DAS-RAMDAS(AS-178/6/1/2014) | Deleted | 4400 | 0 | 2012-08-15
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034211792 — NIRMAL BHART MANGILAL-DAYARAM(AS-197/28/01/2014) | Deleted | 4400 | 0 | 2012-08-15
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034211796 — NIRMAL BHART MANGILAL-BHERAJI(AS-203/28/1/2014) | Deleted | 4400 | 0 | 2012-08-15
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034213574 — NIRMAL BHART GOPAL-THAVAR(AS-205/28/01/2014) | Deleted | 4400 | 0 | 2012-08-15
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034213595 — NIRMAL BHART DINESH-KELASHCHAND(AS-206/28/01/2014) | Deleted | 4400 | 0 | 2012-08-15
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034238240 — NIRMAL BHARAT VJESINGH-RADHAKISAN(TS-248/16/08/201 | Completed | 5111 | 4429 | 2014-06-04 | 2015-05-15
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/22012034239118 — NIRMAL BHART ARJUNSINGH-AJAYSINGH(TS-01/17/04/2014 | Deleted | 5111 | 0 | 2014-05-27
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006041/RS/22012034706077 — Samudayik shochalay Nirman bhavani mata mandir | Completed | 47000 | 22071 | 2023-10-06 | 2024-07-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28329 — NIRMAL BHARAT MANGILAL GANPAT (A/S 103 21/01/2013) | Completed | 4312 | 4353 | 2013-06-04 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28333 — NIRMAL BHARAT RADHESHAM MANOHARLAL (A/S 104 21/01/ | Completed | 4312 | 4353 | 2013-06-04 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28335 — NIRMAL BHARAT RAMCHANDRA KANIRAM (A/S 105 21/01/20 | Completed | 4312 | 4353 | 2013-06-04 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28340 — NIRMAL BHARAT MUKESH HIRAJI (A/S 106 21/01/2013) | Completed | 4312 | 4353 | 2013-06-04 | 2014-04-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28342 — NIRMAL BHARAT BADRILAL DEVAJII (A/S 107 21/01/2013 | Completed | 4312 | 3628 | 2013-06-19 | 2015-12-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/28346 — NIRMAL BHARAT MOHANLAL BHERULAL (A/S 108 21/01/201 | Deleted | 4312 | 0 | 2013-06-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/32230 — NIRMAL BHARAT PRAHLAD NANURAM (AS-117/21/01/2013) | Completed | 4312 | 4353 | 2013-06-15 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/32593 — NIRMAL BHARAT GOVERDHAN S/O RAM CHANDRA(AS-116/21. | Deleted | 4312 | 0 | 2013-06-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/32879 — NIRMAL BHARAT BHARATLAL SUKHRAM(AS-109/21.01.2013) | Completed | 4312 | 4353 | 2013-06-15 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33835 — NIRMAL BHARAT KISHOR RADHAKISHAN (AS-111/21.01.201 | Completed | 4312 | 4353 | 2013-06-15 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33842 — NIRMAL BHARAT MANGUBAI MADANLAL (AS-21/01/2013) | Completed | 4312 | 4423 | 2013-06-19 | 2015-12-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33854 — NIRMAL BHARAT LEELA BAI BABULAL (AS-113/21.01.2013 | Deleted | 4312 | 0 | 2013-06-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33896 — NIRMAL BHARAT BAGDIRAM GANPAT (AS-114/21/01/2013) | Completed | 4312 | 4353 | 2013-06-15 | 2013-12-19
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33905 — NIRMAL BHARAT RAMCHANDRA AMBARAM(AS-115/21.01.2013 | Deleted | 4312 | 0 | 2012-07-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/33910 — NIRMAL BHARAT MANOHARLAL RAMCHANDRA (AS-110/21/01/ | Completed | 4312 | 4353 | 2013-06-15 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55477 — nirmal bharat ghanshyam devisingh(as-118/21.01.201 | Completed | 4312 | 4394 | 2013-08-10 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55484 — nirmal bharat badri uday(as-119/21.01.2013) | Completed | 4312 | 3609 | 2013-08-10 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55557 — nirmal bharat kailash meghaji(as-136/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55561 — nirmal bharat harisingh mangilal(as- 120/21.01.201 | Completed | 4312 | 4353 | 2013-08-10 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55564 — nirmal bharat bhagwan mangilal(as-121/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55568 — nirmal bharat mukesh tejaram(as-122/21.01.2013) | Deleted | 4312 | 0 | 2013-08-10
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55572 — nirmal bharat kailash wardaji(as-123/21.01.2013) | Completed | 4312 | 4394 | 2013-08-10 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55576 — nirmal bharat suresh prahlad(as-124/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55582 — nirmal bharat kachru narayan(as-125/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55589 — nirmal bharat dinesh uday(as-126/21.01.2013) | Completed | 4312 | 4423 | 2013-08-10 | 2015-12-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55591 — nirmal bharat shankar hariram(as-127/21.01.2013) | Completed | 4312 | 2703 | 2013-08-10 | 2016-09-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55595 — nirmal bharat goverdhan jagannath(as-128/21.01.201 | Completed | 4312 | 4394 | 2013-08-10 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55599 — nirmal bharat ishwar heera(as-129/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2014-04-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55604 — nirmal bharat bheru ramsingh(as-130/21.01.2013 | Deleted | 4312 | 0 | 2013-08-10
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55607 — nirmal bharat mahadev rajaram(as-131/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55610 — nirmal bharat sohan fatehsingh(as-132/21.01.2013) | Deleted | 4312 | 0 | 2013-08-10
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55614 — nirmal bharat rameshwar sajjan(AS-133/21.01.2013) | Deleted | 4312 | 0 | 2012-08-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/55619 — nirmal bharat antar bapulal(134/21.01.2013) | Completed | 4312 | 4394 | 2013-08-10 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56617 — nirmalbharat bhawar bhagirath(as-135/21.01.2013) | Completed | 4312 | 4353 | 2013-08-10 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56808 — Nirmal Bharat Umrav Bai Ambaram(A/S 137/21/01/2013 | Completed | 4312 | 4353 | 2013-08-21 | 2015-05-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56810 — nirmal bharat ishwar jagannath(as-157/21.01.2013) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56811 — Nirmal Bharat Dharmendra Kaniram(A/S 138/21/01/201 | Deleted | 4312 | 0 | 2012-08-14
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56814 — nirmal bharat radheshyam narsingh(as-158/21.01.201 | Completed | 4312 | 4353 | 2013-08-29 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56815 — Nirmal Bharat Mohanlal Bapuji(A/S 139/21/01/2013) | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56817 — Nirmal Bharat Kanhaiyalal Bheraji(A/S 140/21/01/20 | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56818 — nirmal bharat babu gangaram(as-159/21.01.2013) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56820 — nirmal bharat sajjan bai hari(as-160/21.01.2013) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56824 — Nirmal Bharat Prabhulal kaniram(A/S 141/21/01/2013 | Deleted | 4312 | 0 | 2012-08-14
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56826 — nirmal bharatparvata badrilal(as-162/21.01.2013) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56828 — Nirmal Bharat Radheshyam Nagji(A/S 142/21/01/2013) | Completed | 4312 | 4353 | 2013-08-21 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/56850 — nirmal bharat ratan bheru(as-163/21.01.2013) | Completed | 4312 | 4353 | 2013-08-27 | 2015-05-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57426 — tajsingh gasiram(ts-248/16.08.2012) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57434 — ramchandra mangilal(as248/16.08.2012) | Deleted | 4312 | 0 | 2012-08-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57436 — madanlal ratanlal(as-248/16.08.2012) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57439 — raysingh fatesingh (as-248/16.08.2012) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57442 — laxman mohanlal(as248/6041/16.08.2012) | Deleted | 4312 | 0 | 2013-08-27
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57447 — umaravbai ambaram (as-248/6041/16.08.2012) | Deleted | 0 | 0 | 2012-08-16
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57471 — govardhan chogalal (as-248/6042/16.08.2012) | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57474 — kamalsingh mansingh(as-248/6041/16.08.2012) | Completed | 4312 | 4353 | 2013-08-21 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57477 — ramesh ganpat(as-248/6041/16.0.2012) | Completed | 4312 | 4353 | 2013-08-21 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57480 — ramlal lalji(as-248/6041/16.08.2012) | Completed | 4312 | 2703 | 2013-08-21 | 2015-12-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57483 — suresh ramchandra(as-248/6041/16.08.2012) | Completed | 4312 | 4353 | 2013-08-21 | 2013-12-19
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57508 — ganshyam thavar (as-248/6041/16.08.2012) | Completed | 4312 | 4423 | 2013-08-21 | 2015-12-25
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57512 — hemraj fatesingh(as-248/6041/16.08.2012) | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57516 — sataynaryan kishorlal(as-248/6041/16.08.2012) | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57521 — isvarlal radhakishan(as-248/6041/16.08.2012) | Completed | 4312 | 4423 | 2013-08-21 | 2016-11-26
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57527 — sankarlal devilal(as-248/6041/16.08.2012) | Deleted | 4312 | 0 | 2013-08-21
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57532 — balu bhgirath (as-248/6041/16.08.2012) | Deleted | 4312 | 0 | 2012-08-15
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006041/RS/57536 — gopal ramaji (as-248/6041/16.08.2012) | Completed | 4312 | 2703 | 2013-08-21 | 2016-09-21
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006041/WC/22012034428269 — MWC chek dem nirman shamshan ke pas | Suspended | 653000 | 43950 | 2018-12-22
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006041/WC/22012034428272 — MWC chek dem girdhari rathor avm rajkumar ke khet ke pas | Suspended | 642000 | 33450 | 2018-12-22
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006041/WC/22012034438664 — check dam nirman | Closed | 0 | 0 | 2018-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034828821 — CTR Sock Pit Nirman shamshan pr | Completed | 14467.3 | 4053 | 2021-09-27 | 2026-01-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034828824 — CTR Sock Pit Nirman school ke pass | Completed | 14467.3 | 4053 | 2021-09-27 | 2026-01-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034828826 — CTR Sock Pit Nirman shiv mandir | Completed | 14467.3 | 4053 | 2021-09-27 | 2026-01-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034828827 — CTR Sock Pit Nirman bus stand | Completed | 14467.3 | 2702 | 2021-09-27 | 2026-01-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034828829 — CTR Sock Pit Nirman bus stand sharma tant ke pass | Completed | 14467.3 | 1351 | 2021-09-27 | 2026-01-28
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034838059 — CTR Rain Water Harvesting school pr | Closed | 16878.31 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034838064 — CTR Rain Water Harvesting school 2 | Closed | 16878.31 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034848524 — CTR Sock Pit Nirman shantidham 1 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034848526 — CTR Sock Pit Nirman shantidham 1 | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034848530 — CTR Sock Pit Nirman shantidham 2 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034848536 — CTR Sock Pit Nirman shantidham 3 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034848539 — CTR Sock Pit Nirman shantidham 4 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849187 — CTR Sock Pit Nirman krashi mahavidhiyale 1 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849192 — CTR Sock Pit Nirman krashi mahavidhiyale 2 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849195 — CTR Sock Pit Nirman kaniya shala 1 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849203 — CTR Sock Pit Nirman kaniya shala 2 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849208 — CTR Sock Pit Nirman aaganawadi nat mohala ke smane | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849214 — CTR Sock Pit Nirman bus stand | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849220 — CTR Sock Pit Nirman tejaji chok | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849224 — CTR Sock Pit Nirman rajput mohala | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849227 — CTR Sock Pit Nirman mongiya basti 1 | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006041/WC/22012034849232 — CTR Sock Pit Nirman kabir ashram | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006041/WC/22012035181940 — Nala Tranching Puliya se Dharmendra ke ghar ki aur | Completed | 226205.96 | 171225 | 2024-03-14 | 2024-07-27
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1718006041/WC/7निर्मल नी — निर्मल नीर सार्वजनिक कूप KHARSODKHURD (49/02.5.12) | Completed | 499200 | 402533.5 | 2013-02-04 | 2016-11-25
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006041/WH/19963691 — तालाब जीर्णोद्धार मरम्मत कार्य Kharsodkhurd TS-190/23.5.17 | Closed | 478000 | 0 | 2017-06-13
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006041/WH/22012034932350 — PDW Talab jinodhar shaskiya talab kharsodkhurd | Closed | 44000 | 0 | 2022-04-14
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | /SK/98 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KHARSODKHURD | Completed | 1251000 | 998040.88 | 2013-12-20 | 2017-11-14