## Work List
Exported on: 2026-09-28 18:00:26
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: LAKHESARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006045/AV/22012034584121 — Construction of Dining Hall Nirman | Closed | 0 | 0 | 2021-04-14
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1718006045/DP/22012034607232 — SHANTI DHAM ME PAYJAL VYAVSTHA AVM SODARIYAKARAN | Ongoing | 107000 | 20112 | 2024-03-09
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/DW/9993653953 — RECHAGRE PIT NIRMAN LAKHESARA ts-75/12.6.15 unit 5 | Completed | 32500 | 30638.95 | 2015-06-20 | 2016-03-30
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1718006045/FP/22012034626575 — Retaining Wall nirman | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006045/IF/22012034323616 — AAY MUNA LAL-ATMARAM(TS-127-26/09/2016 | Completed | 15030 | 14362 | 2017-03-03 | 2017-09-04
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012034342378 — VARKSHA ROPAN KARY KHEL MEDAN NIMBU CHAPRA LAKHESHRA | Deleted | 0 | 0 | 2017-04-14
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012034342400 — VARKSHA ROPAN KARY KHEL MEDAN LAKHESHRA | Completed | 335000 | 72884 | 2017-05-25 | 2020-08-05
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012034357979 — VARKSHA ROPAN SCHOOL PRAGAN MASVADIYA KHALSA | Completed | 335000 | 71486 | 2017-07-07 | 2020-08-05
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012034357982 — vriksharopan 4 | Deleted | 335000 | 0 | 2017-08-09
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012034359238 — VRIKSHAROPAN LAKHESARA | Closed | 335000 | 0 | 2017-04-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/22012035513893 — JGSA khet talab Tolaram pita pira gp lakhesara | Completed | 450885.64 | 125802 | 2025-05-16 | 2026-03-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/22012035544841 — JGSA 2025 khet talab Vedo Sayer bai W/O gangaram GP Lakhesara | Physically Completed | 450885.64 | 307719 | 2025-05-24 | 2026-03-11
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/22012035546093 — JGSA 2025 khet talab Rajkumari Bai W/O bhagwan singh GP Lakhesara | Physically Completed | 450885.64 | 187251 | 2025-05-24 | 2026-04-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012035602078 — EK BAGIYA MAA KE NAAM SUGNA BAI KAMAL LAKHESARA | Ongoing | 161149.72 | 0 | 2025-09-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012035618366 — EK BAGIYA MAA KE NAAM RAMKUNWAR BAI KALURAM LAKHESARA SHG CODE 170039859925 | Ongoing | 263510.03 | 261 | 2025-09-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012035636026 — EK BAGIYA MAA KE NAAM PARVATIBAI NARSINGH LAKHESARA SHG CODE 17001687267 | Deleted | 0 | 0 | 2025-08-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006045/IF/22012035636030 — EK BAGIYA MAA KE NAAM SEEMA RAMESHWAR LAKHESARA SHG CODE 17001687267 | Deleted | 0 | 0 | 2025-08-15
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/9926736299 — bhumi sudhar kailash-bagdiram(ts-87/27.05.2014) | Completed | 105000 | 54222 | 2014-06-11 | 2015-06-04
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/9926736304 — bhumi sudhar ramkuwar-jaswant (ts-85/27.5.14) | Completed | 105000 | 64314 | 2014-06-11 | 2015-06-04
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/9926736318 — bhumi sudhar kailash ataram( ts-86/27.5.14) | Completed | 105000 | 76042 | 2014-06-11 | 2015-06-04
BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/IF/9926736326 — bhumi sudhar mehrban-juwansingh (ts-84/27.5.14) | Completed | 105000 | 69556 | 2014-06-11 | 2015-06-04
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/9993679779 — IAY kailash bai/kishor lal | Completed | 14310 | 6678 | 2015-10-10 | 2016-06-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/9993679785 — iay ramu bai/babu lal | Completed | 14310 | 14310 | 2015-10-10 | 2016-06-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006045/IF/9993685523 — BHUMI SUDHAR(MUKESH-RAMKISHAN)TS-184-28/10/2015 | Completed | 101000 | 65826 | 2015-11-06 | 2016-06-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006045/IF/9993685717 — BHUMI SUDHAR(MANGI LAL-SHANKAR LAL)181/28/10/2015 | Deleted | 101000 | 0 | 2015-08-15
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006045/IF/9993685854 — BHUMI SAMTALIKARAN(MANGILAL-SHANKAR LAL)TS-181/28/10/2015 | Completed | 101000 | 67734 | 2015-11-06 | 2016-06-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006045/IF/9993685975 — BHUMI SAMTALIKARAN(BHERU LAL-DEV JI)TS-182/28/10/2015 | Deleted | 0 | 0 | 2015-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006045/IF/9993685977 — BHUMI SAMTALIKARAN(BHERU-DEV JI)TS 182/28/10/2015 | Completed | 101000 | 81090 | 2015-11-06 | 2016-06-17
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/9993695135 — INDRA AWAS MAYA MUKESH | Completed | 14310 | 13356 | 2015-12-12 | 2016-07-03
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/1859188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5203903 | Completed | 15660 | 15660 | 2018-07-01 | 2018-11-30
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/1859298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5192860 | Completed | 15660 | 15660 | 2018-07-01 | 2018-11-30
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/204995 — Construction of IAY House -IAY REG. NO. MP-18-006-045-002/71 | Approved | 23490 | 0 | 2016-03-31
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/226315 — Construction of IAY House -IAY REG. NO. MP1248275 | Completed | 15030 | 15818 | 2017-02-03 | 2017-09-01
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/234095 — Construction of IAY House -IAY REG. NO. MP1387395 | Completed | 15030 | 15818 | 2017-02-06 | 2017-08-01
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/270270 — Construction of IAY House -IAY REG. NO. MP2639833 | Completed | 15030 | 15818 | 2017-02-06 | 2017-09-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3692002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106642162 | Completed | 18360 | 18190 | 2022-07-04 | 2023-05-10
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3695784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113854932 | Approved | 23490 | 0 | 2022-05-02
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3712950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117876879 | Completed | 18360 | 13712 | 2022-11-22 | 2023-11-02
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3732636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116189853 | Approved | 23490 | 0 | 2022-05-01
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3736300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116248328 | Completed | 18360 | 18202 | 2022-10-04 | 2023-06-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3738802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116264984 | Approved | 23490 | 0 | 2022-05-02
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3820331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117388633 | Approved | 23490 | 0 | 2022-05-02
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3921523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116251000 | Completed | 18360 | 18360 | 2022-07-04 | 2023-05-11
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3921524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116251690 | Completed | 18360 | 17221 | 2022-09-13 | 2023-12-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3923062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113851564 | Completed | 18360 | 18360 | 2022-07-04 | 2022-11-13
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3923799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117404271 | Completed | 18360 | 18360 | 2022-07-26 | 2023-05-11
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3931793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114061107 | Completed | 18360 | 18360 | 2022-08-06 | 2023-01-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3931799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114063002 | Completed | 18360 | 18190 | 2022-07-04 | 2023-05-11
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3936226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115325755 | Completed | 18360 | 18360 | 2022-11-15 | 2023-09-04
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/3936230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115327865 | Completed | 18360 | 17952 | 2022-07-19 | 2022-12-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4299620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115334701 | Completed | 18360 | 18360 | 2022-08-06 | 2023-01-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4328348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118064655 | Completed | 18360 | 17612 | 2022-10-04 | 2023-06-06
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4329022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116246778 | Completed | 18360 | 17136 | 2022-10-04 | 2023-04-14
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4329766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117784647 | Completed | 18360 | 18120 | 2022-08-26 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4329769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117786426 | Completed | 18360 | 17805.4 | 2023-01-05 | 2023-09-16
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4335668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116427466 | Completed | 18360 | 17136 | 2022-10-04 | 2023-04-14
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4378891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113847732 | Completed | 18360 | 18284 | 2022-11-15 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4378898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118079460 | Completed | 18360 | 8806 | 2022-11-15 | 2024-08-25
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4379098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117785518 | Physically Completed | 18360 | 17010 | 2024-05-02 | 2024-11-21
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4688755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644538 | Ongoing | 23490 | 20169 | 2024-10-16
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4754968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117794819 | Physically Completed | 23490 | 21969 | 2025-02-03 | 2026-02-15
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4988914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106640850 | Completed | 23490 | 23049 | 2025-03-22 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4992390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114066225 | Completed | 23490 | 22968 | 2025-09-13 | 2026-01-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4994525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115321503 | Completed | 23490 | 22968 | 2025-06-09 | 2025-12-20
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4997392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115332384 | Completed | 23490 | 23310 | 2025-03-22 | 2026-03-30
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4999520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116239743 | Completed | 23490 | 23310 | 2025-03-22 | 2026-04-22
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4999521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116239759 | Completed | 23490 | 23310 | 2025-03-22 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/4999539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116246742 | Ongoing | 23490 | 2088 | 2025-09-13
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5002478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814844 | Completed | 23490 | 22968 | 2025-08-05 | 2025-12-20
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5003109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117784735 | Completed | 23490 | 23049 | 2025-03-22 | 2025-12-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5246955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116316253 | Completed | 23490 | 22968 | 2025-04-15 | 2026-01-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5247351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118079449 | Completed | 23490 | 22968 | 2025-06-02 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5248890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116253100 | Completed | 23490 | 22968 | 2025-04-10 | 2025-12-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5251641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117404283 | Completed | 23490 | 23490 | 2025-04-30 | 2026-07-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5251757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118079399 | Ongoing | 23490 | 7830 | 2025-07-23
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5252224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643499 | Completed | 23490 | 22707 | 2025-04-10 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5256403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116255544 | Completed | 23490 | 22968 | 2025-04-15 | 2025-12-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5258119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122707290 | Ongoing | 23490 | 18270 | 2025-04-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5260350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116246892 | Completed | 23490 | 22707 | 2025-04-10 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5279654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115322190 | Completed | 23490 | 23229 | 2025-04-30 | 2026-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5282403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812162 | Completed | 23490 | 23490 | 2025-05-18 | 2026-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5285626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117820602 | Ongoing | 23490 | 7308 | 2025-05-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5290032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114060401 | Completed | 23490 | 22707 | 2025-04-10 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5290615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117263947 | Completed | 23490 | 22446 | 2025-04-13 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5291363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117794933 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5292958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113853317 | Completed | 23490 | 22968 | 2025-04-10 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5296859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116246833 | Ongoing | 23490 | 6786 | 2025-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5298212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114058674 | Ongoing | 23490 | 20358 | 2025-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5299660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119577289 | Ongoing | 23490 | 14616 | 2025-04-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5301485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123383353 | Completed | 23490 | 23490 | 2025-04-14 | 2026-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5303765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118079417 | Completed | 23490 | 22707 | 2025-06-02 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5304801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115323511 | Completed | 23490 | 23490 | 2025-04-30 | 2026-07-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5305826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808210 | Completed | 23490 | 23490 | 2025-05-18 | 2026-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5306453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116422279 | Completed | 23490 | 22716 | 2025-04-16 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5310782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117405324 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5312435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113976707 | Completed | 23490 | 22968 | 2025-04-10 | 2025-12-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5312713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116239779 | Ongoing | 23490 | 10440 | 2025-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5316197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118070279 | Completed | 23490 | 22968 | 2025-05-18 | 2025-12-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5316885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115328744 | Ongoing | 23490 | 3654 | 2025-04-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5317750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124785562 | Completed | 23490 | 23490 | 2025-04-15 | 2026-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5319991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117414162 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5321925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114941557 | Completed | 23490 | 22707 | 2025-04-10 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5323757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106637938 | Ongoing | 23490 | 17235 | 2025-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5325295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337192 | Completed | 23490 | 22707 | 2025-04-30 | 2025-12-27
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5328570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118064629 | Completed | 23490 | 22446 | 2025-04-13 | 2026-02-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5330236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117263095 | Completed | 23490 | 23490 | 2025-04-14 | 2026-03-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5330371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117414189 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5333162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117784760 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5334841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117401893 | Completed | 23490 | 22968 | 2025-05-18 | 2025-12-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5335417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808307 | Ongoing | 23490 | 2088 | 2025-09-13
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5341450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339078 | Ongoing | 23490 | 3654 | 2025-04-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5341804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117799539 | Completed | 23490 | 22968 | 2025-08-11 | 2026-03-30
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/541123 — Construction of IAY House -IAY REG. NO. MP3098937 | Completed | 15030 | 14786 | 2017-02-03 | 2017-12-07
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5493330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117794884 | Completed | 23490 | 22968 | 2025-05-04 | 2025-12-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5493883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116422319 | Physically Completed | 23490 | 23490 | 2025-07-09 | 2026-06-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5675459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113846431 | Physically Completed | 23490 | 22707 | 2025-07-28 | 2026-03-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5774726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116255458 | Completed | 23490 | 23490 | 2025-09-13 | 2026-03-30
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5814523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117404294 | Ongoing | 23490 | 16704 | 2026-04-22
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5877114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117416319 | Ongoing | 23490 | 0 | 2026-06-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5877140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113850940 | Physically Completed | 23490 | 15921 | 2026-02-19 | 2026-03-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5877155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114066206 | Physically Completed | 23490 | 12528 | 2026-02-16 | 2026-02-28
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5877160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116419404 | Ongoing | 23490 | 3654 | 2026-04-06
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006045/IF/IAY/5971925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808356 | Approved | 23490 | 0 | 2025-02-23
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/11 — ग्रामीण क्रिडागन खेल मैदान शा Bhumi ग्राम Lakeshra | Completed | 293000 | 278035.3 | 2012-06-21 | 2013-07-29
BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/12ग्रामीण — ग्रामीण क्रिडागन खेल मैदान ग्राम Masvadiya khalsa (T/S 02 /06/04/2011) | Completed | 185000 | 120384 | 2012-06-03 | 2013-03-18
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006045/LD/22012034316524 — SHANTIDHAM SHED NIRMAN GRAM MASWADIYAKHALSA TS7258/9.12.16 AS 103/22.05.17 | Completed | 180018 | 4128 | 2017-07-24 | 2018-06-04
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1718006045/LD/22012034470018 — govt middle school me tarachning or samatlikaran maswadiya khalsa | Closed | 637175.48 | 0 | 2019-08-16
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/22012034538070 — KHEL MEDAN MIDDLE SCHOOL LAKHESRA | Completed | 133216.67 | 63549 | 2021-01-31 | 2022-12-14
BADNAGAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/3799437436 — Khel Medan Masdiya(TS-950/03.0314) | Completed | 500000 | 374758.8 | 2014-04-16 | 2015-06-04
BADNAGAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/3799437438 — shamshan samtalikaran+road(ts-954/3.3.14) | Completed | 481000 | 245006 | 2014-04-16 | 2016-07-03
BADNAGAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006045/LD/3799437439 — khel medan samtalikaran(ts-951/03/03/2014) | Completed | 250000 | 222534.8 | 2014-04-16 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034165785 — ANTRIK MARG PRATHMIK SHALA BHAWAN S HARIJAN MOHALLA | Deleted | 0 | 0 | 2013-04-30
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034165944 — aNTRIKMARG HARIJAN MOHAALA | Deleted | 0 | 0 | 2013-04-17
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034166496 — अर्थ वर्क रोड निर्माण श्री राम मंदिर से धन तालाब ल | Completed | 1500000 | 1294027.71 | 2013-05-16 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034166538 — shashkiya prathmik shala bhawan se ranzor ke ghar | Completed | 100000 | 96091.4 | 2013-05-21 | 2015-06-04
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034166547 — pradhan mathi road se jitendra singh ke ghar tak ( | Completed | 100000 | 84105.5 | 2013-05-14 | 2016-07-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034171321 — Antrik marg masvadiya gopalm k ghar s handpump(T/S | Completed | 100000 | 89782.6 | 2013-06-16 | 2013-07-29
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034208621 — KHAT SADAK NAMALPUR MAN ROAD SE KANKAD TAK (TS-505 | Completed | 1387000 | 1212850.7 | 2014-02-27 | 2015-10-10
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034230742 — Cc road nrega+adimjati rajaram(T/s 208/15/09/2014) | Deleted | 200000 | 0 | 2014-09-30
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034230752 — Cc road nrega+adimjati dinesh(T/s 209/15/09/2014) | Deleted | 200000 | 0 | 2014-09-30
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034264309 — cc road+nali nirman pp+m gram lakhesra | Deleted | 0 | 0 | 2014-10-02
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034264767 — cc+nali nirman mn+pp2 gram abadi lakhesra | Deleted | 0 | 0 | 2014-10-02
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034288288 — SHANTIDHAM PAHUCH MARG LAKHESRA TS188/30.10.2015 AS119/01.11.2015 | Completed | 433000 | 381569 | 2015-11-08 | 2016-07-03
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034288598 — KHET SADAK(RAM MANDIR SE DHANTALAB MARG)TS187/30/10/2015) | Completed | 1461000 | 1247645.2 | 2015-11-08 | 2016-07-03
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034302217 — cc road +nali nirman pp+m | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034302218 — cc road +nali nirman pp+m | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034312876 — NALI NIRMAN BALU SE KAILASH MOGIYA MASWADIYA KHALSA | Completed | 132000 | 130031.55 | 2016-05-20 | 2018-08-10
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034323216 — cc road+nali nirman | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034332759 — CCROAD +NALI NIRMAN DEVNARAYAN MANDIR SE SHANKAR CHOUDHARY KE GHAR KI OR | Completed | 23600 | 23526 | 2017-03-23 | 2018-03-31
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034352226 — DPR CC+NALI NIRMAN MAIN ROAD SE CHAMPU MOGIYA KE GHAR KI OR | Completed | 11300 | 9460 | 2017-09-08 | 2018-04-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034352241 — DPR CC+NALI NIRMAN SANJAY MOGIYA KE GHAR SE JIVAN MONGIYA KE GHAR KI OR | Completed | 8300 | 7052 | 2017-09-24 | 2018-04-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034352244 — DPR CC+NALI NIRMAN MAIN ROAD SE GOPAL MOGIYA KE GHAR KI OR | Completed | 19700 | 16512 | 2017-09-09 | 2018-04-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034361301 — DPR CC+NALI NIRMAN PREM SINGH KE GHAR SE SOCAITY KI OR | Completed | 158000 | 24768 | 2017-09-26 | 2018-06-27
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034362441 — DPR CC+NALI NIRMAN JITENDRA KE GHAR SE SITLA MATA MANDIR HOKAR GOKUL MAHARAJ KE GHAR KI OR | Completed | 44700 | 38012 | 2017-10-03 | 2018-07-08
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034362448 — DPR CC+NALI NIRMAN SHASKIY PRATHMIK SCHOOL SE DASRATH SINGH KE GHAR KI OR | Completed | 33800 | 28896 | 2017-10-10 | 2018-04-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034363006 — DPRcc+nali nirman ataram mogiya ke ghar se ataram balai ke ghar ki or | Completed | 29000 | 28896 | 2017-10-10 | 2018-03-31
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034369657 — DPRcc+nali niman kalu sen ke ghar mangu singh ke ghar tak | Completed | 113000 | 17666 | 2018-06-07 | 2021-09-15
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034371100 — सीसी रोड +नाली | Deleted | 0 | 0 | 2018-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034371691 — SUDHUR GRAM SAMPRAK SADAK NIRMAN NAMLPUR MAIN ROAD SE NAI ABADI KI OR (TS-44/28.11.2017) | Completed | 825000 | 609704.99 | 2017-12-10 | 2019-12-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034391421 — ccroad+nali nirman girdhari ke ghar se bharat ke ghar ki or gram nai abadi maswadiya khalsa | Completed | 54000 | 53340 | 2019-01-17 | 2019-12-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034396785 — cc+nali nirman main road se ambaram raju ji ke ghar ki or | Closed | 6500 | 0 | 2018-08-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034396798 — CC+NALI DEVNARAYAN MANDIR SE RUGNATH CHOUDHARY KE GHAR KI OR | Completed | 12400 | 12320 | 2019-07-17 | 2019-09-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034396806 — CC+NALI BHADAR KE GHAR SE SITLA MATA CHOK KI OR | Closed | 22000 | 0 | 2018-08-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034398074 — CC ROAD+NALI NIRMAN RAMA CHOUDHARI KE GHAR SE RANCHOD CHOUDHARY KE GHAR KI OR | Physically Completed | 11000 | 10560 | 2019-07-17 | 2019-12-10
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034398080 — CC ROAD+NALI NIRMAN RANCHOD KE GHAR SE NAHAR JI KE GHAR KI OR | Completed | 24000 | 23350 | 2019-01-17 | 2019-06-17
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034398085 — CC ROAD+NALI NIRMAN RATAN KE GHAR SE KAILASH KE GHAR KE OR | Completed | 17000 | 16566 | 2019-02-27 | 2019-12-05
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034436202 — CC+NALI NIRMAN MANSINGH KE GHAR SE SITARAM KE GHAR KI OR MASWADIYA | Completed | 36000 | 35106 | 2019-02-08 | 2019-06-17
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034440191 — cc road+nali | Deleted | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034463847 — CC+NALI NIRMAN ISHWAR JAMAI KE GHAR SE SHANKAR KE GHAR KI OR MASWADIYA | Closed | 20000 | 0 | 2019-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034463850 — cc+nali nirman kelash ke ghar se hanpump ki or masvadiya | Closed | 9000 | 0 | 2019-01-26
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034463859 — CC+NALI NIRMAN HARIRAM KE GHAR SE BALU KE GHAR KO OR LAKHESARA | Closed | 13000 | 0 | 2019-01-26
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034463861 — CC+NALI NIRMAN CHENA KE GHAR SE FUNDI LAL JI KE GHAR KI OR LAKHESRA | Completed | 14800 | 14784 | 2019-08-18 | 2019-12-05
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034473604 — CC ROAD NIRMAN SAMANDARSINGH BHATI KE GHAR SE SHAMBUPURI KE GHAR TAK GRAM maswadiya khalasa | Completed | 61000 | 60544 | 2019-09-05 | 2019-12-05
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034519196 — GRAM MASVADIYA ME GRAM AABADI CC ROAD SE SHANTIDHAM TAK PAHUCH MARG | Completed | 371532.34 | 333772.39 | 2020-04-23 | 2022-01-12
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/22012034524818 — SUDAR GRAM SAMPRAK SADAK LAXMAN JI KE KHET SE MANGU SINGH PATEL KE KHET KI OR LAKHESARA | Completed | 1498155.45 | 1475842.88 | 2020-06-17 | 2023-08-01
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034557364 — CC+NALINIRMAN SHYAMSUNDAR KE GHAR SE HANDPUMP KI OR MASWADIYAKHALSA | Completed | 42000 | 43478 | 2021-01-31 | 2021-10-01
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034560562 — NALI NIRMAN MANGI LAL KE GHR SE DASRAT MISTRI KE GHAR KI OR MASWADIYA KHALSA | Completed | 20000 | 20628 | 2021-03-03 | 2021-07-20
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034560564 — CC ROAD NALI NIRMAN DILIP PANDYA KE GHAR SE JAGDISH KE GHAR KI OR MASWADIYA KHALSA | Completed | 10000 | 11400 | 2021-03-07 | 2021-04-15
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034595981 — cc road + nali nirman ranchod choudhari ke ghar se jagdish choudhari ke ghar ki or | Completed | 193000 | 188848 | 2021-11-16 | 2022-04-25
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/22012034665161 — cc road Nirman jagdish chodari ke ghar se manohar singh ke chavada ke ghar | Completed | 43000 | 33617 | 2023-10-07 | 2024-07-09
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/2मुरमीकरण — मुरमीकरण नई आबादी मसवाडिया खालसा लखेसरा | Completed | 36400 | 79558.25 | 2009-02-09 | 2009-03-01
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/3 — शांतिधाम पहुच मार्ग (399/18.1.11) | Completed | 399000 | 336553.22 | 2011-04-02 | 2013-03-18
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/32सी सी रो — सी सी रोङ एवं नाली fनमाण लखेसरा,हनुमान मंदीर से तकेसींह के घर तकPP+M (362/16.02.2012) | Completed | 279300 | 64416 | 2012-05-18 | 2015-06-04
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/33सी सी रो — सी सी रोङ नाली स‍हीत ‍िव+म लखैसरा (129/22.02.2011) | Completed | 300000 | 119804 | 2011-04-06 | 2015-03-30
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/34Arthwork — Arthwork karya nayapur kiloli kakad se bheruji maswadiya (55/15.5.12) | Completed | 500000 | 475264.37 | 2012-05-22 | 2013-03-18
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/34अर्थ वर् — अर्थ वर्क रोड मसवाङीया se kakad tak (4/6.04.2011) | Completed | 497000 | 472450.59 | 2011-05-07 | 2013-03-18
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006045/RC/34सी सी रो — सी सी रोङ नाली स‍हीत आ जा+मनरेगा अजा बस्‍ती गाम लखेसरा(114/08.12.2011) | Completed | 300000 | 111672 | 2012-05-12 | 2015-06-04
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/3 मुरमीकरण — मुरमीकरण लखेसरा से पलदूना काकड तक | Completed | 469249 | 249941.95 | 2009-05-22 | 2009-06-15
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/3लखेसरा अर — लखेसरा अर्थवर्क ग्राम मसवाडिया खालसा से लिंक रोड तक ग्राम लखेसरा | Deleted | 1150000 | 431665.52 | 2009-11-15
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/3लखेसरा ता — लखेसरा तालाब पाल विस्‍तार मसवाडिया खालसा | Completed | 214000 | 198570.04 | 2009-06-20 | 2009-06-26
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006045/RC/5 ?????? ? — Not Known1 | Completed | 0 | 438468 | 2011-04-03 | 2015-11-20
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1718006045/RC/5 लखेसरा अ — लखेसरा अर्थवर्क रोड निर्माण लखेसरा से सोहड मार्ग | Completed | 1473000 | 796139.61 | 2010-04-27 | 2015-11-20
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/6 — अर्थवर्क ( निंबू छापरा से सोहनसिंह के खेत तक) | Completed | 500000 | 358560 | 2010-12-16 | 2013-03-18
BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006045/RC/6 लखेसरा म — लखेसरा मुरमीकरण मसवाडिया खालसा | Completed | 102000 | 114550.19 | 2010-06-01 | 2010-06-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006045/RS/22012034315104 — SBM LILA BAI SHIV NARAYAN(ts-354/05.12.2016)44 JC | Completed | 10800 | 10786 | 2017-01-05 | 2017-10-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006045/RS/22012034315152 — SBM RAJU BAI- LAXMAN(TS-354/05.12..2016) | Completed | 10800 | 10786 | 2017-01-07 | 2017-08-23
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006045/RS/22012034315358 — SBM LAKHAN SINGH-KARAN SINGH(TS-354/05.12.2016) | Completed | 10800 | 10786 | 2017-01-06 | 2017-08-23
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006045/RS/22012034317843 — SBM LAL SINGH-BHARAT SINGH(TS-354/05.12.2016) | Completed | 10800 | 10786 | 2017-01-16 | 2017-02-12
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006045/RS/22012034317851 — SBM RAM SINGH-BHERU SINGH(TS-354/05/12/2016) | Completed | 10800 | 10786 | 2017-01-19 | 2017-08-23
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006045/RS/22012034496114 — SAMUDAYIK SWACHHTA PARISAR LAKHESARA | Completed | 48000 | 27842 | 2020-10-03 | 2021-10-22
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006045/RS/22012034496562 — SAMUDAYIK SWACHHTA PARISAR LAKHESARA | Deleted | 48000 | 0 | 2020-08-15
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006045/RS/22012035124878 — NALI NIRMAN CHANDAR KE GHAR SE CC ROAD KI OR MASWADIYA KHALSA | Closed | 0 | 0 | 2024-01-26
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006045/RS/22012035124879 — NALI NIRMAN CHANDAR KE GHAR SE CC ROAD KI OR MASWADIYA KHALSA | Completed | 20000 | 16996 | 2024-03-09 | 2024-06-29
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718006045/WC/22012034293410 — MWC TALAI PAL VISTAR MASWADIYA KHALSA | Completed | 471400 | 52184 | 2016-05-20 | 2018-06-27
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006045/WC/22012034392227 — navin sankirn talab nirman kary maswadiya | Completed | 510000 | 219381 | 2018-06-17 | 2022-09-21
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/22012034429086 — MWC chek dem avm nala treching ka karay lakheasara | Completed | 951300 | 949379.23 | 2019-01-01 | 2021-08-15
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480033 — RECHARGE PIT HANDPUMP RAJARM CHOUDHARY KE GHAR KE PASS LAKHESRA | Completed | 10857.75 | 9076 | 2019-08-18 | 2021-04-05
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480432 — RECHARGE PITH HANDPUMP NAMAL PUR ROAD MASWADIYA KHALSA | Deleted | 0 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480433 — RECHARGE PITH HANDPUMP AMBARAM BHAT KE GHAR KE PASS NAYA PURA MASWADIYA KHALSA | Closed | 10857.75 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480435 — RECHARGE PITH HANDPUMP MANSINGH JI KE KHET KE PASS MASWADIYA KHALSA | Closed | 10857.75 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480436 — RECHARGE PITH HANDPUMP PANCHAYAT BHAWAN PRAGAN LAKHESRA | Completed | 10857.75 | 9076 | 2019-08-18 | 2021-04-05
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034480437 — RECHARGE PITH HANDPUMP JAGIRDAR KI GADI KE PICHE LAKHESRA | Closed | 10857.75 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/22012034504725 — nala terachking karay masavdiya khalsa | Completed | 621481.05 | 401824 | 2019-11-24 | 2021-10-01
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034580692 — Nala Tranching maswadiya kkhalsa nale par | Completed | 210626.3 | 175630 | 2021-03-18 | 2022-02-01
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/22012034580693 — Check Dam Nirman Maswadiya khalsa nale par | Closed | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair and Maintenance of Stone Spur for Community / Repair and Maintenance of Stone Spur for Community | Repair & maint of Water Harvesting Structures | 1718006045/WC/22012034590805 — NALA TRACHING KARY MASWADIYA KHALSA NAI ABADI KI OR | Completed | 217319.07 | 180360 | 2020-12-30 | 2022-02-01
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1718006045/WC/22012034590806 — NALA TRACHING LIMDI VALA KHAL MASWADIYA KHALSA | Completed | 226011.83 | 189552 | 2020-12-23 | 2022-02-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034776765 — CTR Rain Water Harvesting middle school | Completed | 16878.31 | 9264 | 2021-09-27 | 2022-11-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034776769 — CTR Rain Water Harvesting Aaganwadi Bhavan | Completed | 16878.31 | 6948 | 2021-09-27 | 2022-11-13
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034776774 — CTR Sock Pit Nirman babu bhat ke ghar ke pass handpupm | Closed | 14467.3 | 0 | 2021-04-14
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034776778 — CTR Sock Pit Nirman school ke pass | Completed | 14467.3 | 6948 | 2021-09-27 | 2022-02-21
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034776791 — CTR Sock Pit Nirmansamudayik bhavan ke pass | Completed | 14467.3 | 9264 | 2021-10-11 | 2022-01-12
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034838072 — CTR Sock Pit Nirman 1 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034838075 — CTR Sock Pit Nirman 2 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034850811 — CTR SOCK PITNIRMAN AGANWADI BHAWAN MASWADIYA KHALSA | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858066 — CTR Sock Pit Nirman Handpump kelash bagdiram ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858069 — CTR Sock Pit Nirman handpump pandya ji ke khale ke pass | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858073 — CTR Sock Pit Nirman handpump girghari mongiya ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858076 — CTR Sock Pit Nirman handpump indar singh ke ghar ke pass | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858080 — CTR Sock Pit Nirman Madhiyamik shala bhavan | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858081 — CTR Sock Pit Nirman prathamik school | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858082 — CTR Sock Pit Nirman khel madan 2 | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858084 — CTR Sock Pit Nirman khel madan 3 | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858086 — CTR Sock Pit Nirman khel madan 4 | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006045/WC/22012034858088 — CTR Sock Pit Nirman aaganadi bhavan | Closed | 0 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006045/WC/22012034923926 — PDW तालाब जीर्णोद्धार कार्य, धन तालाब, लखेसरा | Completed | 78000 | 76488 | 2022-03-13 | 2022-08-20
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of gabion Spur for Comm / Repair and Maintenance of Wire crate (gabion) Spur for Community | Repair & maint of Water Harvesting Structures | 1718006045/WC/22012034953762 — NALA TRACHING KARY KHEL MEDAN KE PASS LAKHESRA | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of gabion Spur for Comm / Repair and Maintenance of Wire crate (gabion) Spur for Community | Repair & maint of Water Harvesting Structures | 1718006045/WC/22012034953763 — NALA TRACHING KARY KHEL MEDAN KE PASS LAKHESRA | Completed | 97687.01 | 80954 | 2022-05-10 | 2023-03-31
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1718006045/WC/22012034953770 — NALA TRACHING KARY KHEL MEDAN KE PASS MASWADIYA KHALSA | Completed | 119395.24 | 94817 | 2022-05-10 | 2024-07-08
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1718006045/WC/22012034957432 — TRACHING NIRMAN MASWADIYA KAKAD KE PASS MSAWADIYA KHALSA | Completed | 150717.12 | 126609 | 2022-05-07 | 2023-03-31
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/22012034969305 — Dug Pond Nirman Maswadiya | Closed | 0 | 0 | 2022-04-14
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maintenance of Earthen Spur for Community / Repair and Maintenance of Earthen Spur for Community | Repair & maint of Water Harvesting Structures | 1718006045/WC/22012035086739 — NALA TRACHING SITARAM KE KHET SE SARDAR CHOUDHARY KE KHET KI OR LAKHESRA | Closed | 0 | 0 | 2023-06-08
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006045/WC/22012035122123 — Nala Tranching Nirman Jitaram ke khet se sardar chodari ke khet ki aur | Completed | 368882.48 | 107980 | 2023-10-06 | 2026-04-01
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/22012035185882 — check dam Nirman bhadar bhati ke khet ke pass | Completed | 1042243.2 | 1028268.73 | 2024-05-16 | 2025-02-04
BADNAGAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1718006045/WC/4 — तालाब पाल विस्‍तार गहरीकरण (01/ 21.4.10) | Completed | 100000 | 94066 | 2010-04-26 | 2010-12-06
BADNAGAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1718006045/WC/9993649754 — parkoletion tenk maswadiya(ts-830/3.3.14) | Completed | 240000 | 219281 | 2014-03-07 | 2015-06-04
BADNAGAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006045/WC/9993651155 — TALAI PAL VISTAR (TS-952/03.03.14) | Completed | 246000 | 231350.7 | 2014-04-16 | 2015-06-04
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006045/WH/22012034331897 — तालाब जीर्णोद्धार एवम मरम्मत कार्य | Closed | 0 | 0 | 2018-04-14