## Work List
Exported on: 2026-10-28 08:48:39
Filters applied:
Data source: VBGRAMG
District: UJJAIN
Block: All
Panchayat: BHIDAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1718006079/AV/22012034657023 — nali nirmand gopal lal k ghar se kailas lal k ghar bhidavd kiramk 02 | Approved | 29000 | 0 | 2024-04-14
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718006079/AV/22012034663472 — Shantidham nirman karya pm sadak ke paas | New | 0 | 0 | 2025-01-09
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718006079/AV/22012034663473 — Shantidham nirman karya pm sadak ke paas | New | 0 | 0 | 2025-01-09
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/3994843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142244 | Approved | 27000 | 0 | 2022-05-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/4736450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105819287 | Ongoing | 27000 | 0 | 2024-12-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/4882356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118286243 | Completed | 23490 | 0 | 2025-01-31 | 2026-08-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5175030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142127 | Ongoing | 27000 | 0 | 2025-05-22
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5207584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115665294 | Ongoing | 27000 | 1500 | 2025-08-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5220255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115853082 | Ongoing | 27000 | 6900 | 2025-06-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5221075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009185 | Approved | 27000 | 0 | 2025-02-21
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5224252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114008975 | Ongoing | 27000 | 0 | 2025-08-18
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5768204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118281256 | Physically Completed | 23490 | 0 | 2025-03-10 | 2026-07-26
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5784480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141996 | Approved | 27000 | 0 | 2025-02-21
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/5885026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117803415 | Physically Completed | 23490 | 0 | 2025-02-21 | 2026-07-19
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/6335244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114008379 | Approved | 27000 | 0 | 2025-02-21
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/93441 — Construction of IAY House -IAY REG. NO. MP-18-006-079-001/013 | Approved | 27000 | 0 | 2015-09-16
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006079/IF/IAY/93442 — Construction of IAY House -IAY REG. NO. MP-18-006-079-001/73 | Approved | 27000 | 0 | 2015-09-16
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718006079/RC/22012034819006 — cc road nirmand gopal lal k ghar se narsing lal k ghar bhidavd kirmank 02 | Approved | 40000 | 0 | 2024-04-14
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1718006079/RS/22012034654630 — Nali nirmand ramsingh babar k ghar se sitlamata mandir bhidavd kiramk 2 | Ongoing | 83000 | 0 | 2022-11-18
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1718006079/RS/22012035133074 — nali nirmand pm sadak se ambaram bagari k ghar gram loharia | Approved | 94000 | 0 | 2024-09-17
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1718006079/RS/22012035133076 — nali nirmand pm sadak se sita bai k ghar ki or gram bhidava kiramk 2 | New | 0 | 0 | 2024-10-02
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718006079/WC/22012035228124 — dug out pond lohariya | Approved | 407336.76 | 0 | 2024-10-06
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718006079/WC/22012035228125 — dug out pond bhidawad | Approved | 407336.76 | 0 | 2024-11-06
BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718006079/WC/VB/YD/22012035336727 — Roof top rain wat. har. str. in gov/panchayat bldg | Approved | 29241.15 | 0 | 2026-08-15
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006080/IF/IAY/93026 — Construction of IAY House -IAY REG. NO. MP-18-006-079-002/22 | Approved | 27000 | 0 | 2015-09-16