## Work List
Exported on: 2026-10-22 11:41:06
Filters applied:
Data source: MGNREGA
District: UJJAIN
Block: All
Panchayat: GUNAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2017-2018 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Work-shed for livelihood activity of SHG / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1718006087/AV/22012034358599 — shamshan shed nirman gunawad | Closed | 0 | 0 | 2017-08-15
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006087/AV/22012034368406 — Shamshan shed nirman gunawad | Completed | 180000 | 178714.54 | 2017-08-11 | 2018-07-23
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006087/AV/22012034391311 — Aganvadi bhavan nirman krmank 02 gunavad | Ongoing | 180000 | 51564 | 2018-10-07
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1718006087/AV/22012034577773 — samudaik nadep Gunawad | Closed | 60154.51 | 0 | 2021-04-14
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006087/AV/2556 — Anganwadi/Other Rural Infrastructure,BADNAGAR | Completed | 180000 | 175173 | 2015-08-31 | 2018-07-07
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1718006087/DP/22012034536185 — nutration garden HS gunawadd | Closed | 4972.44 | 0 | 2021-08-15
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006087/DP/जेटरोपा रोपण कार्य तालाब के पास गुणा — जेटरोपा रोपण कार्य तालाब के पास गुणावद | Completed | 30400 | 35476 | 2008-07-22 | 2008-08-25
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/DW/9993654141 — SOKHATA GADDA GUNAWAD TS-60/12/06/2015/UNIT-10 | Completed | 65000 | 4770 | 2015-07-01 | 2016-08-22
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006087/IF/22012034346649 — sarwjanik parisar gunawad varkchha ropan | Completed | 335000 | 19242 | 2017-06-04 | 2020-07-02
BADNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006087/IF/22012034618648 — NANDAN FALOUDHYAN GANGABAI PATI MOTILAL JI | Closed | 142545 | 0 | 2020-11-07
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006087/IF/22012035254347 — CATTLE SHED SANGEETA BAI SANJAY NGUNAWAD | New | 0 | 0 | 2024-06-06
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006087/IF/22012035256122 — CATTEL SHED REKHA BAI KAILASH | Approved | 0 | 0 | 2024-06-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006087/IF/22012035514198 — JGSA khet talab Bharat puri goswami pita dasharat gp Gunawad | Physically Completed | 147621.16 | 99265.81 | 2025-05-16 | 2026-04-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718006087/IF/22012035516141 — Jgsa khet talaab nanda pita rooga bisalkhedi gp barnagar | Deleted | 450885.64 | 260.86 | 2025-05-16
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006087/IF/22012035611676 — EK BAGIYA MAA KE NAAM SUGNA BAI DEVISINGH GUNAWAD | Ongoing | 263510.03 | 261 | 2025-09-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006087/IF/22012035620182 — EK BAGIYA MAA KE NAAM SANGEETA BAI SANJAY GUNAWAD SHG CODE 170021098020 | Ongoing | 263510.03 | 261 | 2025-09-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006087/IF/22012035635639 — EK BAGIYA MAA KE NAAM SAYARA BAI RAMCHANDRA GUNAWAD SHG CODE 170033140951 | Approved | 263511.37 | 0 | 2025-08-15
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006087/IF/22012035648559 — PASHU SHED NIRMAAN KARY REKHA BAI KELASH GUNAWAD SHG CODE 170021354754 | New | 0 | 0 | 2025-10-02
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/9993679240 — IAY Munny Bai - BadriLal AS 1362/19/09/2015 | Completed | 14310 | 12446 | 2015-12-24 | 2017-09-26
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/9993679249 — IAY Jani Bai - Rugnath AS 1360/19/09/2015 | Completed | 14310 | 15336 | 2016-01-11 | 2018-05-25
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/9993689027 — IAY/LANKABAI-BHERULAL1361/19/09/2015 | Completed | 14310 | 12648 | 2016-01-11 | 2017-09-26
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006087/IF/9993718176 — cattle shed | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1041811 — Construction of IAY House -IAY REG. NO. MP3101744 | Completed | 15480 | 14448 | 2017-12-08 | 2018-04-10
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4329132 | Completed | 15660 | 14964 | 2018-09-26 | 2019-03-20
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4483840 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4940290 | Completed | 15660 | 15660 | 2018-07-01 | 2019-03-20
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5358195 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5378222 | Completed | 15660 | 14616 | 2018-07-01 | 2019-03-20
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1848971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5391589 | Completed | 15660 | 14616 | 2018-09-13 | 2019-03-20
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4321277 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4325427 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4472240 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4509997 | Completed | 15660 | 14616 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4510047 | Completed | 15660 | 14964 | 2018-07-01 | 2019-01-01
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5300373 | Deleted | 15660 | 0 | 2018-06-14
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5302745 | Completed | 15660 | 14616 | 2018-07-01 | 2019-03-20
BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/1849370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5338971 | Completed | 15660 | 14964 | 2018-08-03 | 2018-12-10
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/210060 — Construction of IAY House -IAY REG. NO. MP1066116 | Completed | 15030 | 14530 | 2017-02-27 | 2017-12-07
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/231878 — Construction of IAY House -IAY REG. NO. MP1341507 | Completed | 15030 | 14560 | 2017-02-03 | 2018-02-24
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4276948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587829 | Completed | 18360 | 18360 | 2022-07-28 | 2023-03-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4289371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118586982 | Completed | 18360 | 18360 | 2022-08-09 | 2023-03-05
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4289372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587094 | Completed | 18360 | 18318 | 2022-07-28 | 2023-08-23
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4291126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120987950 | Completed | 18360 | 18339 | 2022-10-17 | 2023-08-23
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4291966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118302156 | Completed | 18360 | 18360 | 2022-08-30 | 2023-08-23
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4304376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587789 | Completed | 18360 | 18360 | 2022-08-30 | 2023-03-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4700917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118570902 | Completed | 23490 | 22068 | 2024-10-29 | 2026-04-08
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/4869914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120989302 | Ongoing | 23490 | 1701 | 2025-02-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5246150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587152 | Ongoing | 23490 | 23490 | 2025-08-01
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5247108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587748 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5249198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118318491 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5260259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118570868 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5261619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638024 | Physically Completed | 23490 | 23490 | 2025-07-08 | 2026-04-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5284676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118315213 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5292292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118300526 | Completed | 23490 | 22707 | 2025-04-29 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5305206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118301000 | Completed | 23490 | 23490 | 2025-04-29 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5313730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118586952 | Ongoing | 23490 | 17748 | 2026-02-20
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5343609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587721 | Physically Completed | 23490 | 22968 | 2025-06-24 | 2026-01-09
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/541379 — Construction of IAY House -IAY REG. NO. MP3106179 | Completed | 15030 | 14388 | 2017-02-27 | 2018-04-10
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5489442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118303353 | Physically Completed | 23490 | 23490 | 2025-08-01 | 2026-01-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5489452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118528773 | Physically Completed | 23490 | 22968 | 2025-04-29 | 2026-01-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5490589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120988139 | Completed | 23490 | 23490 | 2025-04-29 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5491335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587684 | Physically Completed | 23490 | 23490 | 2025-06-24 | 2026-01-06
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5491890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118308238 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5492616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587223 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5492670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119567894 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5493147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638122 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5493148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638359 | Physically Completed | 23490 | 23490 | 2025-07-01 | 2026-03-29
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5494864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125300397 | Completed | 23490 | 23490 | 2025-06-24 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5494867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118318007 | Physically Completed | 23490 | 23490 | 2025-08-07 | 2026-01-09
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5495235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120067276 | Ongoing | 23490 | 17748 | 2026-03-13
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5624698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120988559 | Completed | 23490 | 23490 | 2025-07-01 | 2026-02-01
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5627357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118316239 | Completed | 23490 | 23490 | 2025-08-01 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5666071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118587636 | Completed | 23490 | 23490 | 2025-08-30 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5731008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120067353 | Completed | 23490 | 23490 | 2025-09-27 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5732436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638153 | Completed | 23490 | 23490 | 2025-08-30 | 2026-02-26
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5732437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638270 | Approved | 23490 | 0 | 2025-05-18
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5814390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120986811 | Approved | 23490 | 0 | 2025-08-25
BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5871763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118318166 | Ongoing | 23490 | 17748 | 2026-04-10
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/5922763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148159907 | Approved | 23490 | 0 | 2025-03-02
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/735888 — Construction of IAY House -IAY REG. NO. MP2127643 | Completed | 15030 | 14792 | 2017-05-31 | 2018-02-24
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/739738 — Construction of IAY House -IAY REG. NO. MP2223787 | Completed | 15030 | 14988 | 2017-05-31 | 2018-05-25
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/763446 — Construction of IAY House -IAY REG. NO. MP3120094 | Completed | 15030 | 14448 | 2017-05-31 | 2018-03-08
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/769644 — Construction of IAY House -IAY REG. NO. MP3417768 | Completed | 15030 | 14448 | 2017-05-31 | 2018-03-07
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006087/IF/IAY/775331 — Construction of IAY House -IAY REG. NO. MP3692468 | Completed | 15030 | 14520 | 2017-12-23 | 2018-07-21
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034185241 — cc road + nali men road se motilal(ts-849/24.11.12 | Completed | 197830 | 107036 | 2013-09-25 | 2015-03-16
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034198455 — cc+nali pp+m ghar singh se shyam(ts-231/28.12.13) | Completed | 176780 | 131692 | 2014-01-12 | 2016-07-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034202990 — cc+nali ramesh se shivnarayan(ts-230/28.12.13) | Completed | 160748 | 136720 | 2014-02-07 | 2016-07-03
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1718006087/RC/22012034209878 — u akar nali gunawad Nrega+V (ts 176/12/06/2013) | Completed | 200000 | 198557.7 | 2014-03-03 | 2014-07-08
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006087/RC/22012034211194 — khetsadak bisalkhedi (ts 417/24/01/2014) | Completed | 1387000 | 756302 | 2014-03-04 | 2017-02-23
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006087/RC/22012034219705 — Gravel sadak gunawad dotru marg(Ts 18/22/05/2014) | Completed | 1455000 | 886041.4 | 2014-05-31 | 2017-04-12
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034264297 — cc road+nali nirman pp+m main road se suganabai ke ghar ts222/5.11.15 | Deleted | 167000 | 0 | 2014-10-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034264761 — cc road+nali nirman mn+pp main road se shri ram mandir ts223/5.11.15 | Completed | 167000 | 118925.6 | 2016-04-10 | 2017-09-06
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034301861 — CC Road | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034301862 — CC Road | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034314414 — cc road +nali nirman bad se pirkash ke ghar and nirmal ke ghar se nihal ke ghar 14v+m t/s 72/28.7.16 | Completed | 194000 | 99914 | 2016-08-26 | 2017-09-06
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034323176 — CC ROAD AND NALI NIRMAN | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034327087 — cc rode+nali nirbhaysingh ke ghar se sardar-gannikha ke ghar tak | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034350056 — Fulsing ke ghar se mean road tak | Completed | 53000 | 51944 | 2017-09-26 | 2018-03-07
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034350059 — Fulsing ke ghar se mean road tak | Deleted | 0 | 0 | 2017-08-15
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034371030 — सीसी रोड + नाली | Deleted | 0 | 0 | 2018-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034375437 — cc road+nali niraman nirbhaysingh ke ghar se sardar-gannikha ke ghar tak | Completed | 63000 | 61968 | 2017-12-14 | 2019-12-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034375451 — cc road+nali nirman narayan ke ghar se kalukha ke ghar tak | Completed | 21000 | 19644 | 2018-02-02 | 2019-12-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034379652 — cc road+nali nirman girdhari ke ghar se ramesh-sukharam ke ghar tak | Completed | 28000 | 22704 | 2018-02-17 | 2019-12-02
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006087/RC/22012034381486 — sudur sampark rod gunavad se akoliya marg tak(ts371/07/06/2017) | Deleted | 2878000 | 0 | 2017-04-24
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034381661 — cc road+nali nirman mean road se husenkha ke ghar tak | Completed | 67000 | 57420 | 2018-06-07 | 2019-09-06
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034392194 — cc road nirman karya sha.school prangan ke parisar me | Completed | 34000 | 33408 | 2018-09-20 | 2019-02-01
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034396726 — cc road +nali nirman shasakiy bhavan se bharat nandu ke ghar tak | Completed | 41000 | 39672 | 2019-02-05 | 2019-12-03
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034437025 — cc road+nali | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034444164 — cc road+ nali nirman mean road se reshambai ke ghar tak | Completed | 49000 | 31668 | 2019-03-09 | 2020-07-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034463472 — cc road +nali nirman gabbu ke ghar se madan ke ghar tak | Completed | 14000 | 9588 | 2019-11-07 | 2023-08-23
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034463485 — cc road+nali nirman ramdevra se ramprasad ke ghar tak | Completed | 28000 | 27456 | 2019-12-08 | 2020-03-02
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1718006087/RC/22012034463547 — nali nirman madan choudhari ke ghar se umrav ke ghar tak | Closed | 10000 | 0 | 2018-08-15
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1718006087/RC/22012034463607 — nali nirman hirasingh ke ghar se gharsingh ke ghar tak | Closed | 9000 | 0 | 2018-08-15
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034510983 — cc road+nali nirman shriram mandir se ramprasad ke ghar ki or gram bislkhedi | Completed | 47000 | 44364 | 2019-12-27 | 2020-05-29
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034554245 — cc road+nali nirman ramprasad ke ghar se fatehpur marg tak gunavd | Completed | 53000 | 37692 | 2020-12-30 | 2023-08-23
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034560636 — cc road fatehpur marg se badrilal ke ghar gunawad | Completed | 122000 | 116042 | 2021-03-21 | 2024-07-10
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034565508 — cc road nirman Gabbu ke ghar se shreeram ke ghar gunawad | Completed | 116000 | 104802 | 2022-07-23 | 2026-02-26
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034624328 — Cc road nirmand toloram k ghar se radhesyam k ghar gunavad | Completed | 49000 | 47746 | 2023-08-04 | 2024-07-31
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034668081 — Cc road nirmand Bad s bhart lal ji jat k ghar ki or gunavd | Completed | 38000 | 34255 | 2023-10-08 | 2024-07-10
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034671863 — Cc road prahlad k ghar se suresh k ghar gunavd | Completed | 23000 | 22763 | 2024-01-24 | 2024-07-10
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034677138 — Cc road nirmand amrat jat k ghar se devra ki or gunavd | Ongoing | 18000 | 10935 | 2025-03-17
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034819142 — cc road nali nirmand sohan goad k ghar se badrilal k ghar ki or gunavd | Completed | 49000 | 43730.4 | 2024-09-03 | 2024-12-07
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034832104 — cc road nali nirmand babulal pita kana k ghar s sobharam pita dhula k ghar ki or gunavad | Physically Completed | 22000 | 19314.68 | 2025-02-09 | 2026-04-06
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/22012034832107 — cc road nali nirmand sunil pita bherulal k ghar se mahesh pita sobhoram k ghar ki or gunavad | Completed | 27000 | 25864.76 | 2025-02-07 | 2026-03-12
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/29गुणावद श — गुणावद शांतिधाम समतलिकरण सीपीटी (65/16.4.11) | Completed | 305000 | 206692.51 | 2011-06-01 | 2013-11-07
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/2गुणावद अर — गुणावद अर्थवर्क गुणावद से अत्‍याना मार्ग गुणावद | Completed | 398200 | 445961 | 2008-09-19 | 2011-02-25
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/32आंतरीक म — आंतरीक माग (G.S.B.) गीरधारी लाल से शां टांसफामर(752/10.10.2011) | Completed | 228000 | 211188 | 2011-12-23 | 2013-11-07
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/32सी सी रो — सी सी रोङ व नाली P.P+ M. ‍शीवनारायण के घर से खाल त | Completed | 187667 | 157656 | 2012-06-18 | 2015-03-16
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/35Antrik m — Antrik marg(G.S.B)Muramikaran SARDAR SINGH k Ghar RaDHESHAM ( T/S 98/ 02.06.2012) | Completed | 243000 | 161032 | 2012-11-01 | 2013-11-07
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006087/RC/35सी सी रो — सी सी रोङ एवं नाली fनमाण Gunawad Ghiradari k ghar | Completed | 158333 | 109028 | 2013-01-17 | 2015-03-16
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3 अर्थवर्क — अर्थवर्क गुणावद से गौतमपुरा भाग 1 | Completed | 477000 | 453932 | 2009-06-12 | 2010-01-12
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3 गुणावद — गुणावद अर्थवर्क गुणावद से आत्‍याना मार्ग भाग 2 | Completed | 477000 | 474864 | 2009-04-01 | 2011-02-25
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3 गुणावद अ — गुणावद अर्थवर्क मेन रोड से अकोलिया मार्ग -1 | Completed | 470000 | 611238 | 2009-05-30 | 2009-12-16
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3गुणावद अर — गुणावद अर्थवर्क गुणावद से आत्‍याना मार्ग भाग 2 | Deleted | 0 | 0 | 2009-05-07
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3गुणावद से — गुणावद से अकोलिया मार्ग भाग 2 अथर्वक | Completed | 477000 | 127129.55 | 2009-08-10 | 2011-02-25
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/3दोञु मार् — गुणावद अर्थवर्क गुणावद से दोञु मार्ग | Completed | 494000 | 348100 | 2009-10-29 | 2010-11-27
BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006087/RC/4 अर्थवर्क — अर्थवर्क गुणावद से फतेहपुर मार्ग अर्थवर्क | Completed | 494000 | 341521 | 2009-11-04 | 2012-11-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034311260 — badrilal-pira shochalay nirman | Completed | 9800 | 9504 | 2016-12-23 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034313998 — Rugnath-jawara shochalay nirman(ts387/05/12/2016) | Closed | 9800 | 0 | 2016-12-29
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314007 — Devisingh-pira shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8503 | 2016-12-31 | 2018-04-24
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314238 — sardar-hira ji shochalay nirman(ts387/5/12/2016) | Completed | 9800 | 9040 | 2017-01-10 | 2018-07-10
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314936 — akhilesh-ramesh shochalay nirman(ts387/5/12/2016) | Completed | 9800 | 9170 | 2017-01-11 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314940 — bahadursingh-anopsingh shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8836 | 2017-01-13 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314947 — gabbu-harsingh shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8335 | 2017-01-12 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314952 — .ghisibai-dayaram shochalay nirman(ts387/05/12/2016) | Closed | 9800 | 0 | 2017-01-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314966 — shakila bi-salimkha shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8168 | 2017-01-03 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034314973 — nirbhaysingh-nanuram shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8669 | 2017-01-04 | 2018-07-18
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006087/RS/22012034315131 — Nadep compost pit nirman samudayak bisalkhedi 1 (ts 295/30/11/2016) | Closed | 12200 | 0 | 2017-01-03
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006087/RS/22012034315140 — NADAP COMPOST PIT NIRMAAN SAMUDAYAK bisalkhedi 2 (TS295/30/11/2016) | Closed | 0 | 0 | 2016-10-02
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006087/RS/22012034315141 — Nadep compost pit nirman samudayak bisalkhedi 2 (TS295/30/11/2016) | Closed | 12200 | 0 | 2017-01-03
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1718006087/RS/22012034315148 — Nadep compost pit nirman samudayak baisalkhedi 3 (TS295/30/11/2016) | Closed | 12200 | 0 | 2017-01-03
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034316736 — gobibai-badda shochalay nirman(ts387/05/12/2016) | Closed | 9800 | 0 | 2017-01-10
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034316741 — jagdish nandu shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 8836 | 2017-01-11 | 2018-07-14
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034317280 — kamal-shankar shochalay nirman(ts387/05/12/2016) | Completed | 9800 | 501 | 2017-01-13 | 2018-07-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034320563 — luna-laxman shochalay nirman (ts387/05/12/2016) | Completed | 9800 | 835 | 2017-01-28 | 2018-07-11
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006087/RS/22012034320565 — omprakash-pira shochalay nirman (ts 387/05/12/2016) | Completed | 9800 | 501 | 2017-01-28 | 2018-07-11
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012034509002 — nali nirman sarsvati schoole se madrusingh ke ghar gunawad | Ongoing | 140000 | 129205 | 2021-02-26
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006087/RS/22012034636785 — swachchhta parisar sarsvati prathamik vidhyalay ke pas gunawad | Completed | 88000 | 40956 | 2022-03-14 | 2024-07-10
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012034682158 — Nali nirmand Main road se dinesh jat k ghar gunavad | Closed | 0 | 0 | 2022-10-02
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012034682159 — Nali nirmand Main road se dinesh jat k ghar gunavad | Completed | 70000 | 68993 | 2023-05-15 | 2024-07-10
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012035118853 — Nali nirmand Main road se motilal ji jat k ghar ki or gunavad | Completed | 45000 | 42911.16 | 2023-10-08 | 2025-02-05
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006087/RS/22012035121317 — samudayik swachhata parishar giram bisalkhedi | Completed | 47000 | 46674.08 | 2024-06-26 | 2024-12-04
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012035123244 — Nali nirmand Main road se moti lal ji jat k ghar ki or part -2 gunavad | Closed | 0 | 0 | 2023-10-02
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012035123245 — Nali nirmand Main road se moti lal ji jat k ghar ki or part -2 gunavad | Completed | 12000 | 10381 | 2024-03-03 | 2025-02-05
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012035128326 — nali nirmand dharmshala se fatepur marg ki or gunavd | Completed | 93000 | 92224.1 | 2024-07-16 | 2026-02-26
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006087/RS/22012035133790 — nali nirmand school pragand se gotampura road ki or gram bisalkhedi | Physically Completed | 45000 | 42715.52 | 2024-11-23 | 2026-04-06
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012034438715 — check dam | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012034444611 — check dam nala trainchig puliya k pass gram bisalkhedi ts 215/28.2.19 | Completed | 1214000 | 608420 | 2019-03-02 | 2021-03-02
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034480207 — Recharge pit hand pump (pratichhalay ) gunawad | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034480214 — Recharge pit hand pump (puliya ke pas ) gunawad | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034480216 — Recharge pit hand pump (school ke pas) gunawad | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034480219 — Recharge pit hand pump (school ke samane) bisalkhedi | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034480221 — Recharge pit hand pump (dharm shala ke pas) bisalkhedi | Closed | 10857.75 | 0 | 2019-06-22
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012034714306 — chek dam and nala trenching work near ramkundla bisalkhedi | Completed | 995813.06 | 928304 | 2021-06-05 | 2024-12-07
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034831569 — ctr recharge pit gunawad | Completed | 14467.3 | 3474 | 2021-10-05 | 2022-03-23
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034831578 — ctr recharge pit gunawad 2 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034832676 — ctr recharge pit gunawad 1 | Completed | 14467.3 | 7720 | 2021-10-05 | 2022-03-23
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034832684 — ctr recharge pit gunawad 3 | Completed | 14467.3 | 10422 | 2021-10-05 | 2022-03-23
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034832686 — ctr roof water harvesting gunawad 1 | Closed | 16878.31 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034832701 — ctr roof water harvesting gunawad 2 | Closed | 16878.31 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034841047 — ctr recharge pit gunawad 4 | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034841053 — ctr recharge pit bisalkhedi 1 | Closed | 0 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844407 — ctr recharge pit gunawad 6 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844409 — ctr recharge pit gunawad 7 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844411 — ctr recharge pit gunawad 7 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844414 — ctr recharge pit gunawad 8 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844416 — ctr recharge pit gunawad9 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844419 — ctr recharge pit gunawad 10 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844421 — ctr recharge pit gunawad 11 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844426 — ctr recharge pit gunawad12 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844432 — ctr recharge pit gunawad 13 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844437 — ctr recharge pit gunawad 14 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006087/WC/22012034844441 — ctr recharge pit gunawad 15 | Closed | 14467.3 | 0 | 2021-08-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1718006087/WC/22012034915561 — nala trenching karya puliya ke paas bisalkhedi | Closed | 0 | 0 | 2022-02-01
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006087/WC/22012034924995 — PDW तालाब जीर्णोद्धार कार्य, बिसलखेडी | Completed | 47000 | 44388 | 2022-03-15 | 2023-01-07
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1718006087/WC/22012035077930 — Sankirn pond nirman prakash pita shobharaam ke khet ke paas | Completed | 387405.53 | 330309 | 2023-07-08 | 2024-07-27
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012035087089 — Checkdam nirman karya kodiya doj par gunawad | Closed | 0 | 0 | 2023-06-19
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012035094616 — Check dam kam rapta nirmand gunavad(15 vit janpad str+mgnreg) | Completed | 199000 | 189995.15 | 2023-09-07 | 2025-06-04
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006087/WC/22012035126374 — Nala trenching mahesh vakil ke khet se ramswaroop ke khet tak | Closed | 309283.2 | 1768 | 2023-10-06
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012035180393 — check dam nirman karya kodiya doj par gunawad | Closed | 0 | 0 | 2024-02-27
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006087/WC/22012035180394 — check dam nirman karya kodiya doj par gunawad | Completed | 1079492.62 | 1058440.61 | 2024-11-26 | 2026-02-26
BADNAGAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1718006087/WC/9993668876 — Richarj pit | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006087/WH/19960788 — तालाब जीर्णोद्धार मरम्मत कार्य गुणावद(TS-53/19.5.17) | Closed | 336000 | 0 | 2017-04-14