## Work List
Exported on: 2026-09-10 02:56:06
Filters applied:
Data source: MGNREGA + VBGRAMG
District: UJJAIN
Block: All
Panchayat: PATYAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1718006104/AV/22012034567801 — शांतिधाम निर्माण कार्य ग्राम करणपुरा | Deleted | 0 | 0 | 2021-04-15
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1718006104/AV/22012034568203 — शांतिधाम निर्माण कार्य ग्राम करणपुरा तोलाराम खेत के पास | Completed | 196981.11 | 175563.92 | 2021-06-22 | 2023-09-27
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006104/AV/3629 — Aanganbadi/Other Rural Infrastructure,BADNAGAR | Completed | 195000 | 183914.8 | 2015-09-18 | 2018-07-30
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718006104/AV/3675 — Aanganbadi/Other Rural Infrastructure,PATYAKHEDI | Deleted | 0 | 0 | 2015-04-14
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006104/DP/जेट्रोफा रोपण कार्य तालाब की पाल एवं — जेट्रोफा रोपण कार्य तालाब की पाल एवं स्‍कुल ब्राउड्री करणपुरा पात्‍याखेडी | Deleted | 30280 | 7500 | 2008-10-04
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006104/DP/नंदन फलोद्यान दुलेसिह गणपत पात्‍याखे — नंदन फलोद्यान दुलेसिह गणपत पात्‍याखेडी | Deleted | 48200 | 4760 | 2008-09-19
BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006104/DP/नंदन फलोद्यान प्रहलाद हिराजी पात्‍या — नंदन फलोद्यान प्रहलाद हिराजी पात्‍याखेडी | Deleted | 48200 | 25055 | 2008-08-20
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/DW/9993654023 — Sokta gaddha patyakhedi TS45/12/06/15/ 01 | Completed | 6500 | 6086 | 2015-06-26 | 2016-06-05
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/DW/9993654031 — sokhata gadda patyakhedi TS/45/12/06/2015/N0.02 | Completed | 6500 | 6084 | 2015-06-26 | 2016-06-05
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/DW/9993654032 — SOKHATA GADDA PATYAKHEDI TS/45/12/06/2015/03 | Completed | 6500 | 6078 | 2015-06-26 | 2016-06-05
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/DW/9993654036 — SOKHATAGADDA PATYAKHEDI TS/45/12/06/2015 | Completed | 6500 | 6086 | 2015-06-26 | 2016-06-05
BADNAGAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/DW/9993654039 — SOKHATA GADDA PATYAKHEDI TS 45/12/06/2015/05 | Completed | 6500 | 6077.44 | 2015-06-26 | 2016-06-05
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006104/IF/22012034306951 — मुख्यमंत्री अन्त्योदय इंद्रा आवास | Completed | 15030 | 15377 | 2016-12-17 | 2017-09-08
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006104/IF/22012034314281 — प्रधानमंत्री आवास बालुनाथ पिता भेरानाथ ग्राम PATIYAKHEDI | Deleted | 18000 | 0 | 2017-02-27
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1718006104/IF/22012034314286 — प्रधानमंत्रीआवास भारत शंकरलाल ग्राम PATYAKHEDI | Deleted | 0 | 0 | 2017-11-08
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006104/IF/22012034343133 — PODHA ROPAN PRATHMIK SHALA MEDAN KARANPURA | Completed | 335000 | 33104 | 2017-06-02 | 2023-04-26
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006104/IF/22012034358451 — पोधा रोपण कार्य patiyakhediप्राथमिकस्कूल म स स्कूल शांतिधाम | Suspended | 335000 | 0 | 2017-10-27
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006104/IF/22012035252207 — नंदन फलोउद्यान (नीबू) बद्रीलाल अमरा जी ग्राम patykhedi | Deleted | 0 | 0 | 2024-06-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718006104/IF/22012035252212 — नंदन फलोउद्यान (नीबू) बद्रीलाल अमरा जी ग्राम patykhedi | Ongoing | 173308.58 | 2187 | 2024-08-08
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/9993682105 — sajjan bai W/O KALU JI/ iay | Completed | 14310 | 12976 | 2015-10-28 | 2016-09-23
BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/9993704599 — iay sorambai wo hariram 05karanpura | Completed | 14310 | 13836 | 2016-02-16 | 2016-09-23
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/204994 — Construction of IAY House -IAY REG. NO. MP-18-006-104-001/104 | Deleted | 15030 | 0 | 2017-10-27
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/262208 — Construction of IAY House -IAY REG. NO. MP1710630 | Completed | 15030 | 15210 | 2017-01-30 | 2017-12-12
BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/262313 — Construction of IAY House -IAY REG. NO. MP2423862 | Completed | 15030 | 16389.9 | 2017-01-28 | 2017-12-12
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3919887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106184353 | Completed | 18360 | 18241 | 2022-06-10 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191552 | Completed | 18360 | 17136 | 2022-06-10 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106239098 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106987880 | Completed | 18360 | 17136 | 2022-07-25 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106988450 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106988921 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989672 | Completed | 18360 | 17136 | 2022-08-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3922949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989968 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3923122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113870037 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3924781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106295924 | Completed | 18360 | 17136 | 2022-08-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3925485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106990013 | Completed | 18360 | 2448 | 2022-07-25 | 2025-02-14
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3925672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107067397 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3925673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107067834 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3927068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114964727 | Completed | 18360 | 18226 | 2022-08-22 | 2024-10-30
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3928379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106412115 | Completed | 18360 | 17136 | 2022-06-10 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3928475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106444572 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106024302 | Completed | 18360 | 17136 | 2022-08-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106045016 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106050232 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106058374 | Completed | 18360 | 17136 | 2022-06-10 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106065967 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106661744 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3933834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106665662 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3934858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106672996 | Completed | 18360 | 17136 | 2022-06-12 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3935061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106774048 | Completed | 18360 | 17136 | 2022-08-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3935062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106774327 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3962760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106656473 | Completed | 18360 | 16056 | 2022-10-29 | 2025-02-14
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/3966274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106208196 | Completed | 18360 | 2448 | 2022-09-13 | 2025-02-14
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4175936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106208276 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4177059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107067722 | Completed | 18360 | 17136 | 2022-06-22 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4289448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106314968 | Completed | 18360 | 17136 | 2022-07-25 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4289749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113846039 | Completed | 18360 | 17136 | 2022-07-25 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4290266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989064 | Completed | 18360 | 17136 | 2022-07-25 | 2023-07-27
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4326427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106307028 | Closed | 18360 | 0 | 2022-08-19
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4326545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113578413 | Closed | 18360 | 0 | 2022-08-19
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4326573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113651303 | Approved | 27000 | 0 | 2022-07-24
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4327004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106655191 | Closed | 18360 | 0 | 2022-08-19
BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4328193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106056497 | Closed | 18360 | 0 | 2022-08-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4370304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113653230 | Completed | 23490 | 23490 | 2025-05-17 | 2026-02-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4540397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106040429 | Completed | 21870 | 21141 | 2024-09-28 | 2025-02-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4547186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106185925 | Completed | 21870 | 21627 | 2024-09-28 | 2025-02-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4547392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106664301 | Completed | 21870 | 20169 | 2024-09-28 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4687656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106311280 | Completed | 21870 | 21139.04 | 2024-10-04 | 2025-02-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4690848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113792879 | Completed | 23490 | 21627 | 2024-10-05 | 2025-12-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4737159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106100297 | Completed | 21870 | 21141 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4737190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106110254 | Completed | 21870 | 20655 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4737786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106208058 | Completed | 21870 | 21870 | 2024-11-08 | 2025-02-07
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4739410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106499388 | Completed | 21870 | 21627 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4741478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989609 | Completed | 23490 | 22725 | 2024-11-08 | 2025-12-05
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4741481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106990930 | Completed | 21870 | 21384 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4742048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107067899 | Completed | 21870 | 21141 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4742564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483733 | Completed | 21870 | 21627 | 2024-11-08 | 2025-02-09
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4746045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113771542 | Completed | 21870 | 21141 | 2024-11-08 | 2025-03-12
BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4746387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114971992 | Completed | 21870 | 21627 | 2024-11-08 | 2025-03-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/4990327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106990490 | Ongoing | 27000 | 7188 | 2025-09-14
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5245788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106990203 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5248507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106037211 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5254302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906144 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5260768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113579411 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5268994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113578177 | Completed | 23490 | 23490 | 2025-04-08 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5287645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989258 | Completed | 23490 | 23490 | 2025-04-08 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5290576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106988027 | Completed | 23490 | 23229 | 2025-04-08 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5312692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113773638 | Completed | 23490 | 23490 | 2025-04-08 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5313525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106667720 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5316918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106053778 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5317557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106774488 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5319417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113578497 | Ongoing | 27000 | 23490 | 2025-04-08
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5320853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106773654 | Completed | 23490 | 23490 | 2025-04-08 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5389517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989502 | Completed | 23490 | 23490 | 2025-04-18 | 2026-03-30
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5434425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113651535 | Completed | 23490 | 23490 | 2025-04-18 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5435733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106773798 | Completed | 23490 | 23229 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5435869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113772142 | Completed | 23490 | 23229 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5435978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106190522 | Completed | 23490 | 23229 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5436561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113905985 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5436562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906069 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5436819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106840807 | Completed | 23490 | 23490 | 2025-04-18 | 2026-02-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5437150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114972199 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5437273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106989122 | Completed | 23490 | 23229 | 2025-04-18 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5437284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113838041 | Completed | 23490 | 23229 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5437606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106046899 | Completed | 23490 | 23490 | 2025-04-18 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5438093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106990063 | Physically Completed | 23490 | 18270 | 2025-04-18 | 2026-08-02
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5438232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106987995 | Completed | 23490 | 23490 | 2025-04-18 | 2026-02-24
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5438580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106774199 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5438581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106774245 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-05
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5439222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113869490 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5439295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106188399 | Completed | 23490 | 23490 | 2025-04-18 | 2025-12-19
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5492549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106657617 | Completed | 23490 | 23490 | 2025-05-01 | 2026-02-12
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5512418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106097221 | Completed | 23490 | 23490 | 2025-05-01 | 2026-02-03
BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/5814474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106429409 | Completed | 23490 | 23490 | 2025-09-25 | 2026-02-03
BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006104/IF/IAY/93041 — Construction of IAY House -IAY REG. NO. MP-18-006-104-002/011 | Deleted | 14310 | 0 | 2017-10-27
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006104/LD/22012034298629 — शांतिधाम शेडनिर्माण ग्राम patiyakhedi | Completed | 180000 | 177118.54 | 2017-01-23 | 2018-07-18
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006104/LD/22012034314428 — शांतिधाम निर्माण कार्य ग्राम करणपुरा बापूसिंह के खेत के पास TS 09/12/2016 AS.06/ 17/05/2017 | Completed | 180000 | 516 | 2017-06-01 | 2018-07-18
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718006104/LD/9926704091 — khel medan karanpura(ts-871/3.3.14) | Completed | 488200 | 395781.62 | 2014-05-22 | 2017-11-12
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034181289 — cc road+nali nirman maherban anopsingh | Completed | 200000 | 190561 | 2013-09-08 | 2014-10-05
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034196218 — CC ROAD+NALI V+M GRAM ABADI(TS-473/2.8.13) | Completed | 66750 | 65144 | 2013-12-28 | 2015-03-31
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006104/RC/22012034217331 — खेतसड़क तलाब से भगवान क़े खेत(TA-872/3.3.14) | Completed | 1391400 | 394139.2 | 2014-05-22 | 2016-11-27
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034264319 — cc road+nali nirman pp+m gram patyakhedi | Deleted | 0 | 0 | 2014-10-02
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034264773 — cc+nali nirman mn+pp2 gram abadi patyakhedi | Deleted | 0 | 0 | 2014-10-02
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034291550 — CC ROAD NALI NIRMAN | Deleted | 0 | 0 | 2015-10-02
BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034291555 — CC ROAD NALI NIRMAN RAGHUPAL SINGH KE GHAR SE MOKAM SINGH GHAR PP+M T/S 281/26.11.15 | Completed | 145000 | 147889.2 | 2015-12-25 | 2016-11-25
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034294041 — NALI NIRMAN PATYAKHEDI MANHOR SE PMGSY TAK t/s 328/30.11.15 14v+m | Completed | 99333 | 72935.05 | 2016-12-23 | 2018-07-07
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034301970 — cc road+nali | Deleted | 0 | 0 | 2016-04-01
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034323159 — cc+nali nirman | Deleted | 0 | 0 | 2017-01-26
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034329340 — CC ROAD + NALI NIRMAN 14 va Kamal singh ke ghar se Ramlal ke ghar tak | Completed | 29000 | 23705.88 | 2017-03-18 | 2018-04-24
BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034329343 — CC ROAD + NALI NIRMAN (V+MGNREGS) Lakhan singh ke ghar se Gattulal ke ghar tak t/s 290/30.11.16 | Completed | 134000 | 130597 | 2017-03-04 | 2018-02-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034336999 — CC Road + Nali Nirman Jagdish ke ghar se Ganpat singh ke ghar tak | Completed | 33000 | 18576 | 2017-05-05 | 2017-07-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034342258 — सी.सी. रोड+नालीनिर्माण ग्राम करणपुरा रामसिंह केघर से शंकरगब्बा के घर तक | Completed | 104000 | 14448 | 2017-07-05 | 2018-02-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034342662 — सी.सी.रोड नालीनिर्माण ग्राम patiyakhedi जीतेन्द्रसिंह के घर से रविपाल के घर तक | Completed | 158000 | 22704 | 2017-08-01 | 2018-02-24
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1718006104/RC/22012034371123 — सीसी रोड +नाली | Deleted | 0 | 0 | 2018-04-01
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034378541 — सी.सी.रोडनालीनिर्माण ग्राम पात्याखेडी हेडपंप सेगंगामाता मंदिर तक TS/7418/24/12/2016 | Completed | 28000 | 27864 | 2018-01-01 | 2018-04-24
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034378563 — सी.सी.रोडनालीनिर्माण ग्राम पात्याखेडी प्रधानमंत्री रोड से रमेश कालूजी के घर तक TS/7418/24/12/2016 | Completed | 24000 | 23736 | 2018-01-05 | 2018-07-09
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034383759 — सी.सी.रोडनालीनिर्माण ग्राम करणपुरा मुख्यमंत्री रोड से हनुमान मंदिर तक TS/7418/24/12/2016 | Completed | 49000 | 49536 | 2018-02-16 | 2018-06-16
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034383764 — सी.सी.रोडनालीनिर्माण ग्राम करणपुरा मेहरबानसिंह के घर से बापूसिंह के घर तक TS/7418/24/12/2016 | Completed | 20000 | 8256 | 2018-02-23 | 2018-06-28
BADNAGAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034383765 — सी.सी.रोडनालीनिर्माण ग्राम करणपुरा भारतसिंह के घर से हेडपंप तक TS/7418/24/12/2016 | Completed | 15000 | 7224 | 2018-02-16 | 2018-06-28
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034386959 — सी.सी.रोडनालीनिर्माण ग्राम पात्याखेडी रणजीत के घर से ईश्वरलाल व बिजली डीपी त TS/7418/24/12/2016 | Completed | 47000 | 45936 | 2018-04-04 | 2018-06-28
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034390812 — सी.सी.रोडनालीनिर्माण ग्राम पात्याखेडी मोहन के घर से प्रधानमंत्री रोड तक TS/7418/18/04/2018 | Completed | 13000 | 13224 | 2018-10-13 | 2021-08-10
BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034390815 — सी.सी.रोडनालीनिर्माणग्राम करणपुरा बनेसिंह के घर से नारायण सिंह के घर तक तक TS/7418/19/04/2018 | Completed | 27000 | 27144 | 2018-09-14 | 2021-08-10
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034440226 — CC ROAD+NALI | Deleted | 0 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034449334 — सीसी रोड निर्माण शासकीय प्राथमिक स्कूल केसामने ग्राम पात्याखेडी | Completed | 57000 | 57024 | 2019-05-24 | 2021-08-10
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034468446 — सी.सी रोड नालीनिर्माण कार्य रिपरिंग कार्य ग्राम करणपुरा रामलखनदास के घर से हेडपंप तक | Completed | 27000 | 27456 | 2019-12-11 | 2020-06-02
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034470807 — सी.सी.रोडनालीनिर्माण ग्रामपत्याखेडी सोहनलाल के घर से सरदारसिंह के घर तक( रिपेरिंग कार्य) | Completed | 36000 | 29598 | 2019-11-19 | 2024-07-17
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034506352 — प्रधानमंत्री रोड से शांतीधाम तक (ग्राम पात्याखेडी cc rod nirman | Completed | 29000 | 27456 | 2020-01-09 | 2020-06-02
BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034506357 — CC ROD ग्राम पात्याखेडी पंचायत भवन के सामने चौक निर्माण | Completed | 51000 | 49632 | 2019-11-20 | 2020-06-02
BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034551999 — सी सी रोड निर्माण praathmik school के सामने करण पुरा | Completed | 66000 | 64980 | 2020-12-08 | 2021-09-21
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034569459 — आरसीसी नाला निर्माण जगदीश के घर से उन्हेल रोड तक | Completed | 88000 | 85692 | 2021-06-23 | 2021-09-21
BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034590311 — सी सी रोड निर्माण कार्य शांति धाम चौक ग्राम करणपुरा | Closed | 102867 | 0 | 2021-10-03
BADNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034625634 — नाली निर्माण नर्मदाबाई के घर से मेहरबानसिंह के घर तक ग्राम करनपुरा | Completed | 41000 | 40392 | 2023-01-12 | 2024-07-03
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034630132 — आर आर सी सी नाली निर्माण कार्य जगदीश नागुजी के घर से गुड्डुनाथ के घर तक पात्यखेड़ी | Completed | 124000 | 122655 | 2023-05-04 | 2024-04-30
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034630136 — आरसीसी नाली निर्माण गुड्डू नाथ के घर से नाथ नाथ के घर तक पात्यखेड़ी | Completed | 113000 | 112268 | 2023-08-16 | 2024-04-30
BADNAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034672083 — सी सी रोड + नाली निर्माण कार्य लाखनसिंह के घर से सोदानसिंह के घर तक ग्राम पात्याखेड़ी | Completed | 55000 | 53791 | 2024-01-17 | 2024-07-03
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034831265 — Nali nirman aja basti karanpura | Completed | 75000 | 74601 | 2024-12-16 | 2025-02-09
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/22012034837157 — c c road nali nirman dilipsingh ke ghar se jivansingh ke ghar tak patyakhedi | Completed | 103000 | 102789 | 2025-03-11 | 2025-07-16
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/33सी सी रो — सी सी रोङ व नाली P.P+ M.रोशन से राम पात्‍याखेङी (5 | Completed | 284000 | 59790 | 2012-06-01 | 2017-01-29
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006104/RC/34सी सी रो — सी सी रोङ नाली स‍हीत आ जा+मनरेगा अजा बस्‍ती गाम कर | Completed | 300000 | 109618 | 2012-04-30 | 2015-03-31
BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006104/RC/35अर्थ वर् — अर्थ वर्क रोड Patyakhedi से Ingoriya रोड(451/21/02 | Completed | 497000 | 324650 | 2011-04-09 | 2014-10-05
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006104/RC/अर्थवर्क पात्‍याखेडी से जहॉगीरपुर का — अर्थवर्क पात्‍याखेडी से जहॉगीरपुर कांकड पात्‍याखेडी | Completed | 710000 | 505820.02 | 2008-09-14 | 2011-02-17
BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006104/RC/पात्याखेडी मार्ग निमार्ण — अर्थवर्क पात्‍याखेडी से करणपुरा काकड तक पात्‍याखेडी | Completed | 196800 | 358686.25 | 2008-04-04 | 2011-02-17
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254215 — Nirmal bharat Fulbai rugnath(01/30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254224 — Nirmal bharat Ful bai Mangusingh(as 02/30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254228 — Nirmal bharat Kailash Jugharsingh(as 03/30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254232 — Nirmal bharat BAHURNATH bheranath(as 05 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254234 — Nirmal bharat Ramsingh bapuji(as 06 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-31 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254238 — Nirmal bharat Mangu Amaraji (as 07 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254242 — Nirmal bharat Nathunath Naganath(as 08 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254243 — Nirmal bharat Gattulal Ganpat(as 09 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-23
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034254246 — Nirmal bharat Sajjansingh Parvatsingh(as 10 /30/06/2014) | Completed | 5111 | 4237 | 2014-07-30 | 2016-06-26
BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/22012034256009 — NBA shankerlal nandaji(A/s 04/30/06/2014) | Completed | 5111 | 4237 | 2014-08-02 | 2016-06-26
BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718006104/RS/22012035134287 — Nali nirman aja basti karanpura | Deleted | 75000 | 0 | 2024-08-17
BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006104/RS/31987 — NIRMAL BHARAT ISHWARDAS GOPALDAS PATYAKHEDI(AS-100 | Deleted | 4312 | 0 | 2013-06-12
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012034448430 — check dam nirmand nala trainchingtalabk pass west me gram karanpura t/s 200/23.2.19 | Closed | 1118000 | 0 | 2018-10-02
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034479925 — RICHARGE PITT PATYAKHEDI E.G.S SCHOOL KESAMNE | Completed | 10857.75 | 176 | 2019-08-19 | 2021-12-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034479928 — RICHARGE PITT PATYAKHEDI KAMAL RAMSINGH KE GHAR KE SAMNE | Deleted | 0 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034479929 — RICHARGE PITT PATYAKHEDI GAJENDRA SINGH KEGHAR KE SAMNE SAMNE | Closed | 0 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034479930 — RICHARGE PITT KARANPURA PS SCHOOL KE SAMNE | Deleted | 0 | 0 | 2019-04-14
BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034479931 — RICHARGE PITT KARANPURA HANUMAAN MANDIR KE PASS | Closed | 10857.75 | 0 | 2019-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1718006104/WC/22012034543851 — नाला ट्रेचिंग ग्राम पत्याखेडी शांतिधाम के पास | Completed | 294598.26 | 227000 | 2020-04-29 | 2021-09-21
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012034564785 — नाला टैचिग करणपुरा तालाब के पास पूर्व मै | Deleted | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012034564788 — Naala trechingh kranpura taalab ke pass purv me | Completed | 500371.06 | 270232 | 2020-07-10 | 2021-12-31
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012034579843 — Naala treching karanpura तालाब के पास पूर्व की ओर | Deleted | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012034594603 — नाला trechingh patyakhedi aanganwadi से Talab ke रास्ते तक | Deleted | 0 | 0 | 2020-04-14
BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006104/WC/22012034609197 — नाला ट्रेचिंग ग्राम करणपुरा खेल मेदान के पास | Completed | 512975.4 | 360390 | 2021-01-11 | 2021-12-31
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012034669434 — चेक डेम एवं नाला ट्रेचिंग कार्य गंगाराम के खेत के पास ग्राम करणपुरा | Deleted | 0 | 0 | 2021-04-15
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012034669437 — चेक डेम एवं नाला ट्रेचिंग कार्य गंगाराम के खेत के पास ग्राम करणपुरा | Completed | 996132.77 | 968569.98 | 2021-04-25 | 2021-09-22
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012034734286 — चेक डेम + नाला ट्रेचिंग शांति धाम के पास करणपुरा | Completed | 1400929.63 | 1039984.97 | 2021-06-05 | 2022-11-04
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1718006104/WC/22012034744556 — CTR ROOF HARVESTING ANGANWADI BHAWAN PATYAKHEDI | Completed | 13325.25 | 3281 | 2021-09-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034744559 — CTR SOKHTA GADDHA HENDPUMP KE PAAS PATYAKHEDI | Completed | 5272.82 | 2123 | 2021-09-16 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034777475 — CTR SHOKTA GADDA hedpum ke paass samsan | Completed | 14467.3 | 10422 | 2021-09-02 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1718006104/WC/22012034777480 — CTR SHOKTA GADDA FIRST samaan ghaat Mai | Completed | 14467.3 | 10422 | 2021-09-02 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718006104/WC/22012034777486 — CTR SHOKTA GADDA SECOND samaan ghaat Mai | Completed | 14467.3 | 10422 | 2021-09-16 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718006104/WC/22012034777491 — CTR SHOKTA GADDA THIRD samaan ghaat Mai | Completed | 14467.3 | 10422 | 2021-10-09 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718006104/WC/22012034777494 — CTR SHOKTA GADDA FOURTH samaan ghaat Mai | Completed | 14467.3 | 10422 | 2021-10-09 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034832665 — ctr roof harvesting | Completed | 12005.33 | 1544 | 2021-09-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034844694 — CTR SOKTA GADDA hedpump ke पास ps स्कूल karanpura | Completed | 14467.3 | 193 | 2021-10-17 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1718006104/WC/22012034844702 — CTR SOKTA GADDA hedpump ke hakam singh ke ghar के samnekaranpura | Completed | 14467.3 | 193 | 2021-10-17 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1718006104/WC/22012034850476 — CTR रिचार्ज पीट पानी की टंकी के पास। Karanpura 1 | Completed | 14467.3 | 193 | 2021-10-23 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718006104/WC/22012034850488 — CTR रिचार्ज पीट पानी की टंकी के पास। Karanpura 2 | Completed | 14467.3 | 193 | 2021-10-23 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851710 — CTR SOKTA gadda hedpump कमल ghar क़े सामने | Completed | 14467.3 | 193 | 2021-10-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851711 — CTR sokta gadda hedpump मिडिल स्कूल patyakhedi | Completed | 14467.3 | 193 | 2021-10-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851713 — CTR sokta gadda सामुदायिक शौचालय के पास। Patykhedi | Completed | 14467.3 | 193 | 2021-10-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851718 — CTR sokta gadda पानी की टंकी। के पास। Patykhedi | Completed | 14467.3 | 193 | 2021-10-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851722 — CTR sokta gadda बन्नालाल के घर। के सामने patyakhedi | Completed | 14467.3 | 193 | 2021-10-23 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851728 — CTR sokta gadda गोकुल के घर। के सामने patyakhedi | Completed | 14467.3 | 193 | 2021-10-23 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851729 — CTR sokta gadda किचन शेड के पीछे patyakhedi | Completed | 14467.3 | 193 | 2021-10-30 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034851730 — CTR sokta gadda प्राथमिक स्कूल करनपुरा हेंडवाश के पास | Completed | 14467.3 | 193 | 2021-10-23 | 2022-02-06
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859203 — CTR sokta gadda आंगनवाड़ी के पीछे एक नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859206 — CTR sokta gadda आंगनवाड़ी के पीछे दो नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859210 — CTR sokta gadda आंगनवाड़ी के पीछे तीन नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859234 — CTR sokta gadda आंगनवाड़ी के पीछे चार नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859237 — CTR sokta gadda आंगनवाड़ी के पीछे पांच नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859246 — CTR sokta gadda आंगनवाड़ी के पीछे छः नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859248 — CTR sokta gadda आंगनवाड़ी के पीछे सात नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/22012034859252 — CTR sokta gadda आंगनवाड़ी के पीछे आठ नम्बर | Closed | 14467.3 | 0 | 2021-10-02
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012034932012 — चेक डेम + नाला ट्रेचिंग कार्य रतनलाल के खेत के पास ग्राम करणपूरा | Deleted | 0 | 0 | 2022-01-27
BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012034948686 — नाला ट्रेचिंग कार्य मेहरबान के खेत के पास करनपुरा | Deleted | 0 | 0 | 2022-01-27
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006104/WC/22012034950268 — nala trenching meharban ke khet ke pass karanpura | Completed | 139451.7 | 115260 | 2022-04-19 | 2022-11-30
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006104/WC/22012034973441 — नाला ट्रेचिंग कार्य जगदीदास के खेत के पास ग्राम करणपूरा | Completed | 305392.44 | 117504 | 2022-05-25 | 2022-11-30
BADNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006104/WC/22012035045638 — संकीर्ण पोंड निर्माण इन्दर के खेत के पास ग्राम करनपुरा | Deleted | 0 | 0 | 2023-01-27
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718006104/WC/22012035047717 — संकीर्ण पोंड निर्माण इन्दर के खेत के पास करनपुरा | Completed | 474644.25 | 468752.8 | 2023-07-02 | 2024-03-11
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006104/WC/22012035123198 — संकीर्ण पोंड निर्माण अशोक के खेत के पास करनपुरा | Completed | 536729.25 | 469724 | 2023-10-06 | 2024-08-03
BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006104/WC/22012035129364 — Recharge trench at shiv mandir ke piche karanpura | Completed | 295387.01 | 144270 | 2023-10-06 | 2025-02-09
BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006104/WC/22012035209678 — Naala trechingh नई आबादी करनपुरा | Approved | 233704.65 | 0 | 2024-06-12
BADNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006104/WC/22012035313671 — Sankirn pond nirman Karanpura | Completed | 294907.64 | 216108 | 2025-06-24 | 2026-02-01
BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/VB/22012035332933 — handpump recharge pit ps school karanpura | Ongoing | 25164.85 | 3600 | 2026-08-20
BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006104/WC/VB/22012035332934 — handpump recharge pit ms school patyakhedi | Approved | 25164.85 | 0 | 2026-04-14
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006104/WH/19960772 — तालाब जीर्णोद्धार मरम्मत कार्य पात्याखेडी(TS-47/19.5.17) | Deleted | 331000 | 0 | 2017-05-24
BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006104/WH/19963731 — TALAB JIRNODHAR MARAMMAT KARYA PATYAKHEDI(TS-275/25.05.17) | Suspended | 0 | 0 | 2017-11-28
BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006104/WH/22012034333597 — MWC TALAB JIRNODDHAR KARANPURA | Completed | 331000 | 153207 | 2018-06-16 | 2019-05-20
BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/22012034159003 — Aproch Road (Puliya Per Slabe Nirman) Karanpura | Completed | 308000 | 166832.12 | 2012-10-18 | 2013-01-13