## Work List
Exported on: 2026-09-10 10:45:39
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: RAMPURAGUJAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719005008/AV/22012034665755 — ShantiDham Nirman Mhu Gp Rampura Gurjar | New | 0 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719005008/AV/22012034665756 — ShantiDham Nirman Mhu Gp Rampura Gurjar | New | 0 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of building material for Community | Construction of Other Community Building/Assets | 1719005008/AV/22012034665758 — ShantiDham Nirman Mhu Gp Rampura Gurjar | New | 0 | 0 | 2025-04-14
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719005008/DP/22012034588918 — Vasudha Vandan- Amrit Vatika (75) Gram Panchayat Rampuragurjar | Ongoing | 55847.4 | 0 | 2023-11-22
SHAJAPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005008/IF/22012034891054 — KHET TALAB NIRMAN-SODAN SINGH-HOKAM SINGH-GRAM RAMPURA GURJAR | Ongoing | 338902.57 | 0 | 2021-12-04
SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005008/IF/22012035082777 — Kapil dhara kup Niarman Sanjay Devisingh GP Rampuragurjar | Ongoing | 274429.96 | 0 | 2024-02-08
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035269999 — Niji Khet Nandan Falodhan Sitaram S/O Sankarlal Gurjar | Approved | 0 | 0 | 2024-08-15
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035279480 — Khet talab Nirman Chandar Singh s/o Ghisha ji Rampura gurjar | Ongoing | 363692.29 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035279483 — Khet Talab Nirman Babu lal s/o Shivlal Rampura gurjar | Ongoing | 363692.29 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035279486 — Khet talab Nirman Chandr Singh s/o Shivlal Rampura gurjar | Ongoing | 363692.29 | 0 | 2025-05-02
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005008/IF/22012035287955 — kapil dhara kup nirman Mansingh s/o Bhagirath Rampura gurajr | Approved | 322434.5 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035296839 — NIJI KHET TALAB NIRMAN RAHUL S/O ISHWAR SINGH RAMPURA GURJAR | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035296841 — NIJI KHET TALB NIRMAN SHIVLAL S/O UMRAV SINGH RAMPURA GURJAR | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035305176 — Niji Khet Talab Nirman perlad singh s/o Ram singh rampura gurjar dekdi | Approved | 0 | 0 | 2025-01-26
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035454979 — niji khet talab nirman rahul s/o ishwar singh rampura gurjar | Ongoing | 363692.29 | 0 | 2025-05-06
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005008/IF/22012035455019 — niji khet talab nirman shiv lal s/o umrav rampura gurjar | Ongoing | 363692.29 | 0 | 2025-05-06
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035632867 — EK BAGIYA MA KE NAAM Ramprasad Bai | Ongoing | 264661.6 | 0 | 2026-01-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035632874 — EK BAGIYA MA KE NAAM MAYA | Ongoing | 264661.6 | 0 | 2026-01-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035632878 — EK BAGIYA MA KE NAAM Vaishnavi Bai | Ongoing | 257158.61 | 0 | 2026-01-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035632882 — EK BAGIYA MA KE NAAM Mewa Bai | Ongoing | 257158.61 | 0 | 2026-01-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005008/IF/22012035632886 — EK BAGIYA MA KE NAAM Razkunwar Bai | Ongoing | 264661.6 | 0 | 2026-01-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5662270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148521321 | Physically Completed | 23490 | 0 | 2025-11-16 | 2026-07-29
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5692643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151387679 | Completed | 23490 | 0 | 2025-09-22 | 2026-08-05
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149607502 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149607859 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149608422 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150315352 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148521742 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148522202 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148522363 | Ongoing | 27000 | 7800 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151396115 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150316170 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150317914 | Ongoing | 27000 | 4200 | 2026-07-24
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148156532 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148522120 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148521537 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5972996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151369522 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151403796 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151365992 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151368785 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151403562 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146399080 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145505131 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145505407 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148155698 | Physically Completed | 23490 | 300 | 2026-05-02 | 2026-08-25
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151384808 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151358681 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149607949 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149608202 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149608254 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149608366 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149607268 | Ongoing | 27000 | 4200 | 2026-08-05
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148155780 | Ongoing | 27000 | 0 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148155946 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148155967 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/5973909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148155996 | Ongoing | 27000 | 4200 | 2026-06-07
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6097171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145504963 | Ongoing | 27000 | 4200 | 2026-07-24
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6097172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145505171 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6100040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149607697 | Ongoing | 27000 | 0 | 2026-09-06
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6100041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149608327 | Ongoing | 27000 | 4200 | 2026-08-23
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6100513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150315529 | Ongoing | 27000 | 8400 | 2026-08-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6100514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150316362 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6100515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150318552 | Ongoing | 27000 | 0 | 2026-08-23
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6101041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151369786 | Ongoing | 27000 | 8400 | 2026-08-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6101049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151383045 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6101055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151388862 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6101056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151389856 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6101057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151391694 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6107603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150315679 | Ongoing | 27000 | 8400 | 2026-08-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/6107604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150318714 | Approved | 27000 | 0 | 2026-02-28
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005008/IF/IAY/70514 — Construction of IAY House -IAY REG. NO. MP-19-005-008-003/8 | Ongoing | 27000 | 0 | 2018-08-25
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005008/WC/22012035172245 — Chek Dem Nirman Sanjay Ke Khet Ke Pass Mota Chapara | New | 0 | 0 | 2024-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005008/WC/22012035172248 — Chek Dem Nirman Suresh Ke Khet Ke Pass gadiyal Ka Chapraa | New | 0 | 0 | 2023-04-14
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005008/WC/22012035172938 — Chek Dem Nirman Sanjay Ke Khet Ke Pass Mota Chapara | New | 0 | 0 | 2023-01-26
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005008/WC/22012035236283 — Boldar chek dem Kundaliya ka chapra Rampura gurjar | Approved | 0 | 0 | 2024-04-14
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005008/WC/22012035237263 — Gebiyan Part 05 kundal ka chapra rampura gurjar | Approved | 0 | 0 | 2024-04-14
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005008/WC/22012035237265 — Gebiyan Part 06 mota chapra rampura gurjar | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005008/WC/22012035237266 — Gebiyan Part 07 nana chapra rampura gurjar | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005008/WC/22012035237273 — Gebiyan Part 08 sitaram ke khet ke pass rampura gurjar | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005008/WC/22012035237277 — gebiyan Part 08 chandr singh ke khet ke pass rampura | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005008/WC/22012035272600 — JGSA 2025 Dagvel Richargpit samudayik kup ke pas Rampura gurjar | Approved | 24099.46 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005008/WC/22012035272628 — JGSA 2025 Dagvel Richargpit samudayik kup ke pas devmandir parisar mau gp rampura gurjar | Approved | 24099.46 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005008/WC/22012035272650 — JGSA 2025 Dagvel Richargpit samudayik kup ke pas Dhakda gp ramuragurjar | Approved | 24099.46 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005008/WC/22012035272688 — JGSA 2025 Dagvel Richargpit samudayik kup ke pas Lalakhedi GP Rampura gurjar | Approved | 24099.46 | 0 | 2025-04-14
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1719005/WC/22012035169595 — Construction of Gully plug gram Rampura gurjar | New | 0 | 0 | 2024-01-26