## Work List
Exported on: 2026-09-06 04:54:11
Filters applied:
Data source: MGNREGA + VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: TUKARANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1719005013/AV/22012034392362 — PANCHAYAT BHAVAN NIRMAN | Deleted | 0 | 0 | 2018-08-15
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719005013/AV/22012034392383 — panchayat bhawan nirman gram tukrana | Completed | 579200 | 556771 | 2019-03-05 | 2024-10-23
SHAJAPUR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1719005013/AV/22012034572963 — segrigation shed shantidham ke pas tukrana | Closed | 0 | 0 | 2021-04-14
SHAJAPUR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1719005013/AV/22012034572968 — segrigation shed shantidham ke pas tukrana | Closed | 0 | 0 | 2021-04-14
SHAJAPUR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1719005013/AV/22012034576679 — Construction of workshed for livelihood activity for groups (Segrigation shed) GP Tukrana | Ongoing | 580135.28 | 276736.53 | 2022-02-03
SHAJAPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1719005013/AV/22012034576824 — Dinning Hall Arrangement Govt school Tukrana | Closed | 21785.51 | 0 | 2021-04-14
SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719005013/DP/1गोपाल — टुकराना नंदन फलोद्यान गोपाल रामबाबु टुकराना | Deleted | 268500 | 1664 | 2008-08-04
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005013/DP/22012034539028 — Samudra koop Nirman tukarana | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719005013/DP/22012034539524 — Samudayik kup nirman | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719005013/DP/22012034589132 — Vasudha Vandan- Amrit Vatika (75) Gram Panchayat Tukrana | Ongoing | 55847.4 | 11157 | 2023-09-16
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719005013/DW/9993658776 — सार्वजानिक कुप निर्माण | Closed | 0 | 0 | 2016-01-26
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1719005013/FP/22012034639533 — Flood Controal Retaining wall Shantidham k pas Tukrana | Ongoing | 618178.16 | 6 | 2024-03-14
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719005013/IC/22012034886624 — Samudayik Koop Nirman karya Goye me GP Tukrana | New | 0 | 0 | 2024-10-02
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005013/IF/22012034343129 — khet talab sah kup nirman baldev s/o bhagirath | Completed | 210000 | 208236 | 2018-06-05 | 2019-09-16
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005013/IF/22012034343133 — khet talab sah kup nirman gayatra bai w/o ram chandra | Completed | 230000 | 229664 | 2017-05-31 | 2019-09-16
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012034354441 — sarvjanik varksha ropan shantidham | Completed | 335000 | 240530 | 2017-06-21 | 2022-10-21
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012034369697 — vraksha ropan | Completed | 335000 | 860 | 2017-08-09 | 2024-04-11
SHAJAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005013/IF/22012034482997 — khet talab nirman kary jankilal bherulal | Closed | 0 | 0 | 2019-06-05
SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005013/IF/22012034566920 — kapil dhara kup ramnarayan s/o deva ji gram tukrana | Closed | 0 | 0 | 2020-04-14
SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005013/IF/22012034566921 — kapildhara kup kaluram s/o jalam gram tukran | Closed | 0 | 0 | 2020-04-14
SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005013/IF/22012034621708 — khet talab kaluram/ jalam ji sc tukrana | Closed | 0 | 0 | 2020-10-02
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024869 — Devaranyu yojana jankilal /bherulal ST tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024880 — Devarany yojana Badrilal / gangaram ST tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024887 — Devarany yojana gaytribai / ramchandra ST Tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024893 — Devarany yojana shanti bai / ramchandra ST tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024901 — Devarany yojana balchand/ghisaji SC tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024910 — Devarany yojana lilabai patidar /rajaram obc tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005013/IF/22012035024917 — devarany yojana narayan / devilal sc tukrana | Closed | 0 | 0 | 2022-08-16
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035368700 — JGSA 2025 Recharge Structure Kapildhara Koop Baldev/Bhagirath GP Tukrana | Physically Completed | 23899.46 | 23576.98 | 2025-04-27 | 2026-04-11
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035368728 — JGSA 2025 Recharge Structure Kapildhara Koop Gayatribai/Ramchandar GP Tukrana | Completed | 23899.46 | 20444.98 | 2025-04-27 | 2026-03-13
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035370465 — JGSA 2025 Sand Filter for Kapildhara Koop Atmaram/Bhagirath GP Tukrana | Completed | 23899.46 | 23663.98 | 2025-05-01 | 2025-12-16
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035371513 — JGSA 2025 Sand Filter for Kapildhara Koop PremNarayan/Armarsingh GP Tukrana | Completed | 23899.46 | 20 | 2025-04-27 | 2026-05-01
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005013/IF/22012035468254 — JGSA 2025 Khet Talab Nirman Karya Kaluram Jalamsingh GP Tukrana | Completed | 342976.7 | 218457 | 2025-05-12 | 2026-05-01
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005013/IF/22012035468311 — JGSA 2025 Khet Talab Nirman Karya Rameshchandra/Bapulal GP Tukrana | Completed | 342976.7 | 199823 | 2025-05-12 | 2026-05-01
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035469996 — Dug well richarge pit gitabai / ganpat ji tukrana | New | 0 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035474202 — JGSA 2025 Sand Filter for Kapildhara Koop Geetabai/Ganpatsingh GP Tukrana | Completed | 23899.46 | 20685.98 | 2025-05-11 | 2026-04-22
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005013/IF/22012035474240 — JGSA 2025 Sand Filter for Kapildhara Koop Govind/Gopal GP Tukrana | Closed | 23899.46 | 261 | 2025-05-12
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1232023 — Construction of IAY House -IAY REG. NO. MP1141141 | Completed | 15480 | 13746 | 2018-05-02 | 2020-04-30
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1922004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4063882 | Completed | 15660 | 13770 | 2018-10-22 | 2020-04-30
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1922019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4072072 | Completed | 15660 | 15312 | 2018-09-05 | 2019-01-28
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1922409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4012896 | Completed | 15660 | 13517 | 2018-09-05 | 2020-04-30
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1922462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4061968 | Completed | 15660 | 15312 | 2018-09-05 | 2019-03-12
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1922485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4084281 | Completed | 15660 | 15312 | 2018-09-05 | 2019-03-12
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1924088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4787808 | Completed | 15660 | 15312 | 2018-09-05 | 2019-03-12
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1924230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4835744 | Completed | 15660 | 15312 | 2018-09-05 | 2019-03-28
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1930297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5626854 | Completed | 15660 | 14616 | 2018-09-26 | 2020-04-30
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1934229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5581315 | Completed | 15660 | 14094 | 2018-10-22 | 2019-03-10
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/1935931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4852821 | Completed | 15660 | 15312 | 2018-10-18 | 2019-05-01
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/211910 — Construction of IAY House -IAY REG. NO. MP1096333 | Completed | 15030 | 14936 | 2017-02-08 | 2017-12-07
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/218545 — Construction of IAY House -IAY REG. NO. MP1180660 | Completed | 15030 | 14936 | 2017-02-08 | 2017-12-07
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/218584 — Construction of IAY House -IAY REG. NO. MP1181242 | Completed | 15030 | 16340 | 2017-06-14 | 2018-04-06
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/218679 — Construction of IAY House -IAY REG. NO. MP1182473 | Completed | 15030 | 14238 | 2017-02-08 | 2018-06-04
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/220334 — Construction of IAY House -IAY REG. NO. MP1205664 | Completed | 15030 | 14978 | 2017-02-08 | 2018-05-02
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/220998 — Construction of IAY House -IAY REG. NO. MP1215396 | Completed | 15030 | 14800 | 2017-02-08 | 2018-07-19
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/226355 — Construction of IAY House -IAY REG. NO. MP1249046 | Completed | 15030 | 14436 | 2017-02-08 | 2018-08-01
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/235428 — Construction of IAY House -IAY REG. NO. MP1411916 | Completed | 15030 | 14318 | 2017-02-08 | 2017-09-28
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/243667 — Construction of IAY House -IAY REG. NO. MP1643407 | Completed | 15030 | 14936 | 2017-02-08 | 2018-02-19
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/244658 — Construction of IAY House -IAY REG. NO. MP1673670 | Completed | 15030 | 14936 | 2017-02-08 | 2018-04-03
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/247756 — Construction of IAY House -IAY REG. NO. MP1781621 | Completed | 15030 | 14508 | 2017-02-08 | 2020-04-30
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/263521 — Construction of IAY House -IAY REG. NO. MP3196897 | Completed | 15030 | 14936 | 2017-02-08 | 2018-02-19
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/274701 — Construction of IAY House -IAY REG. NO. MP3216608 | Completed | 15030 | 14490 | 2017-02-08 | 2018-07-30
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/278294 — Construction of IAY House -IAY REG. NO. MP3744255 | Completed | 15030 | 14764 | 2017-02-08 | 2017-09-28
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/329341 — Construction of IAY House -IAY REG. NO. MP1089493 | Completed | 15030 | 14949 | 2017-02-08 | 2018-06-14
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/335458 — Construction of IAY House -IAY REG. NO. MP1103262 | Completed | 15030 | 14742 | 2017-02-08 | 2018-06-04
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/36229 — Construction of IAY House -IAY REG. NO. MP-19-005-013-001/14 | Approved | 27000 | 0 | 2015-11-17
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3689698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176385 | Completed | 18360 | 18360 | 2022-07-10 | 2022-12-06
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3691284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114703926 | Completed | 18360 | 18156 | 2022-06-20 | 2022-11-21
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3752268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120231743 | Completed | 18360 | 18360 | 2022-07-21 | 2024-02-28
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3761707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120349351 | Completed | 18360 | 18360 | 2022-07-10 | 2022-12-10
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3761711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120349767 | Completed | 18360 | 18360 | 2022-07-10 | 2023-05-05
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/383713 — Construction of IAY House -IAY REG. NO. MP1163580 | Completed | 15030 | 14961 | 2017-02-08 | 2018-06-04
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/387869 — Construction of IAY House -IAY REG. NO. MP1180673 | Completed | 15030 | 13566 | 2017-03-15 | 2021-06-23
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/3879963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147146771 | Completed | 18360 | 17952 | 2022-07-21 | 2023-07-08
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/389680 — Construction of IAY House -IAY REG. NO. MP1187984 | Completed | 15030 | 14794 | 2017-02-08 | 2018-04-03
SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/407311 — Construction of IAY House -IAY REG. NO. MP1240822 | Completed | 15030 | 20363 | 2017-02-08 | 2018-10-26
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4221924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113617578 | Completed | 18360 | 18360 | 2022-07-10 | 2022-12-12
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4223526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177239 | Completed | 18360 | 18360 | 2022-07-10 | 2023-05-05
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4227460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119822565 | Completed | 18360 | 18360 | 2022-07-28 | 2022-11-21
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4227808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120349554 | Completed | 18360 | 17952 | 2022-07-21 | 2023-05-05
SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4275230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115112002 | Completed | 18360 | 18360 | 2022-07-28 | 2023-09-25
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4563867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176514 | Completed | 23490 | 21870 | 2024-11-21 | 2025-11-01
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4588937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121562207 | Completed | 21870 | 21870 | 2024-10-22 | 2025-03-07
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4741755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113619416 | Completed | 23490 | 21870 | 2024-11-21 | 2025-11-01
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4741799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113626706 | Completed | 23490 | 17982 | 2024-12-05 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/4747609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176550 | Completed | 21870 | 21870 | 2024-11-21 | 2025-11-01
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/48460 — Construction of IAY House -IAY REG. NO. MP-19-005-013-001/13 | Approved | 27000 | 0 | 2015-12-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5155796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177210 | Physically Completed | 23490 | 21141 | 2025-05-24 | 2026-03-22
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5216951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120350964 | Completed | 23490 | 22968 | 2025-05-26 | 2026-02-24
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5357580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119830759 | Ongoing | 27000 | 17916 | 2025-07-13
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5358657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114710116 | Physically Completed | 23490 | 18270 | 2025-07-13 | 2026-08-09
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5360315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176757 | Physically Completed | 23490 | 21924 | 2025-05-24 | 2026-03-22
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5360680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176447 | Completed | 23490 | 23229 | 2025-05-24 | 2025-11-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5364357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114709167 | Completed | 23490 | 21924 | 2025-05-04 | 2026-05-06
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5367564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176418 | Completed | 23490 | 23229 | 2025-05-04 | 2025-11-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5368236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120351905 | Completed | 23490 | 22446 | 2025-05-24 | 2026-02-24
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5369551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177057 | Completed | 23490 | 23229 | 2025-05-24 | 2025-11-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5371830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122467103 | Physically Completed | 23490 | 21924 | 2025-05-24 | 2026-08-25
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5373552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120351665 | Completed | 23490 | 22707 | 2025-05-24 | 2026-08-05
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5373783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113626781 | Completed | 23490 | 23229 | 2025-05-04 | 2025-11-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5374140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119830081 | Physically Completed | 23490 | 21924 | 2025-05-24 | 2025-12-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5376433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132474812 | Ongoing | 27000 | 20097 | 2025-05-24
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5377118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177030 | Ongoing | 27000 | 14616 | 2025-05-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5378524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176328 | Physically Completed | 23490 | 21924 | 2025-05-04 | 2026-03-22
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5378915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120350730 | Ongoing | 27000 | 16182 | 2025-08-22
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5383716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176724 | Completed | 23490 | 23229 | 2025-05-04 | 2025-11-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5662668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120350136 | Ongoing | 27000 | 16182 | 2025-09-30
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5687098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177145 | Completed | 23490 | 23490 | 2025-09-30 | 2026-05-06
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5687238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115176919 | Ongoing | 27000 | 10701 | 2025-08-28
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5797160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114709270 | Approved | 27000 | 0 | 2025-03-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5797686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120351418 | Completed | 23490 | 21402 | 2025-09-13 | 2026-08-05
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/5797862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115177289 | Completed | 23490 | 18270 | 2025-09-13 | 2026-08-25
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/624973 — Construction of IAY House -IAY REG. NO. MP1781656 | Completed | 15030 | 14448 | 2017-05-24 | 2017-12-07
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/789148 — Construction of IAY House -IAY REG. NO. MP1735941 | Completed | 15480 | 15136 | 2017-06-14 | 2018-06-04
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/795262 — Construction of IAY House -IAY REG. NO. MP2190965 | Completed | 15480 | 14940 | 2018-02-14 | 2018-12-21
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/795270 — Construction of IAY House -IAY REG. NO. MP2191707 | Completed | 15480 | 15492 | 2017-12-20 | 2018-05-10
SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/796799 — Construction of IAY House -IAY REG. NO. MP2299504 | Completed | 15480 | 15786 | 2018-04-02 | 2020-05-26
SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/802524 — Construction of IAY House -IAY REG. NO. MP2984422 | Completed | 17100 | 15240 | 2017-12-20 | 2020-03-16
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005013/IF/IAY/94084 — Construction of IAY House -IAY REG. NO. MP-19-005-013-001/03 | Approved | 27000 | 0 | 2015-10-31
SHAJAPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719005013/LD/22012034260514 — शांतिधाम | Physically Completed | 185400 | 181952.96 | 2017-03-08 | 2018-06-14
SHAJAPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005013/LD/22012034296961 — Santidham nirman tukrana | Closed | 0 | 0 | 2016-10-02
SHAJAPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005013/LD/22012034298411 — shantidham vikas karya | Closed | 0 | 0 | 2016-10-02
SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005013/LD/नन्‍दनवन गोंविन्‍द गोपाल टुकराना — नन्‍दनवन गोंविन्‍द गोपाल टुकराना | Deleted | 107400 | 0 | 2008-06-30
SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1719005013/PG/9425888200 — खेलमैदान | Closed | 0 | 0 | 2016-01-26
SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034172571 — मनरेगा पंचपरमेश्‍वर सीसी रोड एवं नाली निर्माण टुकर | Completed | 133600 | 128318 | 2014-01-15 | 2014-09-17
SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034206259 — अनुसूचित जाति मोहल्‍ला पंचपरमेश्‍वर एवं सीसी रोड व | Completed | 142200 | 129384 | 2014-02-19 | 2014-09-17
SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034221705 — CC ROAD TUKRANA | Deleted | 0 | 0 | 2014-01-26
SHAJAPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034229214 — c c road nalai nirman (kashi ram ke makan se rav | Completed | 189800 | 176464 | 2014-09-17 | 2015-05-10
SHAJAPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034229222 — c c road nali nirman (savi singh ke makan se bora | Completed | 189800 | 176760 | 2014-09-17 | 2015-04-09
SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034266307 — c.c.pp kalu singh se unkasingh tak | Completed | 193300 | 193131 | 2015-06-17 | 2016-06-08
SHAJAPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034299022 — cc road pp kaluram ke makan se nala tak | Completed | 140800 | 142473 | 2016-11-19 | 2018-06-14
SHAJAPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034304315 — सी.सी.रोड एवं नाली निर्माण | Completed | 219300 | 201368 | 2016-11-23 | 2018-06-14
SHAJAPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034320604 — C C road pp & nali nirman | Closed | 0 | 0 | 2016-10-02
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719005013/RC/22012034339523 — सुदुर ग्राम सम्‍पर्क सडक(ग्रेवल रोड) निर्माण- गांव के पुलिया से खेडा तक-ग्राम टूकराना | Closed | 1100000 | 0 | 2017-05-30
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034361894 — सी-सी रोड+नाली निर्माण्‍ा-दुलेसिंह के मकान से विष्‍णु के मकान तक-ग्राम टुकराना | Completed | 136100 | 133928 | 2017-10-18 | 2018-06-14
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034368551 — Road nirman | Closed | 0 | 0 | 2018-04-01
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034397095 — c c rod nalinirman nale se om prakash ke makan tak | Completed | 52800 | 53796 | 2019-02-28 | 2020-01-01
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034397108 — c c raod magilal ke makan se rajmal ke makan tak | Completed | 44600 | 43764 | 2019-02-28 | 2019-10-30
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1719005013/RC/22012034438880 — Cc road antersingh ke Markham se bane singh ke Markham tak | Closed | 0 | 0 | 2018-12-24
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034448655 — C C road Babulal ke ghar se Ramchandra ke ghar tak Tukrana | Completed | 16076 | 13578 | 2019-03-06 | 2020-04-02
SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034448661 — C C road onkarsingh ke ghar se Ramlakhan ke ghar tak Tukrana | Completed | 113305 | 109400 | 2019-03-06 | 2019-09-12
SHAJAPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034476544 — C C Road Nali Nirman Rajaram ke ghar se RamkunwarBai ke ghar tak GP Tukrana | Completed | 111860 | 107489.6 | 2019-09-11 | 2020-07-23
SHAJAPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034476548 — C C Road Nali Nirman Main Road Se High School Tak GP Tukarana | Completed | 54860 | 53111 | 2019-09-27 | 2020-05-17
SHAJAPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034532279 — सी.सी.रोड+निर्माण-जानकीलाल के मकान से हरिओम के घर तक-ग्राम टुकराना | Completed | 148558 | 146102 | 2020-08-22 | 2021-09-02
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034655430 — C.C.Road Nirman Ramchandra ke makan se ashok bali ke makan tak gram tukrana | Completed | 57782 | 55300 | 2023-10-06 | 2024-07-03
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Maintenance of bridges constructed by the BRO / Maintenance of bridges constructed by the Border Roads Organization | Other Works | 1719005013/RC/22012034655779 — nali nirmand kisore patidar ke makan se nale tak tukrana | Closed | 0 | 0 | 2023-08-16
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034832438 — jankilal ke makan se syam ke makan tak cc road tukrana | Completed | 52000 | 51992 | 2025-01-23 | 2025-07-30
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034832442 — hariom ke makan se men road ki taraf tukrana | Completed | 111000 | 110911 | 2025-01-23 | 2025-10-09
SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005013/RC/22012034848473 — dud deri se bherulal ke makan tak cc road tukrana | Physically Completed | 97000 | 83781 | 2026-01-02 | 2026-07-23
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034361359 — sochalay niman marramat balchand babuji | Completed | 11000 | 10680 | 2017-08-02 | 2017-12-07
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034361362 — sochalay niman marramat aatamaram bhagirath | Completed | 11000 | 10680 | 2017-08-02 | 2017-12-07
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034361363 — sochalay niman marramat pramod kumar devilal | Completed | 11000 | 10164 | 2017-08-02 | 2018-02-16
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034362736 — sochalay niman marramat hiralal dhulaji | Completed | 11000 | 10132 | 2017-08-09 | 2024-07-09
SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034362738 — sochalay niman marramat nathu lal sidhnath | Completed | 11000 | 10852 | 2017-08-09 | 2017-12-07
SHAJAPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005013/RS/22012034499962 — Samudayik swachhata Parishad temmpu stand ke pas | Closed | 0 | 0 | 2020-08-15
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719005013/RS/22012035112811 — NALI NIRMAN KARY KISHOR KE MAKAN SE NALE TAK GRAM TUKRANA | Completed | 27912 | 27650 | 2023-10-07 | 2024-07-16
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719005013/RS/22012035125149 — jankilal ke makan se vishnuprasad ke makan tak nali nirman tukrana | Completed | 37347 | 36677 | 2024-03-15 | 2024-11-04
SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719005013/RS/22012035125150 — nali nirman dayaram ke makan se ramchandra ke makan tak | Completed | 11523 | 10838 | 2024-03-15 | 2024-10-26
SHAJAPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1719005013/WC/22012034424261 — stegard kanturr trench tukrana | Completed | 163500 | 148448 | 2018-10-04 | 2020-05-25
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1719005013/WC/22012034559827 — stegard kanturr trench tukrana | Completed | 331191.5 | 298515 | 2020-08-07 | 2021-12-01
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005013/WC/22012034578008 — Shanti dham hendpamp ke pass richarge pit | Completed | 14283.77 | 10648 | 2020-09-03 | 2020-11-23
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005013/WC/22012034578218 — kheda handpamp ke pass richarge pitt | Completed | 14283.77 | 13878 | 2020-09-03 | 2021-09-14
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005013/WC/22012034578221 — panchayat ke pass richarge pitt | Completed | 14283.77 | 13322 | 2020-09-03 | 2021-08-01
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005013/WC/22012034580157 — High school ke pass richarge pitt | Completed | 14283.77 | 11487 | 2020-09-03 | 2021-04-02
SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012034589689 — Water Harvesting Pond kala baldha tukrana | Closed | 0 | 0 | 2020-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005013/WC/22012034830983 — Rup water harvesting high school part 2 | Completed | 22084.84 | 9600 | 2021-11-18 | 2024-01-21
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005013/WC/22012034830992 — Rup water harvesting high school part 1 | Completed | 22065.94 | 10422 | 2021-12-02 | 2022-12-12
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1719005013/WC/22012034866161 — Contour trench pahadi dhalan pan | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034886581 — Contour trench nirman pahadi parr | Deleted | 0 | 0 | 2021-10-01
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034886582 — Contour trench nirman pahadi parr | Closed | 0 | 0 | 2021-10-01
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012034908769 — खेत तालाब निर्माण रमेशचंद्र पिता पिता बापूजी | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012034912644 — water harwesting pond jikhdiya balda tukrana | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012034912652 — Samudayik farm pond goya me | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005013/WC/22012034912669 — Bolder chek dem devnarayan mandir ke pass | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034912683 — Contour trench puwadiya balda tukrana | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034912699 — Contour trench puwadiya balda tukrana | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034912701 — Contour trench puwadiya balda tukrana | Completed | 207610.94 | 217632 | 2022-03-09 | 2022-06-01
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1719005013/WC/22012034918614 — repair of stop dam akhilesh ke khet ke pas | Closed | 49000 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1719005013/WC/22012034918617 — repair of stop dam 4 akhilesh ke khet ke pas | Closed | 0 | 0 | 2022-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012034922111 — Khet talab nirman mansingh s/o narayan | Closed | 0 | 0 | 2022-01-27
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WC/22012034937239 — parcolation tank tukrana pahadi | Closed | 0 | 0 | 2022-04-01
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WC/22012034937244 — parcolation tank tukrana pahadi | Closed | 0 | 0 | 2022-04-01
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WC/22012034937246 — parcolation tank tukrana pahadi | Closed | 0 | 0 | 2022-04-01
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WC/22012034937250 — parcolation tank tukrana pahadi | Closed | 0 | 0 | 2022-04-01
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1719005013/WC/22012034945817 — navin talab nirman puwadiya balda ke pass tukrana | Completed | 874656.72 | 786276 | 2022-05-20 | 2024-04-13
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1719005013/WC/22012034945820 — navin talab nirman puwadiya balda ke pass tukrana | Closed | 0 | 0 | 2022-04-09
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005013/WC/22012034980441 — Check dam nirman badrilalke khet ke pas gp tukrana | Closed | 0 | 0 | 2022-04-14
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034980450 — Contour trench talai ke pass balda tukrana | Closed | 411616.89 | 0 | 2022-04-14
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012034980467 — Contour trench nirman talai ke pass pahadi par | Closed | 0 | 0 | 2022-04-14
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035042233 — Khet takab nirman rameshchandra s/o bapulal | Closed | 385261.22 | 0 | 2023-01-25
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035042235 — Khet takab nirman ramesh /bapulal | Closed | 0 | 0 | 2023-01-25
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035042236 — Khet takab nirman kaluram/jalamsingh | Closed | 385261.22 | 0 | 2023-01-25
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035043780 — khet talab nirman mansingh s/o narayan | Closed | 0 | 0 | 2023-01-25
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035043812 — Khet talab nirman mansingh s/o narayan | Closed | 0 | 0 | 2023-01-25
SHAJAPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1719005013/WC/22012035048013 — Puliya nirman kalaji maharaj ke nale par tukrana | Closed | 0 | 0 | 2023-01-26
SHAJAPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1719005013/WC/22012035048014 — Puliya nirman kalaji maharaj ke nale par tukrana | Closed | 0 | 0 | 2023-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012035089175 — khaderiya balda tukrana | Closed | 0 | 0 | 2023-04-14
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005013/WC/22012035090120 — contour trench khanderiya balda tukrana | Completed | 619008.69 | 526053 | 2023-09-26 | 2024-11-11
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171173 — Gully Plug Nirman Karya 1 | Closed | 0 | 0 | 2024-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171175 — Gully Plug Nirman Karya 1 | Completed | 52648.54 | 38505 | 2024-03-17 | 2026-03-05
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171183 — Gully Plug Nirman Karya 2 tukrana | Closed | 0 | 0 | 2024-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171185 — Gully Plug Nirman Karya 2 tukrana | Closed | 0 | 0 | 2024-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171186 — Gully Plug Nirman Karya 2 tukrana | Closed | 0 | 0 | 2024-01-26
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171187 — Gully Plug Nirman Karya 2 tukrana | Completed | 52648.54 | 38808 | 2024-03-17 | 2026-03-05
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1719005013/WC/22012035171192 — Gully Plug Nirman Karya 3 Tukrana | Closed | 0 | 0 | 2024-01-26
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005013/WC/22012035232614 — Construction of Percolation tank Tukrana Pahadi ke niche | Approved | 701044.38 | 0 | 2024-10-02
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005013/WC/22012035269716 — JGSA 2025 Recharge Structure Sarvajanik Koop Shamshan ke Pass GP Tukrana | Completed | 23899.46 | 15660 | 2025-06-12 | 2026-05-02
SHAJAPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719005013/WH/19956157 — talab marmat (gahrikaran) thukrana | Completed | 84181 | 16032 | 2016-05-19 | 2019-04-26
SHAJAPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/19961889 — talab jirnodhhar gram tukrana | Completed | 168000 | 120221 | 2017-05-31 | 2019-08-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034455023 — Stopdam jirnodhar/ marmat moti shing ke khet ke pass | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034455403 — Stop dam Jirnodhar/marammat kary ghanshyam ke khet ke pass | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034455405 — Stopdam jirnodhar / marmmat akhlesh ke khet ke pass | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034909795 — Stop dam jirnodhar/marammat moti singh ke khet ke pass GP tukrana | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034909798 — Stopdam jirnodhar/ marammat Moti singh ke khet ke pass | Completed | 50000 | 47166 | 2022-03-22 | 2024-03-31
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034909805 — Stopdam jirnodhar/ marammat Ghanshyam ke khet ke pass | Completed | 44000 | 65010 | 2022-03-23 | 2022-12-11
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034909806 — Stop dam jirnodhar /marammat ghanshyam ke khet ke pass | Closed | 0 | 0 | 2021-10-02
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034909943 — Talab jirnodhwar kala balda tukrana | Closed | 0 | 0 | 2022-01-27
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005013/WH/22012034939052 — talab jirnodhar nirman | New | 0 | 0 | 2023-04-14