## Work List
Exported on: 2026-09-15 12:33:27
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: HARANGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719005018/DP/22012034590931 — Vasudha Vandan- Amrit Vatika (75) Gram Panchayat Harangaon | Ongoing | 55847.4 | 0 | 2023-09-13
SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005018/IF/22012035206094 — KUP NIRMAN-SITARAM-MADAN SINGH | Ongoing | 282417.57 | 0 | 2024-03-11
SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005018/IF/22012035206097 — KUP NIRMAN-JITENDRA-BHAGWAN SINGH-HARANGAON | Ongoing | 282417.57 | 0 | 2024-03-11
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005018/IF/22012035294586 — Khet Talab Nirman Kary Makhan Singh / Prabhulal Gp Harnganv | Ongoing | 381704.65 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005018/IF/22012035294587 — Khet Talab Nirman Kary Madusingh / Uprav Singh Gp Harnganv | Ongoing | 381704.65 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005018/IF/22012035294876 — Khet talab nirman bane singh/ kishan jiii | Ongoing | 381704.65 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005018/IF/22012035294964 — Khet talab nirman bhagwan singh / nanuram ji gp haranganv | Ongoing | 381704.65 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005018/IF/22012035423703 — khet talab nirman gyan singh / madan ji gp haranganv | Ongoing | 408999.79 | 0 | 2025-05-02
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005018/IF/22012035468719 — Dug vell recharge babu lal pita ram singh | Approved | 0 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005018/IF/22012035468767 — Dug vell recharge Hokam singh shankar lal | Approved | 0 | 0 | 2025-04-14
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005018/IF/22012035468799 — Dug well recharge Ramesh bheru singh | Approved | 0 | 0 | 2025-04-14
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5949990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453232 | Completed | 23490 | 1500 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5950025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114089782 | Physically Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5952525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117308063 | Physically Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5952734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453496 | Completed | 23490 | 1500 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5953103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120890111 | Completed | 23490 | 0 | 2026-03-18 | 2026-07-21
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5954843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115961706 | Completed | 23490 | 0 | 2026-03-18 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5954844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115961754 | Completed | 23490 | 0 | 2026-03-18 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5955971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106452992 | Completed | 23490 | 0 | 2026-03-18 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5955972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453020 | Ongoing | 27000 | 0 | 2026-04-04
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5955973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453037 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5955974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453109 | Ongoing | 27000 | 0 | 2026-04-04
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5956286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686537 | Completed | 23490 | 1500 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5957122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118577550 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5957123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118577887 | Completed | 23490 | 1500 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5957521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113890984 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5957522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113891058 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5957524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113891593 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5958256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104928235 | Completed | 23490 | 0 | 2026-05-03 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5959214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106632915 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5961946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115962500 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5961947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115962670 | Ongoing | 27000 | 0 | 2026-04-04
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5963325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124194203 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5964535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104930195 | Physically Completed | 23490 | 0 | 2026-03-18 | 2026-08-25
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5964613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115962422 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5965053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686109 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5965054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118533515 | Completed | 23490 | 0 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5965055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117021779 | Physically Completed | 23490 | 0 | 2026-03-18 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5965056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117409331 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5965350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117406919 | Ongoing | 27000 | 3900 | 2026-03-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5966059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118577724 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5966440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117409103 | Completed | 23490 | 1500 | 2026-04-04 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5966455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119314082 | Physically Completed | 23490 | 0 | 2026-03-18 | 2026-07-17
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/5972569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686849 | Ongoing | 27000 | 0 | 2026-03-18
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6067780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104927890 | Ongoing | 27000 | 0 | 2026-07-21
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6067781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104928667 | Ongoing | 27000 | 0 | 2026-07-21
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6067782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104928921 | Approved | 27000 | 0 | 2026-02-18
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6069019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106420380 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6071004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114089596 | Ongoing | 27000 | 4200 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6072625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337501 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6072696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115366390 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6073652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115961653 | Approved | 27000 | 0 | 2026-02-27
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6073655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115962202 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6075282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117021792 | Physically Completed | 23490 | 0 | 2026-05-03 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6075283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117021820 | Completed | 23490 | 0 | 2026-05-03 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6075284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117021869 | Completed | 23490 | 0 | 2026-05-03 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6075682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117308052 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6075683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117308182 | Ongoing | 27000 | 0 | 2026-07-17
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6079744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119896031 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6080735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120890082 | Ongoing | 27000 | 0 | 2026-05-03
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6081022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121365144 | Ongoing | 27000 | 0 | 2026-07-21
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6243411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106019765 | Ongoing | 27000 | 2100 | 2026-07-21
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6243550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104927737 | Ongoing | 23490 | 0 | 2026-08-18
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6243552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104929492 | Approved | 27000 | 0 | 2026-02-27
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686443 | Approved | 23490 | 0 | 2026-04-15
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686649 | Approved | 23490 | 0 | 2026-04-15
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106228132 | Approved | 23490 | 0 | 2026-05-13
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106228278 | Approved | 23490 | 0 | 2026-05-13
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106452922 | Approved | 23490 | 0 | 2026-05-04
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005018/IF/IAY/6245416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113891239 | Approved | 23490 | 0 | 2026-05-13
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005018/RC/22012034819360 — CC road Nirman Nirbhay singh ke makan se prabhulal ke makan tak gram harangaon | Approved | 72000 | 0 | 2024-06-10
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719005018/RS/22012035127908 — Nali nirman Ramesh ke makan se Mangilal ke makan tak gram Harangaon | Approved | 49300 | 0 | 2024-06-17
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719005018/RS/22012035127910 — Nali nirman sodan singh ke makan se Ladsingh ke makan tak gram Harangaon | Approved | 49500 | 0 | 2024-06-18
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005018/WH/22012034939058 — talab jirnodhar nirman | New | 0 | 0 | 2024-04-14