## Work List
Exported on: 2026-10-24 19:50:01
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: RAMPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719005023/IC/22012034887041 — samudhyak kup nirman rampura colany 1 | New | 0 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719005023/IC/22012034887118 — samudhyak kup nirman rampura bhya ba ke khet pas | New | 0 | 0 | 2024-10-02
SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719005023/IF/22012034567144 — Kapil dhara kup nirman gopal | Completed | 242453.87 | 0 | 2020-12-14 | 2026-10-06
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719005023/IF/22012035283005 — kapil dhara kup nirman anil sain | Approved | 0 | 0 | 2024-10-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719005023/IF/22012035370108 — Kapildhara koop nirman devbai gram rampura | Ongoing | 301783.99 | 0 | 2025-12-20
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1719005023/IF/22012035469138 — Recharge pit pepkuvar Bai | New | 0 | 0 | 2025-05-04
SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1719005023/IF/22012035469255 — Recharge pit pepkuvar Bai | New | 0 | 0 | 2025-05-04
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4552701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113726522 | Completed | 23490 | 0 | 2024-11-16 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4560047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115396540 | Completed | 23490 | 0 | 2024-12-05 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4560394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115359938 | Completed | 23490 | 0 | 2025-01-25 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4569302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116545455 | Completed | 23490 | 0 | 2024-12-13 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4582086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118724268 | Completed | 23490 | 0 | 2024-12-13 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4582088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118724372 | Completed | 23490 | 0 | 2024-12-13 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4587776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120262245 | Completed | 23490 | 0 | 2024-12-07 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4700196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113985860 | Completed | 23490 | 0 | 2024-12-13 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4700198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113994488 | Completed | 23490 | 0 | 2024-12-05 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4701704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749945 | Completed | 23490 | 0 | 2025-01-25 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4702900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119937480 | Completed | 23490 | 0 | 2025-01-25 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4705181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120268565 | Completed | 23490 | 0 | 2024-11-07 | 2026-08-05
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/4750496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116545255 | Completed | 23490 | 0 | 2024-12-13 | 2026-08-05
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5180393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117141985 | Physically Completed | 23490 | 9000 | 2025-08-28 | 2026-08-23
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5203423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117139055 | Ongoing | 27000 | 0 | 2025-09-08
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5230296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124092322 | Approved | 27000 | 0 | 2025-03-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5385742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119938042 | Ongoing | 27000 | 4200 | 2025-08-01
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5387938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115182816 | Ongoing | 27000 | 0 | 2026-05-02
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5395255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124095783 | Ongoing | 27000 | 4200 | 2025-08-28
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5395256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124096981 | Physically Completed | 27000 | 10500 | 2025-08-28 | 2026-10-04
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5397755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115205256 | Approved | 27000 | 0 | 2025-03-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5399031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116973057 | Physically Completed | 23490 | 4698 | 2025-09-08 | 2026-08-05
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5403053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120260840 | Completed | 23490 | 0 | 2025-06-10 | 2026-08-05
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5405611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117155789 | Ongoing | 27000 | 0 | 2025-08-28
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5405918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117130993 | Approved | 27000 | 0 | 2025-03-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5406248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117149752 | Ongoing | 27000 | 0 | 2025-09-08
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5408731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116544947 | Ongoing | 27000 | 0 | 2025-07-21
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5411867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120263674 | Ongoing | 27000 | 25200 | 2026-08-04
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5522332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118724319 | Ongoing | 27000 | 0 | 2025-06-11
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5644705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125804855 | Ongoing | 27000 | 0 | 2026-09-14
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5661667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114764354 | Ongoing | 27000 | 0 | 2025-09-24
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5662979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115404033 | Physically Completed | 27000 | 16800 | 2026-07-16 | 2026-10-04
SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5692640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113780488 | Ongoing | 27000 | 4200 | 2026-09-14
SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5722184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115166708 | Approved | 27000 | 0 | 2025-03-07
SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/5797481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115163486 | Completed | 23490 | 0 | 2026-02-09 | 2026-08-05
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/94079 — Construction of IAY House -IAY REG. NO. MP-19-005-023-001/65 | Approved | 27000 | 0 | 2015-10-31
SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719005023/IF/IAY/94080 — Construction of IAY House -IAY REG. NO. MP-19-005-023-002/28 | Approved | 27000 | 0 | 2015-10-31
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719005023/RC/22012034832718 — cc road nirman pm sadak se samudhyak bhavan tak rampura | Approved | 59800 | 0 | 2024-10-02
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719005023/RC/22012034839935 — CC road nirman karya Damar road se Radheshyam varma ke ghar ki or | Approved | 150000 | 0 | 2025-01-26
SHAJAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719005023/RC/22012034839937 — CC Road nirman karya Pradhanmantri sadak se samudayik bhawan tak Rampura | Approved | 0 | 0 | 2025-01-26
SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719005023/WC/22012034773742 — Watar harvesting pond pachola road rampura | Ongoing | 160572.96 | 0 | 2021-07-02
SHAJAPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1719005023/WC/22012034779579 — Flood control channel and bank establishment manglik bhavan k pas mewasa | Ongoing | 900040.69 | 0 | 2021-07-10
SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1719005023/WC/22012035017484 — DUG OUT POND AMRUT SAROVER SET KA KHATA RAMPURA | Ongoing | 1489309.95 | 0 | 2022-12-14
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1719005023/WH/22012034938937 — Contour trench Rampura mewasa1 | New | 0 | 0 | 2024-04-01
SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1719005023/WH/22012034938939 — Contour trench Rampura mewasa2 | New | 0 | 0 | 2024-04-01
SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plug for Community | Boulder Check/Gully Plug | 1719005/WC/22012035169611 — Construction of Gully plug gram Rampura | New | 0 | 0 | 2024-01-26