## Work List
Exported on: 2026-10-18 14:21:26
Filters applied:
Data source: VBGRAMG
District: SHAJAPUR
Block: All
Panchayat: BARNAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MOMAN BADODIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1719006009/AV/22012034390118 — Panchayat bhawan nirman barnavad | Ongoing | 579200 | 0 | 2019-01-09
MOMAN BADODIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1719006009/IF/22012034584065 — nandan faloudyan dolatram-ramsingh barnawad | Ongoing | 161671.42 | 0 | 2020-07-23
MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719006009/IF/22012035275499 — Kapildhara Kup nirman mohansingh fullsingh | Approved | 0 | 0 | 2024-12-03
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719006009/IF/22012035275514 — Kapildhara Kup nirman mohansingh fullsingh | Ongoing | 292212.8 | 0 | 2025-05-11
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719006009/IF/22012035499348 — Kapildhara kup nirman Jagdesh chandra Aatmaram OBC Barnawad | Ongoing | 292212.8 | 0 | 2026-03-26
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719006009/IF/22012035499379 — Kapildhara kup nirman Bherulal Govardhan lal ST Barnawad | Approved | 292212.8 | 0 | 2025-04-14
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719006009/IF/22012035621316 — Ek Bagiya Maa Ke Naam Ramkuwar bai /Babulal MP-19-006-009-001/508 | Approved | 263510.03 | 0 | 2025-09-11
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719006009/IF/22012035621359 — Ek Bagiya maa ke naam Lalita bai / Bhagirath Bhilala MP-19-006-009-001/22-C GP barnawad | New | 0 | 0 | 2025-09-11
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719006009/IF/22012035622110 — Ek Bagiya maa ke naam lalita bai / bhagirath bhilala SHG EAK LUVYA GP Barnawad | Ongoing | 263510.03 | 7200 | 2025-10-10
MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/4589102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121581277 | Ongoing | 27000 | 0 | 2024-11-30
MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/4719436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141590611 | Ongoing | 27000 | 3600 | 2025-01-21
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/4721134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141895560 | Physically Completed | 23490 | 0 | 2026-02-20 | 2026-08-02
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5457166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147887302 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-08-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5461808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121429964 | Ongoing | 27000 | 0 | 2025-10-30
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5462298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121426549 | Ongoing | 27000 | 0 | 2026-09-11
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5464457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121719892 | Physically Completed | 23490 | 0 | 2025-10-30 | 2026-08-23
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5465097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894202 | Physically Completed | 27000 | 0 | 2025-09-17 | 2026-09-20
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5466119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141772867 | Physically Completed | 23490 | 0 | 2025-09-10 | 2026-08-02
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5496723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148175423 | Ongoing | 27000 | 0 | 2025-09-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5504042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147217034 | Physically Completed | 23490 | 0 | 2025-10-27 | 2026-08-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5504046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147261941 | Physically Completed | 27000 | 0 | 2025-11-01 | 2026-10-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5504047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263096 | Ongoing | 27000 | 0 | 2025-10-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5504048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263247 | Approved | 27000 | 0 | 2025-04-19
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5506886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121938306 | Completed | 23490 | 0 | 2025-11-01 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5507774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141589176 | Physically Completed | 27000 | 5400 | 2025-10-27 | 2026-09-13
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5507775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141589519 | Ongoing | 27000 | 7200 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5507980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121558315 | Completed | 23490 | 0 | 2025-09-19 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5508040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121654492 | Physically Completed | 27000 | 0 | 2025-11-01 | 2026-09-20
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5509445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141896739 | Ongoing | 27000 | 7200 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5509447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147262380 | Ongoing | 27000 | 3600 | 2025-10-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5509547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127316020 | Physically Completed | 27000 | 0 | 2025-10-30 | 2026-09-13
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5509751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121431207 | Physically Completed | 27000 | 7200 | 2025-09-09 | 2026-09-06
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5509873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142048172 | Physically Completed | 23490 | 0 | 2025-10-27 | 2026-08-16
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133089954 | Completed | 23490 | 0 | 2026-02-25 | 2026-08-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133089955 | Ongoing | 27000 | 0 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133089967 | Physically Completed | 23490 | 1800 | 2025-09-15 | 2026-08-02
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122356571 | Ongoing | 27000 | 14400 | 2026-09-11
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147179472 | Completed | 23490 | 0 | 2025-07-28 | 2026-08-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147218203 | Ongoing | 27000 | 3600 | 2025-07-25
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5510976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147180467 | Ongoing | 27000 | 4800 | 2025-07-21
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5511033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141588788 | Ongoing | 27000 | 3600 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5512857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121586807 | Physically Completed | 23490 | 0 | 2025-09-18 | 2026-08-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5512890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121424736 | Ongoing | 27000 | 0 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5560214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121843478 | Physically Completed | 23490 | 0 | 2025-09-19 | 2026-07-26
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5561284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147180525 | Ongoing | 27000 | 0 | 2025-06-23
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5576739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147216877 | Completed | 23490 | 0 | 2025-10-29 | 2026-08-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5604719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128077044 | Physically Completed | 27000 | 3600 | 2025-10-30 | 2026-10-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5619196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121938266 | Ongoing | 27000 | 0 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5649276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141563884 | Ongoing | 27000 | 7200 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5650278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147218311 | Completed | 23490 | 0 | 2025-09-24 | 2026-08-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5650480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147177925 | Ongoing | 27000 | 0 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5650528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141587863 | Completed | 23490 | 0 | 2025-10-30 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5650529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894392 | Ongoing | 27000 | 0 | 2025-09-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5651123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263769 | Ongoing | 27000 | 1200 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147261513 | Physically Completed | 27000 | 12600 | 2025-09-18 | 2026-10-04
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147662667 | Ongoing | 27000 | 0 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141895655 | Ongoing | 27000 | 0 | 2025-10-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141896496 | Physically Completed | 23490 | 0 | 2025-09-11 | 2026-08-09
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147261282 | Completed | 23490 | 0 | 2025-09-10 | 2026-08-03
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147262984 | Physically Completed | 23490 | 0 | 2025-09-17 | 2026-08-02
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263942 | Ongoing | 27000 | 0 | 2026-02-20
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121024836 | Ongoing | 27000 | 0 | 2025-11-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121012162 | Physically Completed | 23490 | 7200 | 2025-09-17 | 2026-08-23
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147178470 | Completed | 23490 | 0 | 2025-11-24 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121406673 | Ongoing | 27000 | 0 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894353 | Ongoing | 27000 | 0 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141590551 | Ongoing | 27000 | 0 | 2025-09-17
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141590827 | Ongoing | 27000 | 0 | 2025-10-27
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121656835 | Ongoing | 27000 | 7200 | 2025-09-17
MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263365 | Approved | 27000 | 0 | 2025-03-24
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121427138 | Ongoing | 27000 | 1800 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148204439 | Ongoing | 27000 | 3600 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121402603 | Physically Completed | 27000 | 7200 | 2025-09-17 | 2026-09-20
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121652470 | Physically Completed | 23490 | 0 | 2025-10-27 | 2026-07-26
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141772825 | Completed | 23490 | 0 | 2025-09-17 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121422659 | Physically Completed | 23490 | 0 | 2026-02-20 | 2026-08-02
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5659668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141588586 | Ongoing | 27000 | 0 | 2025-09-17
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5666046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133089932 | Ongoing | 27000 | 3600 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5672839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141895095 | Ongoing | 27000 | 3600 | 2025-09-17
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5672841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141896147 | Ongoing | 27000 | 3600 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5672899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121403421 | Ongoing | 27000 | 10800 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5688979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147263906 | Ongoing | 27000 | 3600 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5708824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121556462 | Ongoing | 27000 | 0 | 2025-09-18
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5776201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894239 | Completed | 23490 | 0 | 2025-10-27 | 2026-07-31
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5799464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141587509 | Ongoing | 27000 | 3600 | 2025-10-30
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5799823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121427741 | Physically Completed | 23490 | 3600 | 2025-09-17 | 2026-08-16
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5799977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141587155 | Ongoing | 27000 | 5400 | 2025-11-01
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5800299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147249480 | Physically Completed | 27000 | 3600 | 2025-11-01 | 2026-09-20
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5800857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121012310 | Physically Completed | 27000 | 0 | 2025-09-18 | 2026-08-30
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5869735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121419605 | Ongoing | 27000 | 0 | 2026-05-26
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5869955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141772131 | Physically Completed | 23490 | 0 | 2026-02-20 | 2026-08-23
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/5878630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147180418 | Ongoing | 27000 | 14400 | 2026-09-10
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6101573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121012235 | Ongoing | 27000 | 14400 | 2026-09-11
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6102581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894421 | Ongoing | 27000 | 14400 | 2026-09-10
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6104527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121938080 | Ongoing | 27000 | 7200 | 2026-09-10
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6105391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147218768 | Ongoing | 27000 | 14400 | 2026-09-10
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6105805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133089952 | Approved | 27000 | 0 | 2026-03-18
MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/61095 — Construction of IAY House -IAY REG. NO. MP-19-006-009-001/014 | Approved | 27000 | 0 | 2015-12-27
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/61096 — Construction of IAY House -IAY REG. NO. MP-19-006-009-001/019 | Ongoing | 27000 | 12600 | 2026-08-07
MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/61097 — Construction of IAY House -IAY REG. NO. MP-19-006-009-001/02 | Approved | 27000 | 0 | 2015-12-27
MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/61098 — Construction of IAY House -IAY REG. NO. MP-19-006-009-001/0257 | Physically Completed | 23490 | 0 | 2015-12-27 | 2026-08-02
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6110616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121025276 | Ongoing | 27000 | 21600 | 2026-08-13
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6110622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122839135 | Ongoing | 27000 | 18000 | 2026-08-13
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6110625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141895991 | Ongoing | 27000 | 14400 | 2026-09-10
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6110628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141894183 | Ongoing | 27000 | 7200 | 2026-09-10
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6273945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141895189 | Approved | 27000 | 0 | 2025-04-16
MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6276260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147262129 | Approved | 27000 | 0 | 2025-03-24
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6295935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121011728 | Approved | 27000 | 0 | 2025-04-16
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6300888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148210615 | Approved | 27000 | 0 | 2026-05-15
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6352530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148196250 | Approved | 27000 | 0 | 2026-03-18
MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6365008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148185916 | Ongoing | 27000 | 3600 | 2026-09-26
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6380938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121012507 | Approved | 27000 | 0 | 2025-04-19
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6381228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147662735 | Approved | 27000 | 0 | 2025-04-16
MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719006009/IF/IAY/6397410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122937526 | Approved | 27000 | 0 | 2026-03-18
MOMAN BADODIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719006009/RC/22012034673743 — cc road | New | 0 | 0 | 2024-01-26
MOMAN BADODIYA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719006009/RC/22012034846848 — Test ccroad | Approved | 0 | 0 | 2025-07-27
MOMAN BADODIYA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719006009/RC/22012034846859 — test c c road | Approved | 7000 | 0 | 2025-04-10
MOMAN BADODIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Terracing | 1719006009/WC/22012034726753 — Deepning and repair of flood channel kumersing ke makan se santidhamtak | Ongoing | 412218.46 | 0 | 2021-06-08
MOMAN BADODIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1719006009/WC/22012035318517 — Percolation tank | New | 0 | 0 | 2025-07-27
MOMAN BADODIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1719006009/WC/22012035318522 — Test for geotag | Approved | 10000 | 0 | 2025-07-27